## Sheet1
TX SET Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2019-07-18
Agenda Item: | Decision / Resolution | Action Items :
June 2019 Meeting Notes | No changes were made. | The Texas SET Chair will have the notes posted to the June meeting page.
Flight Update | ERCOT reviewed the flight update.
ERCOT Discussion Items
Extracts/Reports--Feedback Mapping Status Rejects 867_RCS01: 997 | • Texas SET attendees will provide feedback by the next meeting. • Mapping Status Rejects—ERCOT suggest to keep. • 867_RCS01: ERCOT suggest possible removal. • 997: ERCOT suggest possible removal.
RMS Update | No Meeting in July
RMS Assignments
946NPRR-01_Allow_TDSPs_to_Use_814_28_Complete_Un-executable_Transactions_for_814_03_Switch_Transactions_Involved_In_A_Mass_Transition_Event | • ERCOT stated that they did not have comments ready for discussion at this meeting. • The discussion is delayed for a future meeting.
Joint Effort with TDTMS to investigate testing requirements: ERCOT can gain efficiencies, reduce risk, and lessen the overall impact to the market by combining the testing of these 2 systems Projects update for 2020: --EDI translator (PR288-01), Business drivers are reliability and supportability --NAESB (project number: TBD) Business driver is security | • ERCOT stated that the plan for the upgrades for both the EDI translator and the NAESB upgrades to go in at the same time. • ERCOT also stated that they plan to implement these changes approximately August 1, 2020 and that the market will have to test the changes. • EDI translator (PR288-01), Business drivers are reliability and supportability • Texas SET continued to review the list and enter recommendations as needed. • NAESB (project number: TBD); Business driver is security.--This topic will be discussed at the Texas Data Transport and MarkeTrak Systems (TDTMS) meeting. ERCOT noted that they will be upgrading the TLS to version 1.2.
Change Control Call--No Call This Month | Change Controls on the ERCOT Website. http://www.ercot.com/mktrules/issues/txsetcc
Issues | Issues on the ERCOT Website http://www.ercot.com/mktrules/issues/txset
NRG draft Issue--11.4.3 REP Operating Rule 5: Establish Continuous Service Agreement After Move Out Results in De-energized Premise | • NRG stated that the issue they have experienced is where they have a CSA agreement in place at ERCOT, but a new CSA agreement takes place between the time that a Move out is submitted and scheduled as a Move out to CSA and the completion date. • The Move out to CSA is scheduled and completed to the previous CSA REP which no longer has a binding contract with the landlord. • The issue is that the ESI ID should be with the new CSA REP. • The group discussed possible solutions which included the previous CSA REP sending another Move out that would result in a Move out to CSA for the new CSA REP. | NRG will submit an official issue for the August meeting to facilitate further discussion.
Discussion Items
ONCOR draft Change Controls review Construction Hold Add Email on 814_01, 814_03, and 814_16 | • Construction Hold • ONCOR stated that they still support using the 814_28 Construction Hold option, but has agreed to investigate the possibility of using the 814_04 with a new code (long term) in the Status Reason. The short term solution will be to utilized the existing A13 Other code with text explaining the Construction Hold use. • Texas SET attendees expressed a preference for the 814_04 option as the resulting impacts will be fewer. • Add Email on 814_01, 814_03, and 814_16 • ONCOR agreed to submit changes mimicking the 814_PC use of the email section for Outage contacts. • Texas SET attendees agreed that the new use will be optional to allow the individual CRs to determine if they can legally provide the information to the TDSP with the understanding that the information will only be used for outage notifications. | ONCOR will bring redlines to the August meeting for further discussion on both proposals.
RMG Safety NET Timelines Language Changes--Discuss Feedback | Texas SET finalized the review and changes. | The Texas SET Chair will submit the changes to the ERCOT Revision Request site to obtain an official Retail Market Guide Revision Request to be considered at the next RMS meeting.
Testing • Texas Market Test Plan (TMTP) Changes • Future Flight Schedules Review • REP Certification Matrix – Long Term | • Texas SET Leadership continued to discuss changes needed in the Texas Market Test Plan (TMTP) and made additional changes as necessary. • Texas SET will complete a final review at the August meeting. • Texas SET Leadership conducted a discussion related to the ERCOT provided Proposed 2020 Flight Schedule. • Texas SET and ERCOT agreed to update the proposed schedule after the TMTP changes are submitted for approval. • REP Certification Matrix – Long Term • Discussion is delayed on this topic to a future meeting | TMTP • The Texas SET Chair will send the updated documents to the Texas SET email distribution list for review.
Other Business
September Meeting Moving to the 17th--ERCOT feedback |  | The Texas SET Chair will submit the change to ERCOT to move the September meeting from the 18th to the 17th.
Centerpoint Energy 810_02 SAC04 Code update. | Centerpoint Energy provided an update on their planned use of SAC04 codes in the 810_02 Invoice and took related questions from the meeting attendees.
Parking Lot
Plans for Texas SET Release Update
Proposed Texas SET Release Changes.— Continue Discussion and Review 650 RCxxx and DCxxx Purpose Code Matrix
MISP Workshop Action Items • Add a MISP definition in RMG (RMGRR)
Next Meeting--ERCOT MET Center 102 | 2019-08-21
Attendees F-T-F (*) denotes attendance both days
Diana Rehfeldt TNMP | Kathy Scott Centerpoint Energy
Becky Taylor Centerpoint Energy | Sam Pak ONCOR
Kyle Patrick NRG | Jim Lee AEP
David Michelsen ERCOT
Jordon Troublefield ERCOT
Attendees Webex (*) denotes attendance both days
Kim Wall Hansen Technologies | Sai Madhuri Malladi EC InfoSystems
Kaci Jacobs TXUE
Paul Yockey ERCOT
Frank Nunes EC InforSystems
Deb Belin MarketWise