## Sheet1
TX SET Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2019-08-21
Agenda Item: | Decision / Resolution | Action Items :
July 2019 Meeting Notes | No changes were made. | The Texas SET Chair will have the notes posted to the July meeting page.
Flight Update | ERCOT noted that there were no updates to the status since those provided at the August 6, 2019 Retail Market Subcommittee (RMS) meeting.
Flight Script CON01, TDSP loads ESI ID test bed change | • It was noted that the TDSP no longer emails the ESI ID test bed to ERCOT, but uploads this through the FlighTrak tool. • The script will be updated to reflect this change. | Texas SET will review this change at the September meeting.
ERCOT Discussion Items
Extracts/Reports--Feedback Mapping Status Rejects 867_RCS01: 997 | • Texas SET attendees will provide feedback by the next meeting. • Mapping Status Rejects—ERCOT suggest to keep. • 867_RCS01: ERCOT suggest possible removal. • 997: ERCOT suggest possible removal.
Texas SET EDI Questions—Living Document Discussion | • Texas SET agreed to have ERCOT add the term "only one allowed" in the Gray boxes for segments where only one use is allowed per type per the Texas SET rules; but greater than one use is allowed by ANSI standards. • 814_16 Move-in Requests required REF~PH Priority Code segment. • Texas SET members discussed the possible adverse effects related to having ERCOT begin validating that the Segment is present in all 814_16s. • An increase in the number of rejects is predicted if ERCOT begins validating that the segment is present. • This adversely affects the ability to get the power on to customers for those CRs that are not currently compliant to the guides. • Texas SET members noted that the 814_03 only requires the Segment if the CR is requesting a same-day move-in. | Texas SET members will discuss internally to determine if a request to have ERCOT change the guides to show this segment is optional will affect anything internally or not. Feedback will be provided at the September meeting.
NAESB (project number: TBD); Business driver is security—Possible testing specs collaboration with TDTMS | • ERCOT stated that they will test this change at the same time as changes to EDI are tested. • ERCOT stated that they will update the Transport Layer Security (TLS) version to 1.2 from 1.0. • ERCOT will not support version 1.0 once the version 1.2 in implemented. • ERCOT will provide a market notice prior to the go-live date.
RMS Update
NPRR946, Allow TDSPs to Use 814_28, Complete Un-executable Transactions for 814_03 Switch Transactions Involved in a Mass Transition Event—RMS voted to request the PRS to table. RMGRR161, Clarifications to Content of Notice to Affected Parties of a Mass Transition—RMS voted to approve. FYI Only ERCOT suggested that anyone that wants to retain information currently only available at the ETOD (old ERCOT Testing webpage), to do so in the next month or so. ERCOT will be decommissioning the site in the near future; but will provide a 30 day notice prior to doing so.
RMS Assignments
946NPRR-01_Allow_TDSPs_to_Use_814_28_Complete_Un-executable_Transactions_for_814_03_Switch_Transactions_Involved_In_A_Mass_Transition_Event | • ERCOT stated that they did not have comments ready for discussion at this meeting. • The discussion is delayed for a future meeting.
Annual TAC/TAC Subcommittee Structural and Procedural Review: September 17th WebEx only | Texas SET agreed that no changes will be needed at this time. | The RMS Chair will provide this information at the September 17, 2019 Technical Advisory Committee (TAC) workshop
Change Control Call-- 10:00 AM | Change Controls on the ERCOT Website. http://www.ercot.com/mktrules/issues/txsetcc
ChangeControl2019_808_New—add new SAC04 code that uniquely identifies “Pole Attachment Service Charge | Texas SET reached consensus on the language changes and the urgent status; then requested that the recommendation be presented to RMS to approve both the change control and the Texas SET Implementation Guide redlines. | ERCOT to present at RMS.
Issues | Issues on the ERCOT Website http://www.ercot.com/mktrules/issues/txset
2019-I149 Recommend revision to Continuous Service Agreement (CSA) process surrounding Solution to Stacking REP Rules 5 and 6. | • Texas SET and ERCOT discussed possible solutions. • Option 1: Let the Move-out get scheduled; then have ERCOT check for an active CSA CR within a 2 day window of the scheduled Move-out date. If an agreement exists, ERCOT will send the 814_03 Move-out to CSA transaction to override the Move-out. • Option 2: Execute the process as it exists today, scheduling the Move-out to CSA; then check for a change in the current CSA within a 2 day window of the scheduled Move-out date. If there was a change; ERCOT will cancel the first Move-out to CSA and re-submit another Move-Out to CSA for the current CSA CR. • ERCOT stated that Option 2 would be a better way to make the changes. • It was suggested to add an effective date to the 814_18 to specify when the CSA agreement begins. | • The Texas SET Chair will send the updated issue to ERCOT and will continue to conduct discussion for these changes as a part of a Texas SET Release
Discussion Items
ONCOR draft Change Controls review Construction Hold Add Email on 814_01, 814_03, and 814_16 | • Construction Hold • ONCOR changed the draft change control to add a new REF~1P code (CHP) to the 814_04, Enrollment Notification Response and 814_05, CR Enrollment Notification Response. • ONCOR will submit an official change control to ERCOT in order to be reviewed for consensus at the September 17, 2019 Texas SET meeting. • Add Email on 814_01, 814_03, and 814_16 • Texas SET suggested that separate PER segments be added to the transactions for the different types of communication channels. • ONCOR and the other attendees will review this option and provide feedback at the next meeting.
Testing • Texas Market Test Plan (TMTP) Changes • Future Flight Schedules Review • REP Certification Matrix – Long Term | • TMTP • Texas SET members completed the review and updates to the document. • Future Flight Schedules Review • Texas SET reviewed the updated 2020 Flight Schedule and made additional changes as needed. • REP Certification Matrix – Long Term • Discussion is delayed on this topic to a future meeting | TMTP • The Texas SET Chair will send the updated documents to the Texas SET email distribution list for review. Proposed 2020 Flight Schedule. • The Texas SET Chair will send the updated version to ERCOT for further updates; then return to the Texas SET Leadership for distribution to the Texas SET email distribution list.
Other Business
FlighTrak enhancement update. | · ERCOT stated that they are rolling all user accounts to a counter party instead of the individual DUNS for each entity. This will assist entities with multiple DUNS.
Add a County code to the Customer Service Address in the N1~8R loop of the 814_04 Enrollment Notification Response, 814_05, CR Enrollment Notification Response, 814_14, Drop Enrollment Request, and 814_20, ESI ID Maintenance Request. | • A suggestion was to add the N405 with the “CO” qualifier and N406 with a “County Code” elements to the N4 Customer Service Address segment of the N1~8R Customer loop. • One option for populating the “County Code” is to use with the National Weather Service reports for each county. | • Texas SET members will discuss internally and provide feedback at the September meeting
Parking Lot
Plans for Texas SET Release Update
Proposed Texas SET Release Changes.— Continue Discussion and Review 650 RCxxx and DCxxx Purpose Code Matrix
MISP Workshop Action Items • Add a MISP definition in RMG (RMGRR)
Next Meeting--ERCOT MET Center 102 | 2019-09-17
Attendees F-T-F
Diana Rehfeldt TNMP | Kathy Scott Centerpoint Energy
Becky Taylor Centerpoint Energy | Stephen Wilson TXUE
Kyle Patrick NRG | Sam Pak ONCOR
John Schatz TXUE | Jim Lee AEP
Jordon Troublefield ERCOT | Dave Michelsen ERCOT
Kathryn Thurman ERCOT
Attendees Webex
Tyler K. Big Data Energy | Deb Belin MarketWise
Eric Blakey Just Energy | Teresa Rodriguez Stream Energy
Paul Yockey ERCOT | Frank Hunes EcInfoSysems
Kim Wall Hansen Technology | Connie Hermes NEC
Mike Woolsey ONCOR | Tequila Rheems Constellation NE