## Wind Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 17INR0061 | Capricorn IV repower | Sterling | 2018-11-01 | 2008-01-15 | Wind | WT | 9 | 2018 | No
[6 empty] | 17INR0005 | Cabezon Wind | Anderson | 2019-08-16 | 2017-08-03 | Wind | WT | 237.6 | 2019 | Yes
[6 empty] | 18INR0078 | Bobcat Bluff repower | Archer | 2019-08-23 | 2018-12-18 | Wind | WT | 12 | 2019 | No
[6 empty] | 18INR0067 | Gopher Creek Wind | Borden | 2019-08-30 | 2018-01-26 | Wind | WT | 158 | 2019 | Yes
[6 empty] | 18INR0033 | Oveja Wind | Irion | 2019-09-06 | 2018-07-24 | Wind | WT | 300 | 2019 | Yes
[6 empty] | 13INR0026 | Canadian Breaks Wind | Oldham | 2019-09-13 | 2016-05-20 | Wind | WT | 210 | 2019 | Yes
[6 empty] | 11INR0062 | Shaffer | Nueces | 2019-09-15 | 2013-07-02 | Wind | WT | 226 | 2019 | Yes
[6 empty] | 19INR0019 | Foard City Wind | Foard | 2019-09-24 | 2018-11-06 | Wind | WT | 350 | 2019 | Yes
[6 empty] | 16INR0062b | Lockett Wind | Wilbarger | 2019-09-30 | 2015-03-31 | Wind | WT | 184 | 2019 | Yes
[6 empty] | 17INR0069 | Trent repower | Nolan | 2019-09-30 | 2018-10-19 | Wind | WT | 6.4 | 2019 | No
[6 empty] | 17INR0070 | Desert Sky repower | Pecos | 2019-09-30 | 2018-10-18 | Wind | WT | 7.2 | 2019 | Yes
[6 empty] | 20INR0011 | Ranchero Wind | Crockett | 2019-09-30 | 2018-05-02 | Wind | WT | 300 | 2019 | Yes
[6 empty] | 16INR0086 | Cactus Flats Wind | Concho | 2019-10-15 | 2017-03-15 | Wind | WT | 148.4 | 2019 | Yes
[6 empty] | 19INR0174 | Elbow Creek repower | Howard | 2019-10-15 | 2007-11-30 | Wind | WT | 0 | 2019 | No
[6 empty] | 14INR0045 | Torrecillas Wind | Webb | 2019-10-17 | 2018-04-12 | Wind | WT | 300.5 | 2019 | Yes
[6 empty] | 12INR0060 | Wilson Ranch | Schleicher | 2019-10-31 | 2018-05-21 | Wind | WT | 199.5 | 2019 | Yes
[6 empty] | 17INR0052 | Horse13 CallD repower | Taylor | 2019-11-01 | 2019-05-22 | Wind | WT | 44 | 2019 | Yes
[6 empty] | 19INR0182 | Blue Summit Wind III | Wilbarger | 2019-11-01 | 2019-04-09 | Wind | WT | 200 | 2019 | Yes
[6 empty] | 18INR0014 | Karankawa Wind | San Patricio | 2019-11-11 | 2017-11-30 | Wind | WT | 206.64 | 2019 | Yes
[6 empty] | 19INR0053 | Hidalgo II Wind | Hidalgo | 2019-11-15 | 2019-04-25 | Wind | WT | 51 | 2019 | Yes
[6 empty] | 19INR0074 | Karankawa 2 Wind | San Patricio | 2019-11-26 | 2018-02-08 | Wind | WT | 101 | 2019 | Yes
[6 empty] | 17INR0067 | Sweetwater 1 repower | Nolan | 2019-11-30 | Date Not Available | Wind | WT | 0 | 2019 | Yes
[6 empty] | 17INR0068 | Sweetwater 2 repower | Nolan | 2019-11-30 | 2017-11-17 | Wind | WT | 7.3 | 2019 | No
[6 empty] | 17INR0104 | Capricorn 4 repower | Coke | 2019-11-30 | 2018-05-01 | Wind | WT | 0 | 2019 | No
[6 empty] | 17INR0054 | Capricorn I & III repower | Sterling | 2019-12-01 | 2006-11-14 | Wind | WT | 32 | 2019 | No
[6 empty] | 18INR0018 | Peyton Creek Wind | Matagorda | 2019-12-01 | 2018-03-19 | Wind | WT | 151.2 | 2019 | Yes
[6 empty] | 18INR0070 | Blue Summit II | Wilbarger | 2019-12-13 | 2018-11-09 | Wind | WT | 102 | 2019 | Yes
[6 empty] | 15INR0064b | Harald (BearKat Wind B) | Glasscock | 2019-12-20 | 2018-05-30 | Wind | WT | 162.1 | 2019 | Yes
[6 empty] | 17INR0037 | Palmas Altas Wind | Cameron | 2019-12-31 | 2017-11-30 | Wind | WT | 144.9 | 2019 | Yes
[6 empty] | 18INR0069 | Indian Mesa repower | Pecos | 2019-12-31 | 2018-12-04 | Wind | WT | 0 | 2019 | No
[6 empty] | 18INR0079 | Woodward I repower | Pecos | 2019-12-31 | 2018-12-12 | Wind | WT | 0 | 2019 | No
[6 empty] | 18INR0080 | Woodward 2 repower | Pecos | 2019-12-31 | 2018-12-18 | Wind | WT | 0 | 2019 | No
[6 empty] | 19INR0038 | High Lonesome W | Crockett | 2019-12-31 | 2018-04-17 | Wind | WT | 449.5 | 2019 | Yes
[6 empty] | 19INR0112 | Cranel Wind | Refugio | 2019-12-31 | 2018-10-12 | Wind | WT | 220 | 2019 | Yes
[6 empty] | 20INR0262 | High Lonesome Wind Phase II | Crockett | 2020-01-30 | 2019-07-22 | Wind | WT | 50.6 | 2020 | Yes
[6 empty] | 19INR0080 | Whitehorse Wind | Fisher | 2020-02-04 | 2018-12-05 | Wind | WT | 418.9 | 2020 | Yes
[6 empty] | 18INR0038 | Barrow Ranch | Andrews | 2020-02-27 | 2018-06-26 | Wind | WT | 160 | 2020 | Yes
[6 empty] | 16INR0081 | Mesteno Windpower | Starr | 2020-03-01 | 2018-04-25 | Wind | WT | 201.6 | 2020 | Yes
[6 empty] | 18INR0029 | Armstrong Wind | Armstrong | 2020-03-31 | 2018-08-31 | Wind | WT | 253 | 2020 | No
[6 empty] | 19INR0163 | Sage Draw Wind | Lynn | 2020-03-31 | 2018-01-03 | Wind | WT | 338 | 2020 | Yes
[6 empty] | 14INR0009 | WKN Amadeus Wind | Fisher | 2020-05-15 | 2018-03-15 | Wind | WT | 245.9 | 2020 | Yes
[6 empty] | 18INR0075 | Gulf Wind 1 repower | Kenedy | 2020-06-01 | 2007-08-28 | Wind | WT | 0 | 2020 | No
[6 empty] | 18INR0059 | East Raymond Wind | Willacy | 2020-06-30 | 2018-09-18 | Wind | WT | 201.6 | 2020 | Yes
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned | 19INR0051 | Vera Wind | Knox | 2020-07-01 | 2018-07-10 | Wind | WT | 242.8 | 2020 | Yes
2000 | 116 | 116 | 0 | 0 | 0 | 18INR0016 | RTS 2 Wind | McCulloch | 2020-07-10 | 2017-11-21 | Wind | WT | 179.91 | 2020 | Yes
2001 | 816 | 816 | 0 | 0 | 0 | 18INR0064 | Silver Star repower | Eastland | 2020-08-10 | 2018-10-16 | Wind | WT | -7.2 | 2020 | No
2002 | 977 | 977 | 0 | 0 | 0 | 19INR0120 | Sherbino II Wind repower | Pecos | 2020-08-10 | 2008-02-28 | Wind | WT | -13 | 2020 | No
2003 | 1173 | 1173 | 0 | 0 | 0 | 20INR0019 | Trinity Hills Wind repower | Young | 2020-08-10 | 2018-10-17 | Wind | WT | -27 | 2020 | No
2004 | 1385 | 1385 | 0 | 0 | 0 | 18INR0043 | Edmondson Ranch Wind | Glasscock | 2020-09-01 | 2017-10-04 | Wind | WT | 292.5 | 2020 | Yes
2005 | 1854 | 1854 | 0 | 0 | 0 | 19INR0100 | Prairie Hill Wind | McLennan | 2020-09-01 | 2018-09-17 | Wind | WT | 300 | 2020 | Yes
2006 | 2875 | 2875 | 0 | 0 | 0 | 20INR0045 | Maverick Creek I | Concho | 2020-09-01 | 2018-07-30 | Wind | WT | 373.2 | 2020 | Yes
2007 | 4785 | 4785 | 0 | 0 | 0 | 17INR0027b | Coyote Wind | Scurry | 2020-09-15 | 2016-08-09 | Wind | WT | 242.5 | 2020 | Yes
2008 | 8005 | 8005 | 0 | 0 | 0 | 19INR0128 | White Mesa Wind | Crockett | 2020-09-30 | 2018-12-19 | Wind | WT | 500 | 2020 | Yes
2009 | 8916 | 8916 | 0 | 0 | 0 | 20INR0052 | Griffin Trail Wind | Knox | 2020-09-30 | 2019-03-04 | Wind | WT | 201.6 | 2020 | No
2010 | 9400 | 9400 | 0 | 0 | 0 | 17INR0035 | Las Majadas Wind | Willacy | 2020-10-01 | 2018-04-13 | Wind | WT | 272.8 | 2020 | Yes
2011 | 9604 | 9604 | 0 | 0 | 0 | 19INR0052 | TG East Wind | Knox | 2020-10-01 | 2018-10-22 | Wind | WT | 275.6 | 2020 | Yes
2012 | 10407 | 10407 | 0 | 0 | 0 | 19INR0156 | Grape Creek Wind | Coke | 2020-10-01 | 2019-02-14 | Wind | WT | 525 | 2020 | No
2013 | 11065 | 11065 | 0 | 0 | 0 | 13INR0010a | Mariah Del Este | Parmer | 2020-10-30 | 2013-01-31 | Wind | WT | 152.5 | 2020 | Yes
2014 | 12470 | 12470 | 0 | 0 | 0 | 17INR0025 | Reloj Del Sol Wind | Zapata | 2020-10-31 | 2018-12-21 | Wind | WT | 202 | 2020 | Yes
2015 | 15764 | 15764 | 0 | 0 | 0 | 14INR0030c | Panhandle Wind 3 | Carson | 2020-12-01 | 2014-08-25 | Wind | WT | 248 | 2020 | Yes
2016 | 17604 | 17604 | 0 | 0 | 0 | 16INR0037c | Pumpkin Farm Wind | Floyd | 2020-12-01 | 2017-03-24 | Wind | WT | 280.9 | 2020 | Yes
2017 | 20682 | 20682 | 0 | 0 | 0 | 16INR0111 | Las Lomas Wind | Starr | 2020-12-01 | 2018-12-22 | Wind | WT | 200 | 2020 | Yes
2018 | 21751 | 21751 | 0 | 0 | 0 | 18INR0042 | Kaiser Creek Wind | Callahan | 2020-12-01 | 2019-07-11 | Wind | WT | 101.52 | 2020 | No
2019 | 26764.28 | 22244.04 | 4453.54 | 66.7 | 0 | 14INR0033 | Goodnight Wind | Armstrong | 2020-12-12 | 2018-03-07 | Wind | WT | 504.4 | 2020 | No
2020 | 34095.71 | 22244.04 | 10246.65 | 1605.02 | 0 | 20INR0042 | Chalupa Wind | Cameron | 2020-12-21 | 2018-09-28 | Wind | WT | 174 | 2020 | Yes
2021 | 36015.76 | 22244.04 | 11349.2 | 2422.52 | 0 | 20INR0088 | West Raymond (El Trueno) Wind | Willacy | 2020-12-31 | 2019-05-20 | Wind | WT | 239.8 | 2020 | Yes
2022 | 36271.06 | 22244.04 | 11604.5 | 2422.52 | 0 | 18INR0068 | Loraine Windpark Phase III | Mitchell | 2021-05-01 | 2018-04-10 | Wind | WT | 100 | 2021 | Yes
[6 empty] | 20INR0083 | Baird North Wind | Callahan | 2021-06-15 | 2019-05-31 | Wind | WT | 293.55 | 2021 | Yes
[6 empty] | 19INR0099a | Kontiki 1 Wind (ERIK) | Glasscock | 2021-06-30 | 2018-05-07 | Wind | WT | 255.3 | 2021 | Yes
[6 empty] | 18INR0030 | Canyon Wind | Scurry | 2021-08-01 | 2018-09-20 | Wind | WT | 360 | 2021 | No
[6 empty] | 20INR0046 | Maverick Creek II | Concho | 2021-09-01 | 2018-07-30 | Wind | WT | 151.2 | 2021 | Yes
[6 empty] | 15INR0063 | Easter Wind | Castro | 2021-10-31 | 2018-06-01 | Wind | WT | 307.5 | 2021 | No
[6 empty] | 13INR0038 | Wildrose Wind | Swisher | 2021-12-30 | 2015-09-06 | Wind | WT | 302.5 | 2021 | Yes
[6 empty] | 16INR0033 | Hart Wind | Castro | 2021-12-31 | 2018-08-06 | Wind | WT | 150 | 2021 | No
[6 empty] | 19INR0099b | Kontiki 2 Wind (ERNEST) | Glasscock | 2022-06-30 | 2018-05-07 | Wind | WT | 255.3 | 2022 | Yes

## Solar Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 19INR0184 | Oxy Solar | Ector | 2019-08-01 | 2019-01-30 | Solar | PV | 16.2 | 2019 | Yes
[6 empty] | 19INR0029 | Phoebe Solar | Winkler | 2019-09-30 | 2018-03-05 | Solar | PV | 250 | 2019 | Yes
[6 empty] | 18INR0045 | Misae Solar | Childress | 2019-11-19 | 2018-07-18 | Solar | PV | 240.8 | 2019 | Yes
[6 empty] | 14INR0044 | West of Pecos Solar | Reeves | 2019-12-20 | 2019-02-05 | Solar | PV | 100 | 2019 | Yes
[6 empty] | 16INR0019 | BlueBell Solar | Coke | 2019-12-31 | 2015-08-19 | Solar | PV | 30 | 2019 | Yes
[6 empty] | 19INR0102 | Queen Solar | Upton | 2019-12-31 | 2018-09-26 | Solar | PV | 400 | 2019 | Yes
[6 empty] | 19INR0185 | Lapetus Solar | Andrews | 2019-12-31 | 2018-12-21 | Solar | PV | 100 | 2019 | Yes
[6 empty] | 19INR0083 | Oberon Solar | Ector | 2020-03-09 | 2018-10-11 | Solar | PV | 180 | 2020 | Yes
[6 empty] | 19INR0114 | Rambler Solar | Tom Green | 2020-05-31 | 2018-10-11 | Solar | PV | 200 | 2020 | Yes
[6 empty] | 18INR0062 | Wagyu Solar | Brazoria | 2020-06-01 | 2019-06-03 | Solar | PV | 121.9 | 2020 | No
[6 empty] | 19INR0009 | Holstein Solar | Nolan | 2020-06-01 | 2018-09-15 | Solar | PV | 204.47 | 2020 | Yes
[6 empty] | 18INR0039 | Fowler Ranch | Crane | 2020-06-03 | 2018-10-23 | Solar | PV | 152.5 | 2020 | Yes
[6 empty] | 19INR0073 | Shakes Solar | Zavala | 2020-06-24 | 2018-10-26 | Solar | PV | 206 | 2020 | Yes
[6 empty] | 18INR0055 | Long Draw Solar | Borden | 2020-06-30 | 2018-08-16 | Solar | PV | 225 | 2020 | Yes
[6 empty] | 19INR0092 | Prospero Solar | Andrews | 2020-06-30 | 2018-04-20 | Solar | PV | 300 | 2020 | Yes
[6 empty] | 19INR0151 | Impact Solar | Lamar | 2020-07-01 | 2019-07-02 | Solar | PV | 198.55 | 2020 | No
[6 empty] | 17INR0020a | RE Maplewood 2a Solar | Pecos | 2020-07-15 | 2019-05-06 | Solar | PV | 222 | 2020 | Yes
[6 empty] | 16INR0114 | Upton Solar | Upton | 2020-09-01 | 2015-12-04 | Solar | PV | 104.56 | 2020 | Yes
[6 empty] | 19INR0034 | Greasewood Solar | Pecos | 2020-09-30 | 2019-01-25 | Solar | PV | 200 | 2020 | No
[6 empty] | 18INR0053 | Fort Bend Solar | Fort Bend | 2020-10-30 | 2019-06-30 | Solar | PV | 240 | 2020 | No
[6 empty] | 19INR0044 | Lily Solar | Kaufman | 2020-12-01 | 2019-03-29 | Solar | PV | 150 | 2020 | No
[6 empty] | 20INR0054 | Taygete Solar | Pecos | 2020-12-01 | 2018-10-26 | Solar | PV | 255.12 | 2020 | Yes
[6 empty] | 20INR0021 | Garnet Solar | Williamson | 2020-12-18 | 2019-04-30 | Solar | PV | 20 | 2020 | No
[6 empty] | 15INR0090 | Pflugerville Solar | Travis | 2020-12-31 | 2017-06-13 | Solar | PV | 144 | 2020 | No
[6 empty] | 17INR0020b | RE Maplewood 2b Solar | Pecos | 2020-12-31 | 2019-05-06 | Solar | PV | 28 | 2020 | Yes
[6 empty] | 19INR0045 | Rayos Del Sol | Cameron | 2020-12-31 | 2018-11-06 | Solar | PV | 150 | 2020 | Yes
[6 empty] | 19INR0081 | Anson Solar | Jones | 2020-12-31 | 2019-06-05 | Solar | PV | 200 | 2020 | Yes
[6 empty] | 20INR0031 | Rippey Solar | Cooke | 2020-12-31 | 2019-05-15 | Solar | PV | 60 | 2020 | No
[6 empty] | 20INR0091 | Misae Solar II | Childress | 2020-12-31 | 2019-02-21 | Solar | PV | 517.35 | 2020 | Yes
[6 empty] | 15INR0059 | Emerald Grove Solar | Pecos | 2021-04-10 | 2018-06-27 | Solar | PV | 108 | 2021 | Yes
[6 empty] | 18INR0050 | Mustang Creek Solar | Jackson | 2021-05-01 | 2019-01-04 | Solar | PV | 150 | 2021 | No
[6 empty] | 21INR0276 | Elara Solar | Frio | 2021-05-01 | 2019-07-12 | Solar | PV | 178 | 2021 | No
[6 empty] | 19INR0103 | Rodeo Solar | Andrews | 2021-05-15 | 2019-08-20 | Solar | PV | 205 | 2021 | No
[6 empty] | 21INR0026 | Juno Solar | Borden | 2021-05-15 | 2018-12-28 | Solar | PV | 313.2 | 2021 | No
[6 empty] | 16INR0049 | Nazareth Solar | Castro | 2021-05-31 | 2018-05-10 | Solar | PV | 201 | 2021 | Yes
[6 empty] | 18INR0040 | Soda Lake Solar 1 | Crane | 2021-05-31 | 2018-08-20 | Solar | PV | 202.59 | 2021 | No
[6 empty] | 20INR0143 | Soda Lake Solar 2 | Crane | 2021-05-31 | 2018-08-20 | Solar | PV | 202.99 | 2021 | No
[6 empty] | 17INR0020c | RE Maplewood 2c Solar | Pecos | 2021-06-01 | 2019-05-06 | Solar | PV | 250 | 2021 | Yes
[6 empty] | 19INR0001 | Texas Solar Nova | Kent | 2021-06-01 | 2019-06-28 | Solar | PV | 252.2 | 2021 | No
[6 empty] | 19INR0035 | Norton Solar | Runnels | 2021-06-01 | 2019-06-20 | Solar | PV | 125 | 2021 | Yes
[6 empty] | 19INR0121 | Galloway Solar | Concho | 2021-06-01 | 2019-03-28 | Solar | PV | 250 | 2021 | No
[6 empty] | 21INR0233 | Taygete II Solar | Pecos | 2021-06-01 | 2019-03-27 | Solar | PV | 256.25 | 2021 | Yes
[6 empty] | 19INR0088 | Aragorn Solar | Culberson | 2021-06-30 | 2018-05-31 | Solar | PV | 186.3 | 2021 | No
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned | 20INR0032 | IP Titan | Culberson | 2021-06-30 | 2019-02-04 | Solar | PV | 272 | 2021 | No
2010 | 15 | 15 | 0 | 0 | 0 | 21INR0261 | Horizon Solar | Frio | 2021-12-31 | 2019-07-12 | Solar | PV | 204.09 | 2021 | Yes
2011 | 42 | 42 | 0 | 0 | 0
2012 | 82 | 82 | 0 | 0 | 0
2013 | 121 | 121 | 0 | 0 | 0
2014 | 193 | 193 | 0 | 0 | 0
2015 | 287.7 | 287.7 | 0 | 0 | 0
2016 | 566.4 | 566.4 | 0 | 0 | 0
2017 | 1068.7 | 1068.7 | 0 | 0 | 0
2018 | 1857.7 | 1857.7 | 0 | 0 | 0
2019 | 3014.68 | 1877.68 | 1137 | 0 | 0
2020 | 7094.13 | 1877.68 | 4082 | 1134.45 | 0
2021 | 10450.75 | 1877.68 | 5226.34 | 3346.73 | 0

## Battery Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned
2012 | 36 | 36 | 0 | 0 | 0
2013 | 36 | 36 | 0 | 0 | 0
2014 | 36 | 36 | 0 | 0 | 0
2015 | 36 | 36 | 0 | 0 | 0
2016 | 37 | 37 | 0 | 0 | 0
2017 | 69 | 69 | 0 | 0 | 0
2018 | 89 | 89 | 0 | 0 | 0
2019 | 163.4 | 103.9 | 0 | 0 | 59.5
2020 | 165.65 | 103.9 | 0 | 0 | 61.75

## Gas-Combined Cycle Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 16INR0054 | NA | Harris | 2018-09-01 | 2016-10-27 | Gas | CC | 12 | 2018 | Yes
[6 empty] | 19INR0205 | RIO NOGALES AGP UPGRADE CT1 | Guadalupe | 2019-06-30 | 2000-04-21 | Gas | CC | 19 | 2019 | Yes
[6 empty] | 18INR0077 | Colorado Bend 2 repower | Wharton | 2019-09-15 | 2015-12-17 | Gas | CC | 45 | 2019 | No
[6 empty] | 19INR0014 | Formosa Increase | Calhoun | 2019-12-31 | 2019-04-30 | Gas | CC | 240 | 2019 | Yes
[6 empty] | 20INR0272 | RIO NOGALES AGP UPGRADE CT3 | Guadalupe | 2020-04-20 | 2000-04-21 | Gas | CC | 19 | 2020 | Yes
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned
1999 | 2867 | 2867 | 0 | 0 | 0
2000 | 7381 | 7381 | 0 | 0 | 0
2001 | 13967 | 13967 | 0 | 0 | 0
2002 | 18443 | 18443 | 0 | 0 | 0
2003 | 24141 | 24141 | 0 | 0 | 0
2004 | 25641 | 25641 | 0 | 0 | 0
2005 | 25539 | 25539 | 0 | 0 | 0
2006 | 26258 | 26258 | 0 | 0 | 0
2007 | 26815 | 26815 | 0 | 0 | 0
2008 | 27376 | 27376 | 0 | 0 | 0
2009 | 28309 | 28309 | 0 | 0 | 0
2010 | 29770 | 29770 | 0 | 0 | 0
2011 | 30488 | 30488 | 0 | 0 | 0
2012 | 30488 | 30488 | 0 | 0 | 0
2013 | 30538 | 30538 | 0 | 0 | 0
2014 | 33080 | 33080 | 0 | 0 | 0
2015 | 33897 | 33897 | 0 | 0 | 0
2016 | 33515 | 33515 | 0 | 0 | 0
2017 | 35465 | 35465 | 0 | 0 | 0
2018 | 35465 | 35465 | 0 | 0 | 0
2019 | 35861 | 35545 | 271 | 45 | 0
2020 | 35880 | 35545 | 290 | 45 | 0

## Gas-Other Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 17INR0045 | VictPort | Calhoun | 2019-08-09 | 2018-03-06 | Gas | GT | 100 | 2019 | Yes
[6 empty] | 18INR0035 | CityVict | Refugio | 2019-09-30 | 2018-03-06 | Gas | GT | 100 | 2019 | Yes
[6 empty] | 16INR0076 | Hudson (Ineos/Brazoria) | Brazoria | 2019-10-31 | 2017-12-05 | Gas | GT | 96 | 2019 | Yes
[6 empty] | 16INR0003 | LEVEE (Freeport LNG) | Brazoria | 2019-12-15 | 2014-01-13 | Gas | GT | 11 | 2019 | Yes
[6 empty] | 17INR0022 | MIRAGE | Harris | 2020-02-07 | 2016-08-31 | Gas | GT | 11 | 2020 | Yes
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned
1999 | 33703 | 33703 | 0 | 0 | 0
2000 | 33703 | 33703 | 0 | 0 | 0
2001 | 34170 | 34170 | 0 | 0 | 0
2002 | 34170 | 34170 | 0 | 0 | 0
2003 | 34118 | 34118 | 0 | 0 | 0
2004 | 32616 | 32616 | 0 | 0 | 0
2005 | 31217 | 31217 | 0 | 0 | 0
2006 | 30774 | 30774 | 0 | 0 | 0
2007 | 29048 | 29048 | 0 | 0 | 0
2008 | 28681 | 28681 | 0 | 0 | 0
2009 | 23651 | 23651 | 0 | 0 | 0
2010 | 20937 | 20937 | 0 | 0 | 0
2011 | 20575 | 20575 | 0 | 0 | 0
2012 | 20551 | 20551 | 0 | 0 | 0
2013 | 20026 | 20026 | 0 | 0 | 0
2014 | 19917 | 19917 | 0 | 0 | 0
2015 | 18538 | 18538 | 0 | 0 | 0
2016 | 19564 | 19564 | 0 | 0 | 0
2017 | 18818 | 18818 | 0 | 0 | 0
2018 | 19562 | 19562 | 0 | 0 | 0
2019 | 19493.3 | 19186.3 | 307 | 0 | 0
2020 | 19504.3 | 19186.3 | 318 | 0 | 0
2021 | 19504.3 | 19186.3 | 318 | 0 | 0