## Slide 1
Resource Integration Workshop
Resource Integration Topics
ERCOT
Jay Teixeira
September 26, 2019

## Slide 2: Quarterly Stability Assessment (QSA)
Planning Guide 5.9
Next Deadline for QSA
If a GINR is not included in QSA, its Initial Synchronization date will be automatically delayed to the next quarter
All-Inclusive Generation Resource Initial Synchronization Date | Last Day for an IE to meet prerequisites as listed in paragraph (4) below | Completion of Quarterly Stability Assessment
Upcoming January, February, March | Prior August 1 | End of October
Upcoming April, May, June | Prior November 1 | End of January
Upcoming July, August, September | Prior February 1 | End of April
Upcoming October, November, December | Prior May 1 | End of July

## Slide 3: Quarterly Stability Assessment (QSA)
Planning Guide 5.9, Quarterly Stability Assessment
Issue’s seen in the QSA that had May 1, 2018 deadline
  10 day comment period for FIS
    Needs to be complete before QSA deadline
    TSPs need to plan for it
  Dynamic data validation
    Dependent on FIS Stability study
    Need to meet PG 6.9 15 to 30 days prior to QSA deadline

## Slide 4: Resource Integration and Ongoing Operations – Interconnection Services (RIOO-IS) – Releases
Last Release – September 12, 2019
Fix RARF attestation to only go out to those that have FIS request
Fix TSP COD on TSP Dashboard
Fix to not allow empty CR’s to be submitted

## Slide 5: PGRR066 – Implemented in August 2019
Manual Implementation – RIOO-IS “Suspended” status is being used for “Inactive” until RIOO-IS implementation. IE’s see this as “Suspended for Ownership Determination” in RIOO-IS. TSP’s do not see status.
Implementation Date: August 1, 2019
  IE’s with active INR projects can email ERCOT at ResourceIntegrationDepartment@ercot.com to have ERCOT change the status of their INR (1 per email)
  ERCOT queried RIOO database around August 29 to determine the INR projects that should be moved to “Inactive” [5.7.6 (1)]
  Approximately 15 INR’s were moved to “Inactive”

## Slide 6: PGRR066 – Implemented in August 2019
Query was run to determine:
  Last FIS Study or FIS Approved date in RIOO Database was 2 years or more in the past, and
    Blank fields counted as study not approved
  PG 6.9(1) was not marked as complete

## Slide 7: PGRR066 – Implemented in August 2019
Complication
  When an FIS study needs to be redone, ERCOT blanks the fields in the RIOO Database if a previous study was done.
    Older studies remain posted in MIS
    Using the database led to some incorrect status changes
  PG 5.7.6(1) says to use “the date on which ERCOT posts the final FIS studies...to the MIS Secure Area”
  MIS Posting date must be manually checked
  ERCOT will attempt to use the history table to determine the dates of previous studies if they exist.
  ERCOT will check the MIS for all INR’s that meet the query criteria

## Slide 8: PGRR066 – Returning from “Inactive” Status
Many entities assigned “Inactive” status requested instructions on how to get out of it
  Designed to identify INR’s not moving through process at a predetermined pace
  If FIS studies are two years old, work with TSP to initiate new studies
  Meet planning guide 6.9(1)

## Slide 9: Project Size and RARF
Many entities base their project size as the MW’s that cross the POI to the grid
The RARF Unit Info ->Real Power Rating is the MW’s that leave the Generator Terminals
Project size and Real Power Rating need to match

## Slide 10: Active PGRR’s
PGRR066 - Interconnection Request Cancellation and Creation of Inactive Status – BOD approved December 11, 2018. Implemented work around Aug 1, 2019.
PGRR071 - Update Interconnection Process Timetables to Align with NPRR926 – Referred to PLWG by ROS on 7/11/2019. PLWG consensus Sept 18. Goes to ROS on Oct 3rd.
New PGRR – Miscellaneous Updates now split, part called “Add Definitions GSU and MPT”, NPRR, NOGRR, and RRGRR on MPT, GSU definitions.
New PGRR – Miscellaneous Updates, the other part now called “Improvements to GINR”, with non-MPT, non-GSU changes

## Slide 11: Active NPRR’s
Soon on “Add Definitions for MPT and GSU”.

## Slide 12: Other Topics
Oncor Topics

## Slide 13: Oncor Topics
Case Selection
  Should COD or first synchronization date be used to select base case(s) for FIS? COD
  What are the guidelines for selecting base cases for projects with COD or first synchronization date in May to July? June 1
  What are the guidelines for selecting summer peak, HWLL, or both base cases for projects in the panhandle? Should lack of load in the panhandle prior to Lubbock transfer be a consideration? Discuss

## Slide 14: Oncor Topics
Solar Dispatch
  What is the status of discussion on turning solar generation on in HWLL FIS cases given issues with flat starts for stability base case and ERCOT’s decision to not include solar generation in HWLL case? Discuss

## Slide 15: Oncor Topics
Study Questions
  What transfer limits from the panhandle for pre- and post-Lubbock integration should the TSPs use for the FIS? ERCOT is working on for next month’s workshop
  Are harmonics studies needed for inverter based generation or batteries near HVDC ties? Discuss

## Slide 16: Oncor Topics
RIOO Suggestions
  Is there a way to filter out the barrage of notifications coming as blanket announcements from RIOO IS? Certainly like the automation of receiving when changes are made or uploaded but should there be a way to filter by company, or type of change, or other criteria? There is no way to do that in RIOO
  Can a clearer email notification indicating TDSP owners of new gen interconnect request be implemented. Perhaps it includes the assigned TDSP name at the very front of the email subject line? Possibly but not implementable soon

## Slide 17: Oncor Topics
RIOO Suggestions (cont’d)
Currently, “21INR0383 (Icarus Solar) Change Request Accepted”,
Proposed, “ Oncor - 21INR0383 (Icarus Solar) Change Request Accepted”

## Slide 18: Oncor Topics
RIOO Suggestions (cont’d)
Can a way to mass extract documents from RIOO IS be added for i) for the same project, and ii) across multiple projects Both good ideas but not implementable soon
  Same project mass download – propose a check box function to choose what document(s) to download, instead of having to download one document at a time
  Can multiple projects mass download be added? We propose a way to download similar documents across multiple projects, for instance, downloading the final Steady-State Study for projects x, y, z, etc.

## Slide 19: Other contact information
ResourceIntegrationDepartment@ercot.com is distribution list for Resource Integration department

## Slide 20: Questions?
Thank you!