## Sheet1
TX SET Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2019-09-17
Agenda Item: | Decision / Resolution | Action Items :
August 2019 Meeting Notes | Minor changes were made to the notes. | The Texas SET Chair will have these posted to the August 21, 2019 meeting page key documents.
Flight Update | The Texas SET Chair presented the Flight Update as provided by ERCOT.
ERCOT Discussion Items
Extracts/Reports--Feedback Mapping Status Rejects 867_RCS01: 997 | No new discussions were held on this subject.
Texas SET EDI Questions—Living Document Discussion | Texas SET provided the feedback related to the EDI Questions. Texas SET membership agreed to have the 814_16, use of the REF~PH, Priority code segment updated to optional. | The Texas SET Chair will have the updated EDI Questions document posted to the September 17, 2019 meeting page key documents.
NAESB (project number: TBD); Business driver is security—Possible testing specs collaboration with TDTMS | No discussion was held this month.
RMS Update
o RMGRR162, Revisions to Safety-Net Process—RMS voted to approve with the TNMP comments. o OBDRR016, Updates to the Texas Market Test Plan (TMTP)—RMS voted to approve with an effective date of 12/1/2019 as revised by RMS. o Texas SET Change Control Request- 2019-808: Add a new SAC04 code of "SER141" for Unmetered Pole Attachment Service Charge • Urgent Status—RMS voted to approve. • Language Review—RMS voted to approve the change control and the Texas SET Implementation Guide language. o NPRR946, Allow TDSPs to Use 814_28, Complete Un-executable Transactions for 814_03 Switch Transactions Involved in a Mass Transition Event—RMS agreed that this revision will remain tabled pending comments. o RMGRR161, Clarifications to Content of Notice to Affected Parties of a Mass Transition—RMS voted to approve the Impact Analysis. FYI Only | The Texas SET Chair reviewed the updates.
RMS Assignments
946NPRR-01_Allow_TDSPs_to_Use_814_28_Complete_Un-executable_Transactions_for_814_03_Switch_Transactions_Involved_In_A_Mass_Transition_Event | o Texas SET agreed to leave NPRR-01_Allow_TDSPs_to_Use_814_28_Complete_Un-executable_Transactions_for_814_03_Switch_Transactions_Involved_In_A_Mass_Transition_Event tabled until ERCOT can provide feedback. o TDSPs will discuss; then have a conference call with ERCOT to provide a better understanding of how each TDSP’s processes work.
Change Control Call-- No Call for this month | Change Controls on the ERCOT Website. http://www.ercot.com/mktrules/issues/txsetcc
Issues | Issues on the ERCOT Website http://www.ercot.com/mktrules/issues/txset
2019-I149 Recommend revision to Continuous Service Agreement (CSA) process surrounding Solution to Stacking REP Rules 5 and 6. | This will remain tabled unitl a future meeting.
Discussion Items
Proposed Texas SET Release Changes • ONCOR items | • ONCOR requested that Texas SET delay discussion of the Construction Hold addition until next month. ONCOR will submit a Change Control to have this added. • Add Email to 814_01, 814_03, and 814_16. • Texas SET discussed various ways to implement this change to accommodate legal implications within each company. • One suggestion was to have the CRs obtain customer authorization during the signup process in their systems. • ONCOR requested this topic be moved to the Parking Lot section pending the TDSP discussions in November. | • NRG and AEP agreed to collaborate to combine all the approved Change Controls and items being considered for Change Controls into a central location to allow an easier assessment of future release needs. • The Texas SET Chair will compile the necessay documents to send to NRG and AEP for use while completed their task.
• Continue Discussion and Review 650 RCxxx and DCxxx Purpose Code Matrix— | Review is delayed until a future meeting. | NRG and AEP will work together to combine all the Texas SET Release items into a central location to improve the review process.
• Plans for Texas SET Release Update— | Review is delayed until a future meeting. | NRG and AEP will work together to combine all the Texas SET Release items into a central location to improve the review process.
• Add County to the Customer Service Address in the N1~8R loop of the 814_04 Enrollment Notification Response, 814_05, CR Enrollment Notification Response, 814_14, Drop Enrollment Request, and 814_20, ESI ID Maintenance Request. | Texas SET discussed various approaches to incorporate this information into the processes and guides. | NRG will create a change control and include the redlined version of the Implementation Guide provided by Hansen Technologies.
o Testing • Future Flight Schedules Review—Include 2020 Flight Schedule changes as a result of the approval of the TMTP changes. • Script changes needed as a result of the approval of the TMTP changes. • REP Certification Matrix – Long Term | • Texas SET reviewed the proposed changes provided by ERCOT and reached consensus to have that version presented to RMS for a vote at their next meeting. • Texas SET reviewed the Script Pack; then made updates as needed. • The Texas SET Chair will send the updates to the ERCOT Flight Administrator for review and feedback. The REP Certification Matrix was not discussed this month.
o 2020 Meeting Dates | • Texas SET members reviewed the proposed dates and made adjustments where necessary. | • The Texas SET Chair included dates for TDTMS and will send those requests to ERCOT to schedule the meetings.
Other Business
o 969NPRR-01 Clean-up of Protocol 19.8 Retail Market Testing 082819—approved at RMS. Need for Texas SET Comments discussion. | • Texas SET made changes to clarify that ERCOT is the final authority for success or failure during qualification testing. | • The Texas SET Chair will file comments on the behalf of Texas SET to ERCOT in order to have RMS consider those comments at their next meeting.
Parking Lot
MISP Workshop Action Items • Add a MISP definition in RMG (RMGRR)
Next Meeting--ERCOT MET Center 102 | 2019-10-17
Attendees F-T-F
Diana Rehfeldt TNMP | Jim Lee AEP
Stephen Wilson TXUE | Kathy Scott CNP
Kyle Patrick NRG | Sam Pak ONCOR
Jordon Troublefield ERCOT
Attendees Webex
Deb Belin MarketWise | Kathryn Thurman ERCOT
Becky Taylor CNP | Frank Nunes ECInfoSystems
Kim Wall Hansen Technologies | Dave Michelsen ERCOT
Mary Sithihao Stream Energy