## 2016 DSWG Goals
Goal Description | Deliverables | Schedule | Champion | Contributors | Status
Modify rules where conflicts exist for DR participation in multiple programs and multiple parties | Protocol Revisions and/or Changes to the TR & SOW | End of Year | King | Carter, Raish, Totten | Not complete, in progress (still part of LRIS v2)
Next Steps with Smart Meter Texas | Recommend improvements to SMT for third party access and send to WMS for consideration | End of Year | King | Carter, PDW, Goza, Helton | SPEER report issued
Continue to assess the way DR, retail rate structures and Energy Efficiency is counted in the CDR. | DSWG should review any proposals | Ongoing | Reed | Jay Z. | Completed today, include a similar review next year
Review potential improvements to the indicative pricing tool to improve accuracy | Recommend changes as needed | Next Release - End of 2nd Quarter | M Smith | Trefny, Patterson | Completed
Complete the effort to allow 3rd party DR providers to participate in SCED | Recommendation for next steps | End of Year | Totten | Carter, King, Lowrey, PDW, Wiegand, ERCOT staff | Proposed approach presented to WMS and TAC, additional work in progress (still part of LRIS v2)
WMS Assignment to address DR deployment impacts on SCED | Use NPRR 626 as a preliminary deliverable with some historical review once implemented | Ongoing | Carter | PDW, ERCOT Staff | In progress, focus on UFR deployments
Improve annual report on demand response | Change due date and/or data collection frequency; improve/update category definitions; NPRR | End of 3Qtr for NPRR | ERCOT Staff | Jay Z, Thurnher, Wiegand, Barnes/Sams, Morris | SaS code updated/run by mid-Dec for 2015; 2016 will be completed by in first quarter of 2017. NPRR expected next year regarding data collection process.
Modify DSWG working group procedures | Revised procedure | 2016-06-01 | Carter | PDW, ERCOT Staff | Completed
Evaluate participation in SCED by 10 min ERS generation resources | Recommendation for next steps; draft NPRR | Draft NPRR by 6/1 | Thurnher | Trefny, Garcia | Completed
Complete effort associated with TDSP Outages and effect on ERS performance | NPRR738 | NPRR in flight | Carter | Garcia, Goza, PDW | Completed, Approved by the BoD in August

## 2017 DSWG Goals
# | Goal Description | Deliverables | Schedule | Champion | Contributors | Status
1 | Update and review/monitor compliance requirements for engine participation in ERCOT demand response programs | Post information from relevant regulatory authorities clarifying when engines can participate in demand response | End of Q1 | Tim C | Craig M, ERCOT Staff | in progress; TCEQ updated DSWG, expect to post white paper from TCEQ. Will review ERCOT requirements in future meeting
2 | Evaluation of Loads in SCED (something like NPRR 777 or MIRTM) | Develop white paper for simpler method for DR to participate in SCED effectively | End of Q2 | Rob B | Jess T, Greg T | Alternative to Proxy G presented. Discussion ongoing at PUCT.
3 | Consolidate and Post Report Analysis for DR (4CP, Rep Surveys) on ERCOT website | Post information, create SCR if necessary | End of Q2 | Bill B | ERCOT staff | DONE
4 | Review and Update how we report ERS in the CDR | Change how ERS growth is predicted in CDR | End of Q2 | Bill B | ERCOT staff | Discuss at 4/21 DSWG
5 | ERS Data Transport | Develop, Train and Implement Changes required for ERS ERID/Offer workbook process due to update of SaS code. | End of Q3 | ERCOT Staff | ERS QSEs | Changes must be fully implemented in time for the Oct Contract Period with expectation of parallel run with Jun Contract Period
6 | Evaluate if DSWG has Role in DER Activities | Discussion with ETWG and ERCOT to determine if gaps exist; get clarity from WMS if necessary to determine DSWG's role (where is the ETWG/DSWG boundary?) | End of Q3 | Tim C | Jay Z, Frank M | Tim to discuss with ETWG / PLWG Chairs; report back by 4/21
7 | Improve annual report on demand response | Change due date and/or data collection frequency; improve/update category definitions; NPRR | End of Q3 | ERCOT Staff | Jay Z, Thurnher, Wiegand, Barnes/Sams, Morris | SaS code updated/run by mid-Dec for 2015; 2016 will be completed by in first quarter of 2017. NPRR expected next year regarding data collection process.
8 | Define how we would implement local deployment for ERS and/or MRA language | Change protocols consistent with PUCT direction | End of Q4 | Tim C | ERCOT staff | Draft Rule filed to remove local dispatch
9 | Demand Side Non-Transmission Alternatives to Transmission Buildout | Explore current planning process, understand any other alternative methods used elsewhere, evaluate potential changes in ERCOT | End of Q4 | Tim C | Frank M, Jess T, Craig M, Cyrus R, ERCOT Staff
10 | Complete the effort to allow 3rd party DR providers to participate in SCED | Recommendation for next steps | End of Q4 | Totten | Carter, King, Lowrey, Craig M, Wiegand, ERCOT staff | Proposed approach presented to WMS and TAC, additional work in progress (still part of LRIS v2). Discuss next steps at/ meeting
11 | Modify rules where conflicts exist for DR participation in multiple programs and multiple parties | Protocol Revisions and/or Changes to the TR & SOW | End of Q4 | King | Carter, Raish, Totten | Not complete, in progress (still part of LRIS v2)
12 | Continue to assess the way DR, retail rate structures and Energy Efficiency is counted in the CDR. | DSWG should review any proposals | Ongoing | Reed | Jay Z. | Similar review to what was done at the end of 2016
13 | WMS Assignment to address DR deployment impacts on SCED | Use NPRR 626 as a preliminary deliverable with some historical review once implemented | Ongoing | Carter | Craig M, ERCOT Staff | In progress, focus on UFR deployments

## 2018 DSWG Goals
# | Goal Description | Deliverables | Schedule | Champion | Contributors | Status
1 | Review current methodology on how ERCOT reports ERS in the CDR | Make recommendations as necessary | End of 1st Qtr | M Patterson | ERCOT Staff | No changes anticipated.
2 | Define DSWG role with market-related issues for in-front of and behind-the-meter DERs | Discussion at WMS; change DSWG Procedures if necessary | End of 1st Qtr | D. Thompson | Jay Z. | Change in scope presented to DSWG; Reviewed March/Apr DSWG; not presented to WMS.
3 | Analyze current accuracy of and review potential improvements to the indicative pricing tool to improve accuracy | Recommend changes as needed | End of 2nd Qtr | M Smith | Trefny, ERCOT Staff | Concept presented at QMWG; incomplete
4 | Evaluate new operational opportunities and needs for DR / DERs in ERCOT | ERCOT Operations to present to DSWG; recommendations as necessary | End of 2nd Qtr | ERCOT Staff | M Tierney-Lloyd | FERC storage discussed; offline brainstorming for potential new agenda item next DSWG. Complete.
5 | Improve MRA process; including, but not limited to: timing, notifications, contract definitions | Review NPRRs and make recommended changes as necessary | End of 2nd Qtr | Chair | DSWG MPs | NPRR862 (approved), NPRR885, NPRR896
6 | Evaluate ERS risk factors | Change OBD if necessary | End of 3rd Qtr | M Patterson | DSWG MPs | Feedback to be sought from DSWG; Changed risk factor values and time periods. Complete
7 | Formalize REP/ NOIE reporting requirements, process & compliance on demand response | Submit NPRR | End of 3rd Qtr | C Raish | ERCOT Staff, Sheri W., David T. | Decision made to not pursue NPRR; DR/DG survey; Moved to 2019
8 | Investigate the ERCOT transmission planning process to include NWAs | Report or NPRR to allow for the identification and consideration on NWAs in the planning process | End of 3rd Qtr | SPEER - King | Carter | Incomplete
9 | Discussion of DR / DERs at distribution level and impacts with wholesale markets | Develop whitepaper | End of 3rd Qtr | SPEER - King | Carter | May have some interaction with PUCT Project 48023; NPRR917; in process
10 | Continue to assess the way DR, retail rate structures, and energy efficiency is counted in the CDR. | Ongoing | End of 4th Qtr | Reed | Jay Z. | Incomplete; move to 2019
11 | WMS assignment to address DR deployment impacts on SCED | Use NPRR626 as a preliminary deliverable with some historical review once implemented | Ongoing | Chair | Craig M, ERCOT Staff | No deployments in 2018; WMS has asked DSWG /WMWG for joint meeting to review localized deployments and impacts to SCED
12
13

## 2019 DSWG Goals
# | Goal Description | Deliverables | Schedule | Champion | Contributors | Status
1 | Present to WMS DSWG's role with market-related issues for in-front of and behind-the-meter DERs | Present DSWG Procedures for approval at WMS | End of 1st Qtr | Christian P. | Mona T.-L. | Revised Procedures Approved by WMS and posted to Webpage
2 | Review existing reports on DR/DER and identify areas where additional analysis is needed | Report results of review to WMS | End of 3rd Qtr | Jess T. | Marty D., Tim C., M T.-L. |  | Complete
3 | Evaluate storage participation in ERCOT markets | Recommendation to WMS how to treat storage on the distribution and transmission level | End of 3rd Qtr | Mona T.-L. ERCOT Staff | Dave G., Marty D., ERCOT Staff | 4/26 meeting to discuss ES participation in ERS. Follow-up 6/21 mtg. Defn in RTF. Roadmap for ES (TAC). ES wksp identified operational issues: metering, etc. | Complete
4 | Analyze current accuracy of and review potential improvements to the indicative pricing tool to improve accuracy | Recommend changes as needed | End of 2nd Qtr | Mark S. & ERCOT Staff | Floyd T., Jay Z., ERCOT Staff | Discussed indicative pricing tool; discussed changes. Some recommendations were made (use actual telemetered value). Continue to evaluate. Wind and solar forecasting updates? | In process.
5 | Evaluate new operational opportunities and needs for DR / DERs in ERCOT | Recommendation to WMS | End of 2nd Qtr | Mona T.-L. | Christian P., Tim C., jess T, Mark S, Dave G | Early discussion about increasing DR/DER participation relative to reserve shortages in ERCOT. Short term modifications to increase ERS participation unlikely. What are we missing? What will we experience this summer? | In process.
6 | Improve MRA process including, but not limited to: timing, notifications, contract definitions; Identify barriers | Review NPRRs and recommend changes as necessary | End of 2nd Qtr | Mona T.-L. | ERCOT Staff | NPRR862, NPRR885, NPRR896 (approved)
7 | Formalize REP/ NOIE reporting requirements, process & compliance on demand response, and recommend changes in frequency as needed | Submit NPRR(s) as determined | End of 3rd Qtr | C Raish | ERCOT Staff, Sheri W., Christian P. | NPRR933 in flight (currently tabled at PRS for additional discussion) | In process.
8 | Investigate the ERCOT transmission planning process to include NWAs | Report or NPRR to allow for the identification and consideration on NWAs in the planning process | End of 3rd Qtr | Christian P | SPEER - Michael C., Tim C |  | Complete
10 | Continue to assess the way DR, retail rate structures, and energy efficiency is reflected in the CDR, SARA, etc | Ongoing | End of 4th Qtr | Cyrus R. | Jay Z., ERCOT Staff | Joint meeting held with SAWG | Complete
11 | DR deployment impacts on SCED | Use NPRR626 as a preliminary deliverable with some historical review once implemented; Review localized deployments and impacts to SCED - joint meeting with WMWG | Ongoing | Holly | Craig M, ERCOT Staff | Reviewed the methodology; waiting for deployment and will revisit. | Partial; discuss at December Meeting
12 | 5-Minute Settlment | Presentation to DSWG on alternative | End of 2nd Qtr | Floyd T. |  | 4/26 Meeting discussed. Follow-up with DSWG on whether there is support. | Complete
13 | Day Ahead Participation of LR in new DR Program | Pending review and discussion after PUC Project is underway |  |  |  | No activity. | Remove or complete