## Sheet1
No | Enhancement2 | System Change | Notes | Consensus | Transactions | Recommended Version | Change Control (Approved) | TXSET Issue | RMGRR (Approved) | NPRR (Approved)
1 | Timeline for TXSET 5.0 release |  | Gathering requirements through 2020 Initiate project 2021 Go-live mid-2022 |  | N/A
2 | Timeline for TXSET 4.0A release |  | ERCOT to begin testing Q3 2020 (August)??? MORE DISCUSSION NEEDED. |  | N/A
3 | Muni-Coop guidelines are different than the IOU guidelines for meter removal | N |  | Y | 650_04 (MOU/EC) | 4.0A | 800
4 | Sync the language in the Implementation Guide for "CW1" Reject Reason in the 814_09 and 814_13 transaction to support NPRR778 | N | already implemented, sync language in guide | Y | 814_09, 814_13 | 4.0A | 807 |  |  | NPRR778
5 | Sync the Texas SET Implementation Guides with ERCOT Protocols in the way the Muni-Coop is abbreviated | N | MC TDSP --> "MOU/EC TDSP" | Y | N/A | 4.0A | 806
6 | Update all of the TX SET Implementation Guides to allow the receiver of the transaction containing Special Characters to determine to either accept the transaction or to respond with a valid rejection. | ERCOT, TDSP, CR, Service Provider | Will need to create a new reject code. | Y | All | 5.0 | 805 | TXSET143
7 | Clarifies the current description shown in the REF~8X~TE003 of "PCB" Purpose Code to show it as "Investigate Transformer Leaking" in the 650_01 and 650_02. | N | Correcting description of TE003 | Y | 650_01/02 | 4.0A | 799
8 | Updating the 814_24 to allow only the CSA CR to submit the REF~2W and create new reject reason for ERCOT | ERCOT | Adding validation at ERCOT for CSA CR | Y | 814_24 | 5.0 | 798 | TXSET134 | RMGRR124
9 | Make the "Unmetered Service Type" found in the REF~PRT segment "Optional" for the TDSP when the information is available at the time the 814_20 Create transaction is established and communicated to ERCOT. | ERCOT, TDSP | Submitted in 2011 | Y | 814_20, Add/Create | 5.0 | 794
10 | Revise current CSA validation process for MVO process to be separated from CSA CR switch. Two days prior to the scheduled MVO date ERCOT would validate if a CSA was associated to ESIID and drop trxs to TDSP and CSA CR. | ERCOT | Proposed workflow attached to TXSET Issue 149 | N | 814_22, 814_24 | 5.0 |  | TXSET149
11 | All TDSPs agree to re-establish Critical Care status upon request after the CR agrees to the reinstatement date in the MarkeTrak issue. (Completed via RMGRR128) | N | Not needed -- Changes incorporated via RMGRR128 |  | N/A | None |  | TXSET139 | RMGRR128
12 | Harvey Lesson Learned 1) 650_04 BGN08~R8 and REF~5H requests CR to send MVO | TDSP, CR, Service Provider | Need new suspension/reactivation code for REF~5H Greybox description: "814_24 needed because Premise permanantly suspended" | Y | 650_04 | 5.0
13 | Harvey Lesson Learned 2) TDSPs to use 650_04 to notify CRs when power is restored/reactivated for premises that were de-activated | TDSP, CR, Service Provider | TDSPs to communicate reactivation to CRs by sending BGN08~79 with REF~5H=RC002 (RC002 does not exist today, will need to create new+description) |  | 650_04 | 5.0
14 | Harvey Lesson Learned 3) Bi-Directional Turn On/Off Notification | TDSP, CR, Service Provider | Used by TDSP (650_04) and CR (650_01) to DC/RC from direct customer request Reconnect does not need to reference the Disconnect o New codes for bidirectional DC/RC due to floods, Force Majeure events, etc. • 650_01 BGN07 = 72, Purpose Code = DC006 for disconnects Turn Off at Customer Request • 650_01 BGN07 = 79, Purpose Code = RC006 for reconnects Turn On at Customer Request • 650_04 BGN07 = 8S, Purpose Code = DC006 for disconnects Turn Off at Customer Request • 650_04 BGN07 = 79, Purpose Code = RC006 for reconnects Turn On at Customer Request o Add new DC006 / RC006 purpose codes to the 650_01, 650_02 and 650_04 that allows either the TDSP or the CR to disconnect or reconnect due to Potential Hazardous Conditions. Need to clarify the difference between the 650_04 DC001 and DC006 |  | 650_01, 650_02, 650_04 | 5.0
15 | Harvey Lesson Learned 4) Clarify use of the RC003 code | TBD | CRs/TXUE will evaluate whether they need additional RCxxx codes for the 3 scenarios within the RC003: 1) RCN after DNP; 2) RCN for Customer Req. Clearance; 3) RCN after DC due to Tampering Need to clarify greybox language regardless |  | 650_01 | TBD
16 | Harvey Lesson Learned 5) Review 650_04 REF~5H Incident Codes to ensure standardized application by TDSPs | TBD | Review and add new codes if needed. Otherwise, greybox clarification is all that is needed. |  | 650_04 | TBD
17 | Harvey Lesson Learned 6) Review the 814_20 process for meter removal without an 814_24 to allow the TDSPs to use the meter asset at another location. | TBD | Proposal to utilize meter exchange with a “NONE” in new meter number field so the TDSP can physically use the meter that was there in another location. (814_20) Gray Box would need to be modified to make OPTIONAL the number of dials and meter multiplier. (Implem. guide) |  | 814_20 | TBD
18 | Harvey Lesson Learned 7) TDSP Request Contact Information | TBD | TDSP-initiated 814_PC? Can TDSPs leverage CBCI files that are already sent by CRs? Each TDSP would filter for own ESIIDs from master file Idea: CRs submit CBCI files monthly to ERCOT. ERCOT would create report/extract and post on MIS by TDSP DUNS. |  | TBD | TBD
19 | Harvey Lesson Learned 8) Add ESI ID Attributes | ERCOT, CR, TDSP, Service Provider | TDSPs would add premise attributes as a code to describe the type of premise (primary residence vs temporary mobile trailer meter vs boat house vs workshop garage vs barn) Forward-going basis. To be displayed on ERCOT MIS and TDSP ESIID Extract for CR consumption |  | 814_04, 814_05, 814_20
20 | If known by TDSP, communicate to CRs if meter set is required |  | If TDSP knows that a meter does not exist at the location, how to communicate to market that a meter set will be needed. MORE DISCUSSION NEEDED.
21 | Reapplication of SH after MarkeTrak removal process completes (Eliminate -- do not need) |  | 4hr MT removal process completes, Switch Hold removed. However, the new customer's MVI with new CR never gets sent. How does current CR reapply DPP SH? Very minimal volume. Should be resolved with email/escalation to REP Account Manager. |  | 650_01
22 | IAS/IAG Solution |  | Automation to replace the MarkeTrak portion for CRs. TDSPs to evaluate how to automate TDSP portion for cancel/rebilling process. TDSPs will discuss further. Bring back more for TXSET discussions.
23 | Add Counties to the N4 of the N1~8R Customer address of the 814_transactions |  | Kim Wall drafted with N405, N406 with County What will serve as the 'single source' for County listings? How is that added into CIS for TDSPs? Can TDSPs leverage the Weather Moratorium process to identify Counties? |  | 814_04, 814_05, 814_20
24 | Need Uexecutable code added to 650_02 and 814_28 to address instances where a customer has installed Distributed Generation without an Automatic Transfer Switch (ATS) and/or a signed interconnection agreement with the TDSP |  | Add code J009—Requires Automatic Transfer Switch (ATS) installation and/or approval |  | 650_02, 814_28
25 | Need Unexecutable code added to 650_01, 650_02, 650_04 and 814_28 for a code clearance violation |  | 00x–Code Clearance Violation Possibly add a comment in the REF03 that contains the service standards code for the specific violation.—Note : make this element required |  | 650_01, 650_02, 650_04, 814_28
26 | Review 814_16 and 814_03 N1=8R, PER=PN Administrative Communications Contact (Permit Contact Name) to update gray box explanation to clarify how it is used |  | Required if a move-in request is for an ESI ID, which requires a tenant-based permit when there will be a name provided on the permit sent to the TDSP. The name provided in the PER02 must match the name on the permit. MIMO Rules, REP 4, TDSP 2 PER~PN~SNOW, JOE RAY JR PER~PN~ JOE RAY SNOW JR PER~PN~BAILEY BUILDING AND LOAN |  | 814_16, 814_03
27 | Construction Hold |  | Use "CHP" when TDSP identifies Construction Hold needed to add transparency for CRs |  | 814_04, 814_05 |  | 809
28 | Adding direct customer authorization from Customer via CRs to sign up customer for TDSP Outage notifications |  | When CRs send MVI/SWI, CRs would include a Y/N authorization which would then require a mobile number in the 814_01 or 814_16. It would pass through to TDSP to authorize enrollment to the TDSP's Outage Alert/Mobile Alert program. Each TDSP has different criteria needed, which will be discussed among the TDSPs. |  | 814_01, 814_03, 814_16
29 | Add Optional E-mail field on the 814_01, 814_03, & 814_16 |  | Add optional email field on enrollment transactions Possibly rearrange location of the Email field on the 814_PC?? |  | 814_01, 814_03, 814_16