## KTC 12-10-19
BESTF Meetings in 2019/2020
Key Topic & Concept (KTC) | Item | Decision Points and Issues for Developing Principle Concepts | BESTF-NPRR | Support Combo-Model (C)/Single Model (S) | KTC Type (Operations, Markets, & Planning) | Date Topic was First Presented to the BES Task Force | Estimated Date for First/Next Discussion | Estimated Final Meeting for Moving to TAC for Vote | 2019-10-18 | 2019-11-04 | 2019-11-15 | 11/20 TAC | 2019-12-06 | 2020-01-17 | 1/29/2020 TAC | 2020-02-25 | 2020-03-13 | 2020-04-10 | 2020-05-01 | 2020-05-21 | 2020-06-12 | 2020-06-30 | 2019-07-23 | 2020-08-14 | 2020-09-11 | 2020-09-29 | 2020-10-22 | 2020-11-13
Key Topic 1 Definitions and Registration for Energy Storage Resources | 1 | Registration of a battery as a single resource and identified as an Energy Storage Resource (ESR). (Protocol Language and system changes.) NPRR 957 (RTF-4 Definition of Energy Storage Resource and Related Registration and Telemetry Requirements) introduces the ESR definition so that subsequent NPRRs can use the ESR definition. | BESTF-5 | Combo and Single | All | 2019-11-04 | 2019-11-04
Key Topic 2 Physical Responsive Capability, and ORDC Reserve | 1 | Energy Storage Resources contribution to PRC | BESTF-3 (NPRR987) | Combo and Single | Operations | 2019-10-18 | 2019-10-18 | 2019-11-04
| 2 | Energy Storage Resources contribution to ORDC Reserves | BESTF-3 (NPRR987) | Combo and Single | Markets | 2019-10-18 | 2019-10-18 | 2019-11-04
Key Topic 3 Dispatch, Pricing, and Mitigation | 1 | SCED dispatch and Nodal pricing (basepoint weighting) of Energy Storage Resources when charging and discharging | BESTF-2 (NPRR 986) | Combo and Single | Markets/Operations | 2019-10-18 | 2019-10-18 | 2019-11-04
| 2 | Mitigation treatment in SCED | BESTF-2 (NPRR 986) | Combo and Single | Markets/Operations | 2019-10-18 | 2019-10-18 | 2019-11-04
| 3 | Reporting Requirements on how often mitigation would have been applied. | BESTF-2 (NPRR 986) | Combo and Single | Markets/Operations | 2019-10-18 | 2019-10-18 | 2019-11-04
| 4 | Charging restrictions during an emergency conditions (Note PUCT rule on charging during emergencies.) | BESTF-5 | Combo and Single | Operations | 2019-11-04 | 2019-11-04
Key Topic 4 Technical Requirements | 1 | Reactive Capability and Voltage Support Service | BESTF-1 | Combo and Single | Operations | 2019-10-18 | 2019-10-18 | 2019-11-04
| 2 | Voltage/frequency Ride-through requirements | BESTF-1 | Combo and Single | Operations | 2019-10-18 | 2019-10-18 | 2019-11-04
| 3 | Governor Deadband and Droop Setting Requirement | BESTF-1 | Combo and Single | Operations | 2019-10-18 | 2019-10-18 | 2019-11-04
| 4 | Governor Testing | BESTF-1 | Combo and Single | Operations | 2019-10-18 | 2019-10-18 | 2019-11-04
Key Topic 5 Performance | 1 | Energy Storage Resource Performance Deployment (ESRDP) - NPRR 963 | NA | Combo Model | Operations | 2019-10-18 | 2019-10-18 | NA
| 2 | Energy Storage Resource Performance Deployment (ESRDP) | BESTF-4 | Single Model | Operations | 2019-11-04 | 2019-11-04
Key Topic 6 ESR Options to maintain desired level of State of Charge | 1 | Allow Energy Storage Resources to update their EOC closer to real-time | BESTF-2 (NPRR 986) | Combo and Single | Markets | 2019-10-18 | 2019-10-18 | 2019-11-04
| 2 | single model ESR attributes and Offer structure | BESTF-4 | Single Model | Markets | 2019-11-04 | 2019-11-04 | 2015-11-15
Key Topic 7 Settlement | 1 | Base-Point Deviation (BPD) - NPRR 963 | NA | Combo Model | Markets | 2019-10-18 | 2019-10-18 | NA
| 2 | Single model ESR settlement changes | BESTF-4 | Single Model | Markets | 2019-11-04 | 2019-11-04 | 2019-12-06
| 3 | Single model ESR Base-Point Deviation (BPD) | BESTF-4 | Single Model | Markets | 2019-11-04 | 2019-11-04 | 2019-12-06
| 4 | SODG /SOTG settled at Nodal pricing while charging and discharging |  | Policy | Markets |  | 2020-04-10
| 5 | ESR Settlement using Nodal basepoint weighted prices | BESTF-4 | Combo and Single | Markets | 2019-11-04 | 2019-11-04 | 2019-12-06
| 6 | ESR Reliability Instructions and Associated Settlement | NA | Single Model | Markets |  | 2019-12-06 | 2020-01-17
| 6 | ESR treatment during SCED Failures (RTCTF assigned) | NA | Single Model | Markets | 2019-11-15 | 2019-11-15 | NA
Key Topic 8 WSL Treatment | 1 | Should WSL treatment implementation extend to batteries that can self-serve PUN Load with the stored energy? | NA | Policy | Markets | 2019-11-15 | 2019-11-15 | 2019-12-06
| 2 | Should WSL treatment implementation extend to non-dispatched generators? If yes, should there be differentiation between a SOG that is co-located with customer load and one that only has auxiliary loads behind the metering point? |  | Policy | Markets | 2019-11-15 | 2019-11-15 | TBD
Key Topic 9 ESR on the Distribution System | 1 | How is an ESR (in SCED) interconnected to the distribution system addressed in the protocols and handled by the ERCOT systems? (Coordinate with DGR Workshops) |  | Policy | Markets |  | 2020-04-10
Key Topic 10 ESR - Study & Capacity Assumptions | 1 | Define "Storage Peak Average Capacity Percentage" to be used in CDR for various batteries. | NA | Policy | Markets/Operations | 2019-11-15 | 2019-11-15 | 2019-12-06
| 2 | Outage Coordination Studies | NA | Policy | Operations | 2019-11-15 | 2019-11-15 | NA |  |  |  | NA
| 3 | Reliability Unit Commitment Studies | NA | Combo Model | Markets/Operations | 2019-10-18 | 2019-10-18 | 2019-11-04
| 4 | Operational Studies | NA | Policy | Operations | 2019-11-15 | 2019-11-15 | NA |  |  |  | NA
| 5 | Transmission Planning Studies | NA | Policy | Planning | 2019-11-15 | 2019-11-15 | NA |  |  |  | NA
| 6 | Reliability Unit Commitment Studies |  | Single Model | Markets/Operations | 2019-12-06 | 2019-12-06
Key Topic 11 DC Coupled Resources | 1 | Registration |  | Policy | All |  | 2020-01-17
| 2 | Participation Model (EMS and MMS) |  | Policy | All |  | 2020-01-17
| 3 | Forecasting |  | Policy | All |  | 2020-01-17
| 4 | Should existing performance exemptions to IRR apply |  | Policy | Market/Operations |  | 2020-01-17
| 5 | Mitigation treatment in SCED |  | Policy | Markets |  | 2020-01-17
| 6 | WSL Treatment |  | Policy | Markets |  | 2020-01-17
| 7 | Data Requirements from QSEs |  | Policy | All |  | 2020-01-17
| 8 | Interconnection Issues |  | Policy | All |  | TBD
Key Topic 12 AC Coupled Resources that want to operate as one resource | 1 | Registration |  | Policy | All |  | 2020-01-17
| 2 | IRR/Battery operating as single unit |  | Policy | All |  | 2020-01-17
| 3 | GT/Battery operating as single unit |  | Policy | All |  | 2020-01-17
| 4 | Participation Model (EMS and MMS) |  | Policy | Markets/Operations |  | 2020-01-17
| 5 | WSL Treatment |  | Policy | Markets |  | 2020-01-17
| 6 | Forecasting |  | Policy | All |  | 2020-01-17
| 7 | Should existing performance exemptions to IRR apply? |  | Policy | Market/Operations |  | 2020-01-17
| 8 | Interconnection Issues |  | Policy | All |  | TBD
Key Topic 13 Process and Policy Questions related to Interconnection Requests for Energy Storage Resources | 1 | How should a request to interconnect an energy storage resource at an existing generation site be evaluated, when the ESR addition is solely to enhance the capability of the existing resources at the site ? No increase in POI limit is requested. |  | Policy | All |  | 2020-01-17
Key Topic 14 Review existing Study Requirements and Determine if new Studies are Needed | 1 | Identify if new studies are needed for interconnecting ESR due to interactions between the controls of the ESR and neighboring active devices such as HVDC tie, SVC, STATCOM, or ESR. |  | Policy | All |  | 2020-01-17