| PGRR Number | 071 | PGRR Title | Update Interconnection Process Timetables to Align with NPRR926 |
| --- | --- | --- | --- |
| Date of Decision | December 10, 2019 |
| Action | Approved |
| Timeline | Normal |
| Effective Date | January 1, 2020 |
| Priority and Rank Assigned | Not applicable |
| Planning Guide Sections Requiring Revision | 5.7.5, Interconnection Process Timetables |
| Related Documents Requiring Revision/Related Revision Requests | None |
| Revision Description | This Planning Guide Revision Request (PGRR) updates information in Section 5.7.5 to align with Nodal Protocol Revision Request (NPRR) 926, Removal of 90-Day Period Between SSR Study Approval and Synchronization, which was approved by the ERCOT Board on June 11, 2019. |
| Reason for Revision | Addresses current operational issues. Meets Strategic goals (tied to the ERCOT Strategic Plan or directed by the ERCOT Board). Market efficiencies or enhancements Administrative Regulatory requirements Other: (explain) (please select all that apply) |
| Business Case | This PGRR brings the Planning Guide into alignment with NPRR926. |
| ROS Decision | On 7/11/19, ROS unanimously voted to table PGRR071 and refer the issue to the Planning Working Group (PLWG). All Market Segments were present for the vote. On 10/3/19, ROS unanimously voted to recommend approval of PGRR071 as revised by ROS. All Market Segments were present for the vote. On 11/7/19, ROS unanimously voted to endorse and forward to TAC the 10/3/19 ROS Report and the Impact Analysis for PGRR071. All Market Segments were present for the vote. |
| Summary of ROS Discussion | On 7/11/19, ERCOT Staff clarified the intent of the revised language proposed to the interconnection process timetable following the incorporation of NPRR926 into the Protocols. On 10/3/19, an additional clarification was made as a result of discussion at the 9/18/19 PLWG meeting. On 11/7/19, there was no discussion. |
| TAC Decision | On 11/20/19, TAC unanimously voted to recommend approval of PGRR071 as recommended by ROS in the 11/7/19 ROS Report. All Market Segments were present for the vote. |
| Summary of TAC Discussion | On 11/20/19, there was no discussion. |
| ERCOT Opinion | ERCOT supports approval of PGRR071. |
| Board Decision | On 12/10/19, the ERCOT Board approved PGRR071 as recommended by TAC in the 11/20/19 TAC Report. |

| Sponsor |
| --- |
| Name | Jay Teixeira |
| E-mail Address | jay.teixeira@ercot.com |
| Company | ERCOT |
| Phone Number | 512-248-6582 |
| Cell Number | 512-656-6734 |
| Market Segment | N/A |

| Market Rules Staff Contact |
| --- |
| Name | Phillip Bracy |
| E-Mail Address | phillip.bracy@ercot.com |
| Phone Number | 512-248-6917 |

| Comments Received |
| --- |
| Comment Author | Comment Summary |
| None |  |

Market Rules Notes

None

Proposed Guide Language Revision

### 5.7.5	Interconnection Process Timetables

(1)	P.U.C. Subst. R. 25.198, Initiating Transmission Service, provides deadlines for ERCOT and TSP(s) to complete and report on the required interconnection studies provided that the IE submits all required data and appropriate fee(s).  Therefore, the IE must ensure that ERCOT and the TSP(s) performing these studies receive all required data in order to establish reasonable study models and assumptions that provide meaningful results and recommendations for interconnecting the proposed generating project.

(2)	Because the FIS is generally the critical path item in the GINR process, ERCOT recommends that a timetable for the FIS be developed and included in the study scope agreement.  In addition, major improvements to the transmission system resulting from interconnection requests should be identified as early in the process as possible so project validity can be considered before the parties go forward with extensive interconnection studies.  Once the FIS is underway, the parties may determine whether an adjustment to the original estimated completion date is necessary.  Should a schedule adjustment become necessary, the parties must provide Notice to ERCOT and the TSP(s) as soon as practicable, indicating the revised expected completion date.

(3)	The following timetable complies with P.U.C. Subst. R. 25.198.  It is intended to serve as a guideline only and the times stated are not requirements unless stated elsewhere in this section.  If the number of days shown is less than 30, these are Business Days; if the number of days shown is 30 days or more, these are calendar days.

| Task | Responsible Entity | Time Required to Complete |
| --- | --- | --- |
| Acknowledgement of GINR Application | ERCOT | 1 to 10 Business Days |
| Notification of Additional Information Needed to Complete Application | ERCOT | 1 to 10 Business Days |
| Perform Security Screening Study (after application is deemed complete) | ERCOT | 10 to 90 days |
| Decision to Pursue FIS (following issuance of Security Screening Study by ERCOT) | IE | Up to 180 days |
| Develop Scope Agreement for FIS (following IE’s Notification to ERCOT of desire for FIS and remittance of appropriate fees) | IE, ERCOT, and TSP(s) | Up to 60 days |
| Perform FIS (following agreement on scope) |  | 40 to 300 days |
| Steady-State and Transfer Analysis | TSP(s) | 10 to 90 days |
| System Protection Analysis (following Steady-State Analysis) | TSP(s) | 10 to 30 days |
| Dynamic and Transient Stability Analysis (following System Protection Study) | TSP(s) | 10 to 90 days |
| Facility Study | TSP(s) | 10 to 90 days |
| SSR | TSP(s) | 60 to 180 days |
| Study Report Review and Acceptance (following issuance of FIS) | ERCOT, and TSP(s) | 10 to 15 Business Days |
| FIS Posted to Market Information System (MIS) | ERCOT | Within 10 days of being deemed complete |
| Report stability resolution findings to ERCOT | TSP | Within 90 days |
| Negotiate and Execute Standard Generation Interconnection Agreement (SGIA) (following acceptance of FIS) | IE and TSP | 180 days |