## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
December 12, 2019

## Slide 2
Project Portfolio Update
  Recent / Upcoming Project Implementations
  2019 Release Targets
  2020 Release Targets
  Planned Project Starts
  Aging Items Report
  2019 Project Spending Forecast
  Revision Request Funding Placeholder Status
  Priority/Rank Options for Revision Requests with Impacts
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Implementations
2019 December Release – R6 – 12/10/2019 – 12/12/2019 In Flight
  NPRR911 – Improved Calculation of Real-Time LMPs at Logical Resource Nodes for On-Line Combined Cycle Generation Resources
  NPRR952 – Use of Katy Hub for the Fuel Index Price
  PGRR072 – Treatment of Generation Resource Retirement and Mothball in Regional Transmission Plan and Geomagnetic Disturbance Vulnerability Assessment
2019 December Release – Off-Cycle – 12/16/2019 In Flight
  NPRR920 – Change to Ramp Rate Calculation in Resource Limit Calculator
2020 January Release – Off-Cycle – 1/1/2020 In Flight
  NPRR877 Ph2 – Use of Actual Interval Data for IDR ESI IDs for Initial Settlement
  NPRR968 – Revise EEA Level 3 Triggers from 1375 MW to 1430 MW to Align with New Most Severe Single Contingency Value
2020 January Release – Off-Cycle – 1/9/2020 In Flight
  NPRR873 – Posting of ERCOT Wide Intra-Hour Wind Power & Load Forecast on MIS Public
  SCR797 – Provide Current Operating Plans (COPs) to TSPs
2020 February Release – R1 – 2/4/2020 – 2/6/2020 In Flight
  No Revision Requests are planned for this release
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2019 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/5 – 2/7 | April 4/2 – 4/4 | May 5/28 – 5/30 | August 8/6 – 8/8 | October 10/15 – 10/17 | December 12/10 – 12/12
NPRR842 NPRR858 NPRR878 SCR794 PGRR057(b) OBDRR011 RMGRR156 PGRR062 NPRR916(a) | NPRR809(b) NPRR817 NPRR833(a/b) NPRR845 NPRR847 NPRR865 NPRR866 NPRR880 VCMRR021 RRGRR017 VCMRR022 NPRR877 Ph1 NPRR833(c) NPRR749 | NPRR901 NPRR910 NPRR912 NPRR916(b) NOGRR174 OBDRR010 NPRR909 NPRR519 NPRR620 NPRR741 NPRR755 NOGRR154 | NPRR925 SCR793 SCR796 SCR798 OBDRR003 OBDRR014 NPRR821 PGRR066 NPRR899 | NPRR895 NPRR914 NPRR923 OBDRR007 PGRR061 PGRR070(a) RR917(a) NPRR889 RMGRR155 RRGRR018 NPRR921 NOGRR185 PGRR069 | NPRR911 NPRR952 PGRR072 NPRR920
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
NPRR809(b) – Reporting/posting system changes
NPRR833(a/b) – DAM/SCED system changes
NPRR833(c) – CRR system changes
NPRR916(a) – Mitigated Offer Floor to $0/MWh
NPRR916(b) – Mitigated Offer Floor to -$20/MWh
PGRR057(b) – List of GMD event contingencies
PGRR070(a) – Sect. 3.1.8, paragraphs (1) and (2)
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
E
E
E
E
7/1
6/2
ü
ü
CMM Release 1b
5/1
1/22
3/26
ü
ü
ü
ü
ü
ü
ü
TBD Items | 2017 | 2018 | 2019
 | NPRR702, NPRR829 | NPRR825(b), NPRR867, NPRR841 | NPRR887,NPRR904,OBDRR009,NPRR905,NPRR936,NPRR951, PGRR066,SCR804
3/1
3/5
5/6 – 5/7
12/9
RARF (SCR781)
Testing/Training of View/Update
(Go-Live in April 2020)
ü
R1
R2
R3
R4
R5
R6
ü
4/10
ü
ü
6/15
ü
ü
ü
ü
ü
ü
ü
ü
ü
6/1
9/1
ü
ü
ü
ü
ü
ü
ü
ü
ü
8/1
ü
10/18
11/1
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
12/16

## Slide 5: 2020 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/4 – 2/6 | April 3/31 – 4/2 | May 5/26 – 5/28 | August 8/4 – 8/6 | October 10/13 – 10/15 | December 12/8 – 12/10
NPRR877 Ph2 NPRR968 NPRR873 SCR797 NPRR863 Ph1 | SCR802 NPRR929 SCR781(a) RRGRR016 RRGRR019 | NPRR856 NPRR884 NPRR935 OBDRR006 SCR803 | NPRR905 SCR804 | MMS/OS Refresh | SCR799 NPRR863 Ph2 NPRR885 NPRR917 PGRR070(b) SCR781(b)
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
3/1
NPRR863 Ph1 – FFR portion
NPRR863 Ph2 – ECRS portion
PGRR070(b) – Remaining PGRR language
SCR781(a) – View / Edit capability
SCR781(b) – Add capability
MMS/OS Upgrade “Chill”
MMS/OS Upgrade “Freeze”
April
RARF Go-Live for View/Update
P
P
E
E
E
E
E
E
E
E
P
P
NS
P
NS
November
Off-Cycle
1/1
Future Year Go-Live Targets
2021
2022
NS
NS
I
NS
E
E
September
Off-Cycle
NS
NS
1/9
E

## Slide 6: Approved Revision Requests “Not Started” – Planned to Start in Future Months
Revision Request | Target Start Date | Release Target | Cost Estimate | Author
NPRR935 – Post All Wind and Solar Forecasts | Dec 2019 | 2020-R3 | $50k-$70k | ERCOT
NPRR863 Phase 2 – Creation of ERCOT Contingency Reserve Service (ECRS) | Dec 2019 | 2021 | $1.9M-$2.9M | ERCOT
SCR803 – Enhance Wind Integration Report and Create Solar Integration Report and Solar Dashboard | Jan 2020 | 2020-R3 | $50k-$75k | Reliant
Project Initiations – Next 3 Months

## Slide 7: Aging Items Report
Aging Items Report | Last Action | Status
NPRR702 – Flexible Accounts, Payment of Invoices, and Disposition of Interest on Cash Collateral | Board approved on 12/8/2015 | Partial implementation on 9/1/2018 Remaining grey boxes pending decision on Treasury software
NPRR825 – Require ERCOT to Issue a DC Tie Curtailment Notice Prior to Curtailing any DC Tie Load | Board approved on 12/12/2017 | Partial implementation on 10/1/2018 Remaining grey boxes expected to be paired with internal ERCOT project (Security Constrained Unit Commitment)
Aging Items PPL Logic: Project Status = “Not Started” and
Priority < “2019” (current year)
Status updates in bold

## Slide 8: 2019 Project Spending
2019 PPL Budget = $20.4M
“Potential Demand” represents internal ERCOT projects that have not been fully approved
May actuals not yet available
June-December forecasts are updated

## Slide 9: Revision Request Funding Placeholder Status
In 2019, ERCOT forecasted $4.0M for Revision Request work
In ERCOT’s 2020/2021 proposed budget, the following amounts are allocated for Revision Request work
  2020 = $4M
  2021 = $4M
Yearly Revision Request Spending Forecast Summary
Project Status | 2019 | 2020
YTD Actuals | $2.62M | -
Approved – In-Flight / Complete | $2.92M | $1.13M
Approved – Not Started | $0.01M | $1.84M
Remaining Funding | $1.07M | $1.03M
Total Allocation | $4.00M | $4.00M
As of 11/30/2019
May actuals not yet available
Updated to include April actuals

## Slide 10: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR826 | Mitigated Offer Caps for RMR Resources | TBD | TBD | Additional time requested to complete IA due to MMS impacts
NPRR963 | Creation of Generation and Controllable Load Resource Group (GCLR Group) | TBD | TBD | Additional time requested to complete IA due to EMS impacts Expected cost = $150k-$200k Expected duration = 6-9 months
NPRR971 | Replacing the Real-Time Average Incremental Energy Cost | 2020 | 2950 | Add to end of 2020 list and work into plan without disrupting in-flight projects
NPRR974 | Capacity Insufficiency Operating Condition Notice (OCN) Transparency | TBD | TBD | Additional time requested to complete IA
NPRR977 | Create MIS Posting for RUC Cancellations | 2020 | 2960 | Add to end of 2020 list and work into plan without disrupting in-flight projects
Options for…
PPL Rank Information
Next available 2020 Rank in Business Strategy = 2950
Next available Rank in Regulatory = 240
Note
Items in the Regulatory section of the PPL are not tracked against the market Revision Request funding allocation

## Slide 11: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR978 | Alignment with Amendments to PUCT Substantive Rule 25.505 | 2020 | 240 | REGULATORY Add to end of 2020 list and work into plan without disrupting in-flight projects
SCR806 | Adding QSE and DME Information to Disclosure Reports | 2020 | 250 | REGULATORY Add to end of 2020 list and work into plan without disrupting in-flight projects
Options for…
PPL Rank Information
Next available 2020 Rank in Business Strategy = 2950
Next available Rank in Regulatory = 240
Note
Items in the Regulatory section of the PPL are not tracked against the market Revision Request funding allocation