## Sheet1
No | Enhancement2 | System Change | Notes | Consensus | Transactions | Recommended Version | Change Control (Approved) | TXSET Issue | RMGRR (Approved) | NPRR (Approved)
4.0A | Muni-Coop guidelines are different than the IOU guidelines for meter removal | N | Muni-Coop guidelines are different than the IOU guidelines for meter removal | Y | 650_04 (MOU/EC) | 4.0A | 800
4.0A | Sync the language in the Implementation Guide for "CW1" Reject Reason in the 814_09 and 814_13 transaction to support NPRR778 | N | already implemented, sync language in guide | Y | 814_09, 814_13 | 4.0A | 807 |  |  | NPRR778
4.0A | Sync the Texas SET Implementation Guides with ERCOT Protocols in the way the Muni-Coop is abbreviated | N | MC TDSP --> "MOU/EC TDSP" | Y | N/A | 4.0A | 806
4.0A | Update all of the TX SET Implementation Guides to allow the receiver of the transaction containing Special Characters to determine to either accept the transaction or to respond with a valid rejection. | N | 11/14/19 discussion: 2 phase approach: 1) implement table of unacceptable special characters within the TXSET guides | Y | All | 4.0A | 805 | TXSET143
4.0A | Update Greybox explanation to clarify that tenant-based permit must be sent to TDSP by the Applicable Legal Authority (ALA) -- city, county, etc. | N | Revise current greybox language to read: Required if a move-in request is for an ESI ID, which requires an occupancy permit. The Applicable Legal Authority (ALA) will notify the TDSP directly of the completed permit. The name provided in the PER02 must match the name on the occupancy permit. |  | 814_16, 814_03 | 4.0A | NEEDED
4.0A | Clarifies the current description shown in the REF~8X~TE003 of "PCB" Purpose Code to show it as "Investigate Transformer Leaking" in the 650_01 and 650_02. | N | Correcting description of TE003 | Y | 650_01/02 | 4.0A | 799
4.0A | Harvey Lesson Learned 4) Clarify greybox language of the usage of the RC003 code in 650_01 | N | Greybox language currently used for RC003: 1) RCN after DNP; 2) RCN for Customer Req. Clearance; 3) RCN after DC due to Tampering Clarify greybox language: "Used by CR to reconnect premise when CR did not send disconnect" Also to remove the examples above (1, 2, 3) |  | 650_01 | 4.0A | NEEDED
4.0A | <ESIID>, <Membership ID>, <Special Needs Indicator>,etc | CR, Service Provider | PR288-01 (EDI Translator upgrade) Current SET: Max Use: >1 Current ERCOT: last provided Notes: 814 ANSI > 1 ERCOT Rec: add Notes to restrict to 1 use TXSET Rec: Add "only one allowed" to gray box |  | All | 4.0A | NEEDED
4.0A | REF~PH (Priority Code) | CR, Service Provider | PR288-01 (EDI Translator upgrade) Current SET: REQ on standard Move In Current ERCOT: optional Notes: even split on LSE compliance ERCOT Rec: change guide to Optional TXSET Rec: 08/16/2019: Homework for T/X SET members to determine if "Optional" vs "Required" TX SET members to provide consensus or not at the September 2019 meeting. 09172019: TX SET members agreed that the 814-_16 language should be changed to make the requirment optional. |  |  | 4.0A | NEEDED
4.0A | Populating N3 and N401 and N402 in the N18R loop. | CR, Service Provider | PR288-01 (EDI Translator upgrade) Current SET: Only N403 is valid in the N18R loop. N3 is not valid in the N18R loop. N401 and N402 are marked not used for the N4. Current ERCOT: optional Notes: Example: N1*8R*CUSTOMER NAME~ N3*CUSTOMER ADDRESS~ N4*CITY*TX*760536829~ ERCOT Rec: Market Participants to make updates to follow TX SET Guides TXSET Rec: Texas SET agrees with the ERCOT recommendation to reject. |  |  | 4.0A | NEEDED
4.0A | PER~IC located in the wrong N1 Loop | CR, Service Provider | PR288-01 (EDI Translator upgrade) Current SET: Should be located in the N1~8R loop Current ERCOT: optional Notes: Example: N1*N1*CUSTOMER NOTIFICATION~ N3*STREET ADDRESS~ N4*CITY*TX*784043867~ PER*IC*CONTACT NAME~ ERCOT Rec: Market Participants to make updates to follow TX SET Guides TXSET Rec: Texas SET agrees with the ERCOT recommendation to reject. |  |  | 4.0A | NEEDED
4.0A | REF~2W located in the wrong N1 loop | CR, Service Provider | PR288-01 (EDI Translator upgrade) Current SET: Should be located in the N1~SJ loop Current ERCOT: optional Notes: Example: N1*8R*CUSTOMER NAME~ N4***770604210~ REF*2W*MVO~ ERCOT Rec: Market Participants to make updates to follow TX SET Guides TXSET Rec: Texas SET agrees with the ERCOT recommendation to reject. |  |  | 4.0A | NEEDED
4.0A | PER~IC located in the wrong N1 Loop (No N1~BT was used in the transaction and it was not a Muni ESI) | CR, Service Provider | PR288-01 (EDI Translator upgrade) Current SET: Should be located in the N1~BT loop Current ERCOT: optional Notes: Example: N1*8R*CUSTOMER NAME~ N4***78362~ PER*IC*CUSTOMER NAME*TE*1234567890~ N1*AY*ERCOT*1*183529049**40~ ERCOT Rec: Market Participants to make updates to follow TX SET Guides TXSET Rec: Texas SET agrees with the ERCOT recommendation to reject. |  |  | 4.0A | NEEDED
1 | Update all of the TX SET Implementation Guides to allow the receiver of the transaction containing Special Characters to determine to either accept the transaction or to respond with a valid rejection. | ERCOT, TDSP, CR, Service Provider | Need to create a new reject code. Upon implementation of TXSET 5.0, ERCOT & TDSPs would code to Reject any inappropriate special characters used. 11/14/19 discussion: Part 2) implement the reject code as part of 5.0 release (new change control needed to specify reject code). | Y | All | 5.0 | NEEDED
2 | Updating the 814_24 to allow only the CSA CR to submit the REF~2W and create new reject reason for ERCOT | ERCOT | Adding validation at ERCOT for CSA CR | Y | 814_24 | 5.0 | 798 | TXSET134 | RMGRR124
3 | Make the "Unmetered Service Type" found in the REF~PRT segment "Optional" for the TDSP when the information is available at the time the 814_20 Create transaction is established and communicated to ERCOT. | ERCOT, TDSP | Submitted in 2011 | Y | 814_20, Add/Create | 5.0 | 794
4 | Revise current CSA validation process for MVO process to be separated from CSA CR switch. Two days prior to the scheduled MVO date ERCOT would validate if a CSA was associated to ESIID and drop trxs to TDSP and CSA CR. | ERCOT | http://www.ercot.com/content/wcm/key_documents_lists/187801/2019_I149.docx Workflow attached to Issue 149 | N | 814_22, 814_24 | 5.0 | NEEDED | TXSET149
5 | Harvey Lesson Learned 1) 650_04 BGN08~R8 and REF~5H requests CR to send MVO | TDSP, CR, Service Provider | Need new suspension/reactivation code for REF~5H Greybox description: "814_24 with B44 code needed because Premise permanantly suspended" | Y | 650_04 | 5.0 | NEEDED
6 | Harvey Lesson Learned 2) TDSPs to use 650_04 to notify CRs when power is restored/reactivated for premises that were de-activated | TDSP, CR, Service Provider | TDSPs to communicate reactivation to CRs by sending BGN08~79 with REF~5H=RC002 (RC002 does not exist today, will need to create new code, description and new DTM segment) |  | 650_04 | 5.0 | NEEDED
7 | Harvey Lesson Learned 3) Bi-Directional Turn On/Off Notification | TDSP, CR, Service Provider | Used by TDSP (650_04) and CR (650_01) to DC/RC from direct customer request Reconnect does not need to reference the Disconnect o New codes for bidirectional DC/RC due to floods, Force Majeure events, etc. • 650_01 BGN07 = 72, Purpose Code = DC006 for disconnects Turn Off at Customer Request • 650_01 BGN07 = 79, Purpose Code = RC006 for reconnects Turn On at Customer Request • 650_04 BGN07 = 8S, Purpose Code = DC006 for disconnects Turn Off at Customer Request • 650_04 BGN07 = 79, Purpose Code = RC006 for reconnects Turn On at Customer Request o Add new DC006 / RC006 purpose codes to the 650_01, 650_02 and 650_04 that allows either the TDSP or the CR to disconnect or reconnect due to Potential Hazardous Conditions. Need to clarify the difference between the 650_04 DC001 and DC006 |  | 650_01, 650_02, 650_04 | 5.0 | NEEDED
8 | Harvey Lesson Learned 5) Review 650_04 REF~5H Incident Codes to ensure standardized application by TDSPs | TBD | Review and add new codes if needed. No coding changes -- Greybox clarification is needed |  | 650_04 | TBD
9 | Harvey Lesson Learned 6) Review the 814_20 process for meter removal without an 814_24 to allow the TDSPs to use the meter asset at another location. | ERCOT, TDSP, CR, Service Provider | Proposal to utilize meter exchange with a “NONE” in new meter number field so the TDSP can physically use the meter that was there in another location. (814_20) Implementation Guide Gray Box would need to be modified to make OPTIONAL the number of dials and meter multiplier. (Change Control needed) |  | 814_20 | 5.0 | NEEDED
10 | Harvey Lesson Learned 8) Add ESI ID Attributes | ERCOT, CR, TDSP, Service Provider | TDSPs would add premise attributes as a code to describe the type of premise (primary residence vs temporary mobile trailer meter vs boat house vs workshop garage vs barn vs Master Metered) 1) Forward-going basis. 2) To be displayed on ERCOT MIS and TDSP ESIID Extract for CR consumption. 3) TDSPs currently have lists, and will collaborate to create master list for market use. From Kim Wall: I would recommend using a REF segment within the N1*8R to provide the type of premise (e.g., Garage, etc.). REF02 would have whatever list of codes the TDSPs want to create and REF03 can optionally be used for additional text. I can’t add the notes for the gray boxes without getting on a different computer but the basic X12 structure is below. It would be a new REF segment at this position, not currently used for any reason today in this N1 loop. ST*814*78001 BGN*11*878862304201911091858330781111*20191109***201911090000465335100006312222**5 N1*8S*CENTERPOINT ENERGY*1*957877905 N1*AY*ERCOT*1*183529049**41 N1*SJ*X ENERGY*9*0787031111000**40 N1*8R*BONNIE SMITH N3*104 SHAWNEE PL N4*MISSOURI CITY*TX*77459 REF*JR*GRG*GARAGE LIN* |  | 814_04, 814_05, 814_14, 814_20, 814_22 | 5.0 | NEEDED
15 | Add Counties to the N4 of the N1~8R Customer address of the 814_transactions (required field) | ERCOT, CR, TDSP, Service Provider | N405 "CO", N406 'County name' (N406 character length: 30 AlphaNumeric) What will serve as the 'single source' for County listings? (Texas Comptroller, NOAA, NWS) |  | 814_04, 814_05, 814_14, 814_20, 814_22 | 5.0 | NEEDED
16 | Need Unexecutable code added to 650_02 and 814_28 to address instances where a customer has installed Distributed Generation without an Automatic Transfer Switch (ATS) and/or a signed interconnection agreement with the TDSP | ERCOT, CR, TDSP, Service Provider | Add code J009—"DG Customer Requires Automatic Transfer Switch (ATS) installation and/or signed Interconnection Agreement" |  | 650_02, 814_28 | 5.0 | NEEDED
17 | Need Unexecutable code added to 650_01, 650_02, 650_04 and 814_28 for a code clearance violation | ERCOT, CR, TDSP, Service Provider | Add Required element for code "00x–Code Clearance Violation" (create within Change Control) Possibly add a comment in the REF03 that contains the service standards code for the specific violation. |  | 650_01, 650_02, 650_04, 814_28 | 5.0 | NEEDED
18 | Construction Hold | ERCOT, CR, TDSP, Service Provider | Use "CHP" when TDSP identifies Construction Hold needed to add transparency for CRs |  | 814_04, 814_05 | 5.0 | 809
19 | IAS/IAG Solution | TBD | Automation to replace the MarkeTrak portion for CRs. TDSPs to evaluate how to automate TDSP portion for cancel/rebilling process. TDSPs will discuss further. Bring back more for TXSET discussions. |  |  | TBD | TBD
11 | Customer contact information: TDSP Request Contact Information | TBD | TDSP-initiated 814_PC? Can TDSPs leverage CBCI files that are already sent by CRs? Each TDSP would filter for own ESIIDs from master file Idea: CRs submit CBCI files monthly to ERCOT. ERCOT would create report/extract and post on MIS by TDSP DUNS. |  | TBD | TBD | TBD
12 | Customer contact information: Add Optional E-mail field on the 814_01, 814_03, & 814_16 | TBD | Add optional email field on enrollment transactions Possibly rearrange location of the Email field on the 814_PC?? |  | 814_01, 814_03, 814_16 | TBD | TBD
13 | Customer contact information: Adding direct customer authorization from Customer via CRs to sign up customer for TDSP Outage notifications | TBD | When CRs send MVI/SWI, CRs would include a Y/N authorization which would then require a mobile number in the 814_01 or 814_16. It would pass through to TDSP to authorize enrollment to the TDSP's Outage Alert/Mobile Alert program. Each TDSP has different criteria needed, which will be discussed among the TDSPs. |  | 814_01, 814_03, 814_16 | TBD | TBD
14 | If known by TDSP, communicate to CRs if meter set is required | TBD | If TDSP knows that a meter does not exist at the location, how to communicate to market that a meter set will be needed. Unless it is a brand new meter set (new construction), difficult for TDSPs to know on front end when meter set is needed. Generally won't know until field personnel has been dispatched. MORE DISCUSSION NEEDED. |  |  | TBD | TBD
| Timeline for TXSET 5.0 release |  | Gathering requirements through 2020 Initiate project 2021 Go-live mid-2022 |  | N/A | 5.0
| Timeline for TXSET 4.0A release |  | ERCOT to begin testing Q3 2020 (August)??? Separate project but would utilize the same resources for the EDI Translator Project (PR288-01) |  | N/A | 4.0A