## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
February 13, 2020

## Slide 2
Project Portfolio Update
  Recent / Upcoming Project Implementations
  2020 Release Targets
  Planned Project Starts
  2020 Project Spending Forecast
  Revision Request Funding Placeholder Status
  Priority/Rank Options for Revision Requests with Impacts
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Implementations
2020 January Release – Off-Cycle – 1/19/2020 Complete
  NPRR943 – Holiday Schedule Update
2020 February Release – R1 – 2/4/2020 – 2/6/2020 Complete
  NPRR873 – Posting of ERCOT Wide Intra-Hour Wind Power & Load Forecast on MIS Public
  SCR797 – Provide Current Operating Plans (COPs) to TSPs
2020 March Release – Off-Cycle – 3/1/2020 In Flight
  NPRR863 Phase 1 – Creation of ECRS and Revisions to Responsive Reserve
    FFR portion only
  NPRR960 – Phased Approach and Clarifications for NPRR863, Creation of ERCOT Contingency Reserve Service and Revisions to Responsive Reserve
  NOGRR187 – Related to NPRR863, Creation of ERCOT Contingency Reserve Service and Revisions to Responsive Reserve
  OBDRR011 – ORDC OBD Revisions for PUCT Project 48551
2020 April Release – R2 – 3/31/2020 – 4/2/2020 In Flight
  NPRR928 – Cybersecurity Incident Notification
  NPRR929 – PTP Obligations with Links to an Option DAM Award Eligibility
  SCR802 – Enhance Communications of System Inertia
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2020 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/4 – 2/6 | April 3/31 – 4/2 | May 5/26 – 5/28 | August 8/4 – 8/6 | October 10/13 – 10/15 | December 12/8 – 12/10
NPRR873 SCR797 NPRR877 Ph2 NPRR968 NPRR943 EMIL Web Interface NPRR863 Ph1 NPRR960 OBDRR011 | SCR802 NPRR928 NPRR929 SCR781(a) RRGRR016 RRGRR019 | NPRR856 NPRR884 NPRR935 OBDRR006 SCR803 NPRR887 NPRR907 NPRR985 | NPRR902 NPRR905 NPRR951 MIS testing SCR804 SCR781(a) | NPRR936 MIS Go-Live MMS/OS Refresh | SCR799 NPRR857 NPRR863 Ph2 NPRR885 NPRR917 NPRR941 PGRR070(b) SCR781(b)
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
NS
R1
R2
R3
R4
R5
R6
3/1
NPRR863 Ph1 – FFR
NPRR863 Ph2 – ECRS
NPRR935(a) – All changes except Section 4.2.3
NPRR935(b) – Section 4.2.3 changes
PGRR070(b) – Remaining PGRR language
SCR781(a) – View / Edit capability
SCR781(b) – Add capability
MMS/OS Upgrade “Chill”
MMS/OS Upgrade “Freeze”
April RIOO
RARF Go-Live for View/Update
E
E
E
ü
ü
ü
E
E
P
P
P
P
I
E
E
E
November
Off-Cycle
1/1
Future Year Go-Live Targets
2021
2022
NS
NS
NS
P
NS
NS
E
E
September
Off-Cycle
NS
NS
NS
P
1/19
E
ü
ü
TBD Items | 2017 | 2018 | 2019
 | NPRR702, NPRR829 | NPRR825(b), NPRR867, NPRR841 | NPRR887, NPRR904, OBDRR009, NPRR879, NPRR918, NRR935(b), NPRR939, PGRR066, SCR800
ü
CMM Release 2a
1/30
August
October
Q3 RIOO
RARF Go-Live for View/Update

## Slide 5: Approved Revision Requests “Not Started” – Planned to Start in Future Months
Revision Request | Target Start Date | Release Target | Cost Estimate | Author
NPRR863 Phase 2 – Creation of ERCOT Contingency Reserve Service (ECRS) | Feb 2020 | 2021 | $1.9M-$2.9M | ERCOT
NPRR902 – ERCOT Critical Energy Infrastructure Information | Feb 2020 | 2020-R4 | $150k-$225k | ERCOT
NPRR905 – CRR Balancing Account Resettlement | Feb 2020 | 2020-R4 | $60k-$80k | MSWG
NPRR951 – Active and Inactive SCED Constraint Reporting | Mar 2020 | 2020-R4 | $25k-$45k | DC Energy
NPRR936 – CRR Account Holder Limits | Apr 2020 | 2020-TBD | $150k-$250k | Engie
SCR799 – ERCOT Outage Study Cases in the System Operations Test Env. (SOTE) | May 2020 | 2020-R6 | $150k-$250k | Oncor
Project Initiations – Next 3 Months
Moved from January start
Moved from February start Potential bundle with SCR807 or SCR808

## Slide 6: 2020 Project Spending
2020 PPL Budget = $29.0M
“Potential Demand” represents internal ERCOT projects that have not been fully approved
May actuals not yet available
June-December forecasts are updated

## Slide 7: Revision Request Funding Placeholder Status
In ERCOT’s 2020/2021 proposed budget, the following amounts are allocated for Revision Request work
  2020 = $4M
  2021 = $4M
Yearly Revision Request Spending Forecast Summary
Project Status | 2020 | 2021
YTD Actuals | $0.20M | -
Approved – In-Flight / Complete | $1.47M | $0.39M
Approved – Not Started | $1.66M | $1.46M
Remaining Funding | $0.87M | $2.15M
Total Allocation | $4.00M | $4.00M
As of 1/31/2020

## Slide 8: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR973 | Add Definitions for Generator Step-Up and Main Power Transformer | N/A | N/A | <$10k to be absorbed into PR106-01 RARF Replacement (RIOO) project
SCR807 | Increase CRR Transaction Capability | TBD | TBD | IA posted on 1/14/2020 PRS discussion expected
SCR808 | Congestion Revenue Right Time Of Use Transaction Limits in Long-Term Auction Sequence Auctions | TBD | TBD | IA posted on 1/14/2020 PRS discussion expected
Options for…
PPL Rank Information
Next available 2020 Rank in Business Strategy = 2990
Next available Rank in Regulatory = 260
Note
Items in the Regulatory section of the PPL are not tracked against the market Revision Request funding allocation