## Slide 1
CDR Planned Projects:
Predicted vs. Actual In-service Dates
Supply Analysis Working Group
Dan Mantena
Resource Adequacy
February 20, 2020

## Slide 2: The December 2018 CDR showed 20 planned projects would go online before Summer 2019
Only 4 of the 20 listed projects went operational before June 1st, 2019.

## Slide 3: CDR eligible criteria for planned projects
Current criteria used in CDR/SARA reports for planned projects
Signed interconnection agreement with TSP
Additional requirements for thermal projects
  Air and GHG Permits from TCEQ
  Proof of Adequate Water Supplies
Planned projects listed in Dec 2018 CDR for summer 2019

## Slide 4: Performance review of December 2018 CDR

## Slide 5: Two ways to improve planned project forecast
Reduce false positives
Reduce false negatives

## Slide 6: Evaluating different criteria for planned projects

## Slide 7: Impact of different criteria on December 2018 CDR planned projects

## Slide 8: Criteria sensitivity results for December 2018 CDR
Criteria | # of false positive projects | # of false negative projects | total projects | Rank
+ Commissioning Plan Submitted | 4 | 1 | 5 | 1
+ Part 1 POI Energization | 6 | 0 | 6 | 2
+ Section 6.9 (1) + Full Interconnect Study | 6 | 2 | 8 | 3
+ Financial Security and Notice to Proceed | 7 | 2 | 9 | 4
+ Quarterly System Assessment (QSA) | 13 | 1 | 14 | 5
+ Section 6.9 (1) | 14 | 1 | 15 | 6
+ Full Interconnect Study | 15 | 0 | 15 | 6
Base case (current CDR criteria) | 16 | 0 | 16 | 8

## Slide 9: Criteria sensitivity results for recent December CDRs
Criteria | Rank for Dec 2018 CDR (Summer 2019) | Rank for Dec 2017 CDR (Summer 2018) | Rank for Dec 2016 CDR (Summer 2017)
+ Commissioning Plan Submitted | 1 | 1 | 6
+ Part 1 POI Energization | 2 | 1 | 1
+ Section 6.9 (1) + Full Interconnect Study | 3 | 3 | 3
+ Financial Security and Notice to Proceed | 4 | 8 | 6
+ Quarterly Stability Assessment (QSA) | 5 | 6 | 6
+ Section 6.9 (1) | 6 | 3 | 3
+ Full Interconnect Study | 6 | 6 | 1
Base case (current CDR criteria) | 8 | 3 | 5
Top 3 criteria's for each CDR report are highlighted in green.

## Slide 10: Highlighting most effective criteria’s for December CDRs

## Slide 11: Findings
December CDR reports frequently list planned projects that don’t go operational before the start of the upcoming summer
GINR project milestones that have the potential to filter out these projects in future CDR reports
  Commissioning Plan Submitted
  Part 1 POI Energization Approval
  Planning Guide Section 6.9 (1) + Full Interconnect Study

## Slide 12: Appendix

## Slide 13: Criteria sensitivity results for Dec 2017 CDR
Criteria | # of false positive projects | # of false negative projects | total projects | Rank
+ Part 1 POI Energization | 1 | 3 | 4 | 1
+ Commissioning Plan Submitted | 2 | 2 | 4 | 1
Base case (current CDR criteria) | 6 | 0 | 6 | 3
+ Section 6.9 (1) | 6 | 0 | 6 | 3
+ Section 6.9 (1) + Full Interconnect Study | 6 | 0 | 6 | 3
+ Full Interconnect Study | 6 | 1 | 7 | 6
+ Quarterly Stability Assessment (QSA) | 0 | 7 | 7 | 6
+ Financial Security and Notice to Proceed | 1 | 7 | 8 | 8

## Slide 14: Criteria sensitivity results for Dec 2016 CDR
Criteria | # of false positive projects | # of false negative projects | total projects | Rank
+ Part 1 POI Energization | 4 | 3 | 7 | 1
+ Full Interconnect Study | 7 | 0 | 7 | 1
+ Section 6.9 (1) | 9 | 0 | 9 | 3
+ Section 6.9 (1) + Full Interconnect Study | 9 | 0 | 9 | 3
Base case (current CDR criteria) | 12 | 0 | 12 | 5
+ Commissioning Plan Submitted | 1 | 12 | 13 | 6
+ Quarterly Stability Assessment (QSA) | 0 | 13 | 13 | 6
+ Financial Security and Notice to Proceed | 0 | 13 | 13 | 6