## KTC 02-28-20
BESTF Meetings in 2019/2020
Key Topic & Concept (KTC) | Item | Decision Points and Issues for Developing Principle Concepts | BESTF-NPRR | Support Combo-Model (C)/Single Model (S) | KTC Type (Operations, Markets, & Planning) | Date Topic was First Presented to the BES Task Force | Estimated Date for First/Next Discussion | Estimated Final Meeting for Moving to TAC for Vote | 2019-10-18 | 2019-11-04 | 2019-11-15 | 11/20 TAC | 2019-12-06 | 2020-01-17 | 1/29/2020 TAC | 2020-02-25 | 2020-03-13 | 2020-04-10 | 2020-05-01 | 2020-05-21 | 2020-06-12 | 2020-06-30 | 2019-07-23 | 2020-08-14 | 2020-09-11 | 2020-09-29 | 2020-10-22 | 2020-11-13
Key Topic 1 Definitions and Registration for Energy Storage Resources | 1 | Registration of a battery as a single resource and identified as an Energy Storage Resource (ESR). (Protocol Language and system changes.) NPRR 957 (RTF-4 Definition of Energy Storage Resource and Related Registration and Telemetry Requirements) introduces the ESR definition so that subsequent NPRRs can use the ESR definition. | BESTF-5 (NPRR 1002) | Combo and Single | All | 2019-11-04 | 2019-11-04 | 2019-12-06
Key Topic 2 Physical Responsive Capability, and ORDC Reserve | 1 | Energy Storage Resources contribution to PRC | BESTF-3 (NPRR987) | Combo and Single | Operations | 2019-10-18 | 2019-10-18 | 2019-11-04
| 2 | Energy Storage Resources contribution to ORDC Reserves | BESTF-3 (NPRR987) | Combo and Single | Markets | 2019-10-18 | 2019-10-18 | 2019-11-04
Key Topic 3 Dispatch, Pricing, and Mitigation | 1 | SCED dispatch and Nodal pricing (basepoint weighting) of Energy Storage Resources when charging and discharging | BESTF-2 (NPRR 986) | Combo and Single | Markets/Operations | 2019-10-18 | 2019-10-18 | 2019-11-04
| 2 | Mitigation treatment in SCED | BESTF-2 (NPRR 986) | Combo and Single | Markets/Operations | 2019-10-18 | 2019-10-18 | 2019-11-04
| 3 | Reporting Requirements on how often mitigation would have been applied. | BESTF-2 (NPRR 986) | Combo and Single | Markets/Operations | 2019-10-18 | 2019-10-18 | 2019-11-04
| 4 | Charging restrictions during an emergency conditions (Note PUCT rule on charging during emergencies.) | BESTF-5 (NPRR 1002) | Combo and Single | Operations | 2019-11-04 | 2019-11-04 | 2020-01-17
Key Topic 4 Technical Requirements | 1 | Reactive Capability and Voltage Support Service | BESTF-1 (NPRR 989) | Combo and Single | Operations | 2019-10-18 | 2019-10-18 | 2019-11-04
| 2 | Voltage/frequency Ride-through requirements | BESTF-1 (NPRR 989) | Combo and Single | Operations | 2019-10-18 | 2019-10-18 | 2019-11-04
| 3 | Governor Deadband and Droop Setting Requirement | BESTF-1 (NPRR 989) | Combo and Single | Operations | 2019-10-18 | 2019-10-18 | 2019-11-04
| 4 | Governor Testing | BESTF-1 (NPRR 989) | Combo and Single | Operations | 2019-10-18 | 2019-10-18 | 2019-11-04
Key Topic 5 Performance | 1 | Energy Storage Resource Performance Deployment (ESRDP) - NPRR 963 | NA | Combo Model | Operations | 2019-10-18 | 2019-10-18 | NA
| 2 | Energy Storage Resource Performance Deployment (ESRDP) | BESTF-4 | Single Model | Operations | 2019-11-04 | 2019-11-04 | 2019-11-15
Key Topic 6 ESR Options to maintain desired level of State of Charge | 1 | Allow Energy Storage Resources to update their EOC closer to real-time | BESTF-2 (NPRR 986) | Combo and Single | Markets | 2019-10-18 | 2019-10-18 | 2019-11-04
| 2 | single model ESR attributes and Offer structure | BESTF-4 | Single Model | Markets | 2019-11-04 | 2019-11-04 | 2020-01-17
Key Topic 7 Settlement | 1 | Base-Point Deviation (BPD) - NPRR 963 | NA | Combo Model | Markets | 2019-10-18 | 2019-10-18 | NA
| 2 | Single model ESR settlement changes | BESTF-4 | Single Model | Markets | 2019-11-04 | 2019-11-04 | 2019-12-06
| 3 | Single model ESR Base-Point Deviation (BPD) | BESTF-4 | Single Model | Markets | 2019-11-04 | 2019-11-04 | 2019-12-06
| 4 | SODG /SOTG settled at Nodal pricing while charging and discharging |  | Policy | Markets |  | 2020-04-10
| 5 | ESR Settlement using Nodal basepoint weighted prices | BESTF-4 | Combo and Single | Markets | 2019-11-04 | 2019-11-04 | 2019-12-06
| 6 | ESR Reliability Instructions and Associated Settlement | NA | Single Model | Markets | 2019-12-06 | 2019-12-06
| 6 | ESR treatment during SCED Failures (RTCTF assigned) | NA | Single Model | Markets | 2019-11-15 | 2019-11-15 | NA
Key Topic 8 WSL Treatment | 1 | Should WSL treatment implementation extend to batteries that can self-serve PUN Load with the stored energy? | NA | Policy | Markets | 2019-11-15 | 2019-11-15 | 2019-12-06
| 2 | Should WSL treatment implementation extend to non-dispatched generators? If yes, should there be differentiation between a SOG that is co-located with customer load and one that only has auxiliary loads behind the metering point? |  | Policy | Markets | 2019-11-15 | 2019-11-15 | TBD
Key Topic 9 ESR on the Distribution System | 1 | How is an ESR (in SCED) interconnected to the distribution system addressed in the protocols and handled by the ERCOT systems? (Coordinate with DGR Workshops) |  | Policy | Markets |  | 2020-04-10
Key Topic 10 ESR - Study & Capacity Assumptions | 1 | Define "Storage Peak Average Capacity Percentage" to be used in CDR for various batteries. | Future SAWG NPRR | Policy | Markets/Operations | 2019-11-15 | 2019-11-15 | 2020-01-17
| 2 | Outage Coordination Studies | NA | Policy | Operations | 2019-11-15 | 2019-11-15 | 2020-01-17
| 3 | Reliability Unit Commitment Studies | NA | Combo Model | Markets/Operations | 2019-10-18 | 2019-10-18 | 2019-11-04
| 4 | Operational Studies | NA | Policy | Operations | 2019-11-15 | 2019-11-15 | 2020-01-17
| 5 | Transmission Planning Studies | NA | Policy | Planning | 2019-11-15 | 2019-11-15 | 2020-01-17
| 6 | Reliability Unit Commitment Studies |  | Single Model | Markets/Operations | 2019-12-06 | 2019-12-06
Key Topic 11 DC Coupled Resources | 1 | Resource Definition and Registration |  | Policy | All | 2020-01-17 | 2020-01-17 | 2020-03-13
| 2 | Participation Model (EMS and MMS) |  | Policy | All | 2020-01-17 | 2020-01-17 | 2020-03-13
| 3 | Forecasting PV/Wind |  | Policy | All | 2020-01-17 | 2020-01-17 | 2020-03-13
| 4 | Performance |  | Policy | Market/Operations | 2020-01-17 | 2020-01-17 | 2020-03-13
| 5 | Mitigation treatment in SCED |  | Policy | Markets | 2020-01-17 | 2020-01-17 | 2020-03-13
| 6 | WSL Treatment & Renewable Energy Credits |  | Policy | Markets | 2020-01-17 | 2020-01-17 | 2020-03-13
| 7 | Data Requirements from QSEs |  | Policy | All | 2020-01-17 | 2020-01-17 | 2020-03-13
| 8 | Operations and Planning Studies |  | Policy | All | 2020-01-17 | 2020-01-17 | 2020-03-13
| 9 | Resource Adequacy Reporting |  | Policy | All | 2020-01-17 | 2020-01-17 | 2020-03-13
| 10 | Proxy Offer Curve and Bid to Buy for DC Coupled Resources |  | Policy | All | 2020-01-17 | 2020-01-17 | 2020-03-13
| 11 | RUC Capacity Short Calculations |  | Policy | All | 2020-02-25 | 2020-02-25 | 2020-03-13
| 12 | Physical Responsive Reserve (PRC) and Real-Time On-Line Capacity (RTOLCAP) Calculations |  | Policy | All | 2020-02-25 | 2020-02-25 | 2020-03-13
| 13 | Charging an ESS portion of DC Coupled Resource under ERCOT Emergency Conditions |  | Policy | All | 2020-02-25 | 2020-02-25 | 2020-03-13
| 14 | Resource Statuses |  | Policy | All | 2020-02-25 | 2020-02-25 | 2020-03-13
Key Topic 12 AC Coupled Resources that want to operate as one resource | 1 | Registration |  | Policy | All | 2020-01-17 | 2020-01-17 | 2020-03-13
| 2 | IRR/Battery operating as single unit |  | Policy | All | 2020-01-17 | 2020-01-17 | 2020-03-13
| 3 | GT/Battery operating as single unit |  | Policy | All | 2020-01-17 | 2020-01-17 | 2020-03-13
| 4 | Participation Model (EMS and MMS) |  | Policy | Markets/Operations | 2020-01-17 | 2020-01-17 | 2020-03-13
| 5 | WSL Treatment |  | Policy | Markets | 2020-01-17 | 2020-01-17 | 2020-03-13
| 6 | Forecasting |  | Policy | All | 2020-01-17 | 2020-01-17 | 2020-03-13
| 7 | Should existing performance exemptions to IRR apply? |  | Policy | Market/Operations | 2020-01-17 | 2020-01-17 | 2020-03-13
| 8 | Interconnection Issues |  | Policy | All | 2020-01-17 | TBD | 2020-03-13
Key Topic 13 Self-Limiting issues related to Interconnection Requests for Energy Storage Resources | 1 | Self Limit Assumptions |  | Policy | All | 2020-01-17 | 2020-01-17 | 2020-03-13
| 2 | Compliance and Monitoring program for Self-Limiting Resources |  | Policy | All | 2020-01-17 | 2020-01-17 | 2020-03-13
| 3 | Real-Time Telemetry and COP requirements |  | Policy | All | 2020-01-17 | 2020-01-17 | 2020-03-13
| 4 | GINR study Pmax for DC Coupled Resource |  | Policy | All | 2020-01-17 | 2020-01-17 | 2020-03-13
| 5 | Resource Adequacy Reporting |  | Policy | All | 2020-01-17 | 2020-01-17 | 2020-03-13
| 6 | GINR Process- Adding battery to existing PV/WGR site and sharing the existing inverter (DC-Coupled) - No Grid Charging (Column C) |  | Policy | All | 2020-01-17 | 2020-01-17 | 2020-03-13
| 7 | GINR Process- Adding battery to existing PV/WGR site and sharing the existing inverter (DC-Coupled) - With Grid Charging (Column B) |  | Policy | All | 2020-01-17 | 2020-01-17 | 2020-03-13
| 8 | GINR Process- Adding battery to existing thermal generation site (AC Coupled) (Column A) |  | Policy | All | 2020-01-17 | 2020-01-17 | 2020-03-13
| 9 | GINR Process- Adding battery to existing PV/WGR site (AC Coupled) (Column A) |  | Policy | All | 2020-01-17 | 2020-01-17 | 2020-03-13
| 10 | GINR Process - New DC Coupled Resource (Column G) |  | Policy | All | 2020-01-17 | 2020-01-17 | 2020-03-13
| 11 | GINR Process - New AC Coupled Resource (Column H) |  | Policy | All | 2020-01-17 | 2020-01-17 | 2020-03-13
Key Topic 14 Review existing Study Requirements and Determine if new Studies are Needed | 1 | Identify if new studies are needed for interconnecting ESR due to interactions between the controls of the ESR and neighboring active devices such as HVDC tie, SVC, STATCOM, or ESR. |  | Policy | All | 2020-02-25 | 2020-02-25 | Topic closed at 2/25/20 BESTF meeting (Part of IBR work)
Key Topic 15 Additional Items | 1 | Proxy Offer Curve and Bid to Buy for ESRs |  | Policy | All | 2020-02-25 | 2020-02-25 | 2020-03-13