## Wind Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 19INR0174 | Elbow Creek repower | Howard | 2019-10-15 | 2007-11-30 | Wind | WT | 0 | 2019 | No
[6 empty] | 20INR0262 | High Lonesome Wind Phase II | Crockett | 2020-01-30 | 2019-07-22 | Wind | WT | 50.6 | 2020 | Yes
[6 empty] | 11INR0062 | Shaffer | Nueces | 2020-01-31 | 2013-07-02 | Wind | WT | 226 | 2020 | Yes
[6 empty] | 18INR0067 | Gopher Creek Wind | Borden | 2020-01-31 | 2018-01-26 | Wind | WT | 158 | 2020 | Yes
[6 empty] | 18INR0078 | Bobcat Bluff repower | Archer | 2020-02-24 | 2018-12-18 | Wind | WT | 12 | 2020 | No
[6 empty] | 19INR0053 | Hidalgo II Wind | Hidalgo | 2020-02-25 | 2019-04-25 | Wind | WT | 51 | 2020 | Yes
[6 empty] | 12INR0060 | Wilson Ranch | Schleicher | 2020-02-28 | 2018-05-21 | Wind | WT | 199.5 | 2020 | Yes
[6 empty] | 17INR0052 | Horse13 CallD repower | Taylor | 2020-02-28 | 2019-05-22 | Wind | WT | 44 | 2020 | Yes
[6 empty] | 18INR0033 | Oveja Wind | Irion | 2020-02-28 | 2018-07-24 | Wind | WT | 300 | 2020 | Yes
[6 empty] | 19INR0080 | Whitehorse Wind | Fisher | 2020-03-09 | 2018-12-05 | Wind | WT | 418.9 | 2020 | Yes
[6 empty] | 17INR0037 | Palmas Altas Wind | Cameron | 2020-03-16 | 2017-11-30 | Wind | WT | 144.9 | 2020 | Yes
[6 empty] | 19INR0038 | High Lonesome W | Crockett | 2020-03-20 | 2018-04-17 | Wind | WT | 449.5 | 2020 | Yes
[6 empty] | 17INR0069 | Trent repower | Nolan | 2020-03-31 | 2018-10-19 | Wind | WT | 6.4 | 2020 | No
[6 empty] | 17INR0070 | Desert Sky repower | Pecos | 2020-03-31 | 2018-10-18 | Wind | WT | 7.2 | 2020 | Yes
[6 empty] | 19INR0163 | Sage Draw Wind | Lynn | 2020-03-31 | 2018-01-03 | Wind | WT | 338 | 2020 | Yes
[6 empty] | 20INR0011 | Ranchero Wind | Crockett | 2020-03-31 | 2018-05-02 | Wind | WT | 300 | 2020 | Yes
[6 empty] | 16INR0081 | Mesteno Windpower | Starr | 2020-04-01 | 2018-04-25 | Wind | WT | 201.6 | 2020 | Yes
[6 empty] | 18INR0018 | Peyton Creek Wind | Matagorda | 2020-04-01 | 2018-03-19 | Wind | WT | 151.2 | 2020 | Yes
[6 empty] | 18INR0038 | Barrow Ranch | Andrews | 2020-04-15 | 2018-06-26 | Wind | WT | 160 | 2020 | Yes
[6 empty] | 15INR0064b | Harald (BearKat Wind B) | Glasscock | 2020-04-16 | 2018-05-30 | Wind | WT | 162.1 | 2020 | Yes
[6 empty] | 17INR0068 | Sweetwater 2 repower | Nolan | 2020-04-30 | 2017-11-17 | Wind | WT | 7.3 | 2020 | No
[6 empty] | 19INR0112 | Cranel Wind | Refugio | 2020-05-15 | 2018-10-12 | Wind | WT | 220 | 2020 | Yes
[6 empty] | 18INR0075 | Gulf Wind 1 repower | Kenedy | 2020-06-01 | 2007-08-28 | Wind | WT | 0 | 2020 | No
[6 empty] | 16INR0086 | Cactus Flats Wind | Concho | 2020-06-30 | 2017-03-15 | Wind | WT | 148.4 | 2020 | Yes
[6 empty] | 17INR0061 | Capricorn IV repower | Sterling | 2020-06-30 | 2008-01-15 | Wind | WT | 9 | 2020 | No
[6 empty] | 18INR0059 | East Raymond Wind | Willacy | 2020-06-30 | 2018-09-18 | Wind | WT | 201.6 | 2020 | Yes
[6 empty] | 18INR0069 | Indian Mesa repower | Pecos | 2020-06-30 | 2018-12-04 | Wind | WT | 0 | 2020 | No
[6 empty] | 18INR0070 | Blue Summit II | Wilbarger | 2020-06-30 | 2018-11-09 | Wind | WT | 102 | 2020 | Yes
[6 empty] | 18INR0079 | Woodward I repower | Pecos | 2020-06-30 | 2018-12-12 | Wind | WT | 0 | 2020 | No
[6 empty] | 18INR0080 | Woodward 2 repower | Pecos | 2020-06-30 | 2018-12-18 | Wind | WT | 0 | 2020 | No
[6 empty] | 19INR0182 | Blue Summit Wind III | Wilbarger | 2020-06-30 | 2019-04-09 | Wind | WT | 200 | 2020 | Yes
[6 empty] | 19INR0051 | Vera Wind | Knox | 2020-07-01 | 2018-07-10 | Wind | WT | 242.8 | 2020 | Yes
[6 empty] | 17INR0054 | Capricorn I & III repower | Sterling | 2020-07-05 | 2006-11-14 | Wind | WT | 32 | 2020 | No
[6 empty] | 18INR0016 | RTS 2 Wind | McCulloch | 2020-08-06 | 2017-11-21 | Wind | WT | 179.91 | 2020 | Yes
[6 empty] | 18INR0064 | Silver Star repower | Eastland | 2020-08-10 | 2018-10-16 | Wind | WT | -7.2 | 2020 | Yes
[6 empty] | 19INR0120 | Sherbino II Wind repower | Pecos | 2020-08-10 | 2008-02-28 | Wind | WT | -18 | 2020 | Yes
[6 empty] | 20INR0019 | Trinity Hills Wind repower | Young | 2020-08-10 | 2018-10-17 | Wind | WT | -27 | 2020 | No
[6 empty] | 19INR0100 | Prairie Hill Wind | McLennan | 2020-09-01 | 2018-09-17 | Wind | WT | 300 | 2020 | Yes
[6 empty] | 20INR0045 | Maverick Creek I W | Concho | 2020-09-01 | 2018-07-30 | Wind | WT | 373.2 | 2020 | Yes
[6 empty] | 20INR0052 | Griffin Trail Wind | Knox | 2020-09-30 | 2019-03-04 | Wind | WT | 201.6 | 2020 | No
[6 empty] | 19INR0156 | Aviator Wind | Coke | 2020-10-01 | 2019-02-14 | Wind | WT | 525 | 2020 | Yes
[6 empty] | 17INR0027b | Coyote Wind | Scurry | 2020-10-29 | 2016-08-09 | Wind | WT | 242.6 | 2020 | Yes
[6 empty] | 17INR0035 | Las Majadas Wind | Willacy | 2020-10-29 | 2018-04-13 | Wind | WT | 272.6 | 2020 | Yes
[6 empty] | 14INR0009 | WKN Amadeus Wind | Fisher | 2020-10-30 | 2018-03-15 | Wind | WT | 250.12 | 2020 | Yes
[6 empty] | 17INR0025 | Reloj Del Sol Wind | Zapata | 2020-10-31 | 2018-12-21 | Wind | WT | 202 | 2020 | Yes
[6 empty] | 20INR0046 | Maverick Creek II W | Concho | 2020-11-11 | 2018-07-30 | Wind | WT | 118.8 | 2020 | Yes
[6 empty] | 16INR0037c | Pumpkin Farm Wind | Floyd | 2020-12-01 | 2017-03-24 | Wind | WT | 280.9 | 2020 | Yes
[6 empty] | 16INR0111 | Las Lomas Wind | Starr | 2020-12-01 | 2018-12-22 | Wind | WT | 200 | 2020 | Yes
[6 empty] | 18INR0042 | Kaiser Creek Wind | Callahan | 2020-12-01 | 2019-07-11 | Wind | WT | 101.52 | 2020 | No
[6 empty] | 14INR0033 | Goodnight Wind | Armstrong | 2020-12-12 | 2018-03-07 | Wind | WT | 504.4 | 2020 | No
[6 empty] | 20INR0033 | WILDWIND | Cooke | 2020-12-15 | 2020-02-21 | Wind | WT | 180.08 | 2020 | No
[6 empty] | 20INR0088 | West Raymond (El Trueno) Wind | Willacy | 2020-12-15 | 2019-05-20 | Wind | WT | 239.8 | 2020 | Yes
[6 empty] | 17INR0031 | Espiritu Wind | Cameron | 2020-12-21 | 2020-01-29 | Wind | WT | 25.2 | 2020 | Yes
[6 empty] | 20INR0042 | Chalupa Wind | Cameron | 2020-12-21 | 2018-09-28 | Wind | WT | 174 | 2020 | Yes
[6 empty] | 19INR0128 | White Mesa Wind | Crockett | 2020-12-31 | 2018-12-19 | Wind | WT | 500 | 2020 | Yes
[6 empty] | 18INR0031 | Maryneal Windpower | Nolan | 2021-02-15 | 2020-01-31 | Wind | WT | 182.4 | 2021 | Yes
[6 empty] | 18INR0030 | Canyon Wind | Scurry | 2021-03-31 | 2018-09-20 | Wind | WT | 360 | 2021 | Yes
[6 empty] | 16INR0074 | Chocolate Bayou W | Brazoria | 2021-05-01 | 2019-09-26 | Wind | WT | 149.5 | 2021 | No
[6 empty] | 18INR0068 | Loraine Windpark Phase III | Mitchell | 2021-05-01 | 2018-04-10 | Wind | WT | 100 | 2021 | Yes
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned | 20INR0083 | Baird North Wind | Callahan | 2021-06-15 | 2019-05-31 | Wind | WT | 331.2 | 2021 | Yes
2000 | 116 | 116 | 0 | 0 | 0 | 19INR0099a | Kontiki 1 Wind (ERIK) | Glasscock | 2021-06-30 | 2018-05-07 | Wind | WT | 255.3 | 2021 | Yes
2001 | 816 | 816 | 0 | 0 | 0 | 16INR0104 | Big Sampson Wind | Crockett | 2021-09-01 | 2019-11-08 | Wind | WT | 400 | 2021 | No
2002 | 977 | 977 | 0 | 0 | 0 | 18INR0043 | Edmondson Ranch Wind | Glasscock | 2021-12-01 | 2017-10-04 | Wind | WT | 293.28 | 2021 | Yes
2003 | 1173 | 1173 | 0 | 0 | 0 | 19INR0052 | TG East Wind | Knox | 2021-12-15 | 2018-10-22 | Wind | WT | 336 | 2021 | Yes
2004 | 1385 | 1385 | 0 | 0 | 0 | 20INR0068 | Blackjack Creek Wind | Bee | 2021-12-15 | 2019-10-24 | Wind | WT | 239.8 | 2021 | Yes
2005 | 1854 | 1854 | 0 | 0 | 0 | 16INR0033 | Hart Wind | Castro | 2021-12-31 | 2018-08-06 | Wind | WT | 150 | 2021 | No
2006 | 2875 | 2875 | 0 | 0 | 0 | 19INR0022 | Monte Alto I | Willacy | 2021-12-31 | 2020-02-05 | Wind | WT | 223.8 | 2021 | No
2007 | 4785 | 4785 | 0 | 0 | 0 | 19INR0099b | Kontiki 2 Wind (ERNEST) | Glasscock | 2022-06-30 | 2018-05-07 | Wind | WT | 255.3 | 2022 | Yes
2008 | 8005 | 8005 | 0 | 0 | 0
2009 | 8916 | 8916 | 0 | 0 | 0
2010 | 9400 | 9400 | 0 | 0 | 0
2011 | 9604 | 9604 | 0 | 0 | 0
2012 | 10407 | 10407 | 0 | 0 | 0
2013 | 11065 | 11065 | 0 | 0 | 0
2014 | 12470 | 12470 | 0 | 0 | 0
2015 | 15764 | 15764 | 0 | 0 | 0
2016 | 17604 | 17604 | 0 | 0 | 0
2017 | 20682 | 20682 | 0 | 0 | 0
2018 | 21777 | 21777 | 0 | 0 | 0
2019 | 23860 | 23860 | 0 | 0 | 0
2020 | 33197.24 | 23834.24 | 8336 | 1027 | 0
2021 | 36219.05 | 23834.24 | 10434.21 | 1950.6 | 0
2022 | 36474.35 | 23834.24 | 10689 | 1950.6 | 0

## Solar Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 19INR0185 | Lapetus Solar | Andrews | 2020-03-01 | 2018-12-21 | Solar | PV | 100 | 2020 | Yes
[6 empty] | 19INR0102 | Queen Solar Phase I | Upton | 2020-03-06 | 2018-09-26 | Solar | PV | 200 | 2020 | Yes
[6 empty] | 18INR0045 | Misae Solar | Childress | 2020-03-13 | 2018-07-18 | Solar | PV | 240.8 | 2020 | Yes
[6 empty] | 19INR0083 | Oberon Solar | Ector | 2020-04-29 | 2018-10-11 | Solar | PV | 180 | 2020 | Yes
[6 empty] | 20INR0298 | Queen Solar Phase II | Upton | 2020-04-30 | 2020-01-09 | Solar | PV | 200 | 2020 | Yes
[6 empty] | 19INR0184 | Oxy Solar | Ector | 2020-05-15 | 2019-01-30 | Solar | PV | 16.2 | 2020 | Yes
[6 empty] | 19INR0114 | Rambler Solar | Tom Green | 2020-05-31 | 2018-10-11 | Solar | PV | 200 | 2020 | Yes
[6 empty] | 18INR0062 | Wagyu Solar | Brazoria | 2020-06-01 | 2019-06-03 | Solar | PV | 120 | 2020 | Yes
[6 empty] | 19INR0009 | Holstein Solar | Nolan | 2020-06-01 | 2018-09-15 | Solar | PV | 204.47 | 2020 | Yes
[6 empty] | 18INR0039 | Fowler Ranch | Crane | 2020-06-03 | 2018-10-23 | Solar | PV | 152.5 | 2020 | Yes
[6 empty] | 19INR0092 | Prospero Solar | Andrews | 2020-06-30 | 2018-04-20 | Solar | PV | 300 | 2020 | Yes
[6 empty] | 18INR0055 | Long Draw Solar | Borden | 2020-07-31 | 2018-08-16 | Solar | PV | 226.73 | 2020 | Yes
[6 empty] | 16INR0114 | Upton Solar | Upton | 2020-09-01 | 2015-12-04 | Solar | PV | 104.56 | 2020 | Yes
[6 empty] | 19INR0045 | Rayos Del Sol | Cameron | 2020-10-22 | 2018-11-06 | Solar | PV | 150 | 2020 | Yes
[6 empty] | 19INR0034 | Greasewood Solar | Pecos | 2020-11-30 | 2019-01-25 | Solar | PV | 255 | 2020 | Yes
[6 empty] | 20INR0054 | Taygete Solar | Pecos | 2020-12-01 | 2018-10-26 | Solar | PV | 255.07 | 2020 | Yes
[6 empty] | 19INR0151 | Impact Solar | Lamar | 2020-12-15 | 2019-07-02 | Solar | PV | 198.55 | 2020 | Yes
[6 empty] | 15INR0090 | Pflugerville Solar | Travis | 2020-12-31 | 2017-06-13 | Solar | PV | 144 | 2020 | Yes
[6 empty] | 17INR0020b | RE Maplewood 2b Solar | Pecos | 2020-12-31 | 2019-05-06 | Solar | PV | 28 | 2020 | Yes
[6 empty] | 19INR0081 | Anson Solar | Jones | 2020-12-31 | 2019-06-05 | Solar | PV | 201.53 | 2020 | Yes
[6 empty] | 20INR0219 | Eunice Solar | Andrews | 2020-12-31 | 2019-12-11 | Solar | PV | 420 | 2020 | Yes
[6 empty] | 19INR0073 | Shakes Solar | Zavala | 2021-02-12 | 2018-10-26 | Solar | PV | 206 | 2021 | Yes
[6 empty] | 19INR0033 | Murphy Lake Solar | Kaufman | 2021-03-15 | 2019-12-27 | Solar | PV | 120 | 2021 | No
[6 empty] | 17INR0020a | RE Maplewood 2a Solar | Pecos | 2021-04-01 | 2019-05-06 | Solar | PV | 222 | 2021 | Yes
[6 empty] | 19INR0155 | Morrow Lake Solar | Frio | 2021-04-01 | 2019-08-29 | Solar | PV | 204 | 2021 | Yes
[6 empty] | 21INR0276 | Elara Solar | Frio | 2021-04-01 | 2019-07-12 | Solar | PV | 134 | 2021 | Yes
[6 empty] | 15INR0059 | Emerald Grove Solar | Pecos | 2021-04-10 | 2018-06-27 | Solar | PV | 108 | 2021 | Yes
[6 empty] | 19INR0091 | Phoenix Solar | Fannin | 2021-04-23 | 2019-10-22 | Solar | PV | 82.3 | 2021 | Yes
[6 empty] | 18INR0050 | Mustang Creek Solar | Jackson | 2021-05-01 | 2019-01-04 | Solar | PV | 150 | 2021 | Yes
[6 empty] | 20INR0226 | Timberwolf POI A | Upton | 2021-05-01 | 2019-12-11 | Solar | PV | 150 | 2021 | No
[6 empty] | 19INR0103 | Rodeo Solar | Andrews | 2021-05-15 | 2019-08-20 | Solar | PV | 205 | 2021 | No
[6 empty] | 21INR0026 | Juno Solar | Borden | 2021-05-15 | 2018-12-28 | Solar | PV | 313.2 | 2021 | No
[6 empty] | 15INR0044 | Corazon Solar | Webb | 2021-05-31 | 2020-01-09 | Solar | PV | 200 | 2021 | No
[6 empty] | 18INR0040 | Soda Lake Solar 1 | Crane | 2021-05-31 | 2018-08-20 | Solar | PV | 202.59 | 2021 | No
[6 empty] | 18INR0053 | Fort Bend Solar | Fort Bend | 2021-05-31 | 2019-06-30 | Solar | PV | 240 | 2021 | No
[6 empty] | 20INR0143 | Soda Lake Solar 2 | Crane | 2021-05-31 | 2018-08-20 | Solar | PV | 202.99 | 2021 | No
[6 empty] | 19INR0035 | Norton Solar | Runnels | 2021-06-01 | 2019-06-20 | Solar | PV | 125 | 2021 | Yes
[6 empty] | 19INR0041 | Myrtle Solar | Brazoria | 2021-06-01 | 2019-11-13 | Solar | PV | 240 | 2021 | Yes
[6 empty] | 19INR0044 | Lily Solar | Kaufman | 2021-06-01 | 2019-03-29 | Solar | PV | 148.05 | 2021 | No
[6 empty] | 19INR0121 | Galloway Solar | Concho | 2021-06-01 | 2019-12-20 | Solar | PV | 250 | 2021 | No
[6 empty] | 19INR0134 | Cottonwood Bayou | Brazoria | 2021-06-01 | 2019-11-13 | Solar | PV | 150 | 2021 | No
[6 empty] | 20INR0053 | Bravepost Solar | Tom Green | 2021-06-01 | 2019-10-30 | Solar | PV | 200 | 2021 | Yes
[6 empty] | 20INR0069 | Danish Fields Solar | Wharton | 2021-06-01 | 2020-02-24 | Solar | PV | 200 | 2021 | No
[6 empty] | 21INR0233 | Taygete II Solar | Pecos | 2021-06-01 | 2019-03-27 | Solar | PV | 256.25 | 2021 | Yes
[6 empty] | 21INR0431 | Galloway 2 Solar | Concho | 2021-06-01 | 2019-12-20 | Solar | PV | 110 | 2021 | No
[6 empty] | 20INR0091 | Misae Solar II | Childress | 2021-06-21 | 2019-02-21 | Solar | PV | 517.35 | 2021 | Yes
[6 empty] | 17INR0020c | RE Maplewood 2c Solar | Pecos | 2021-06-30 | 2019-05-06 | Solar | PV | 250 | 2021 | Yes
[6 empty] | 19INR0088 | Aragorn Solar | Culberson | 2021-06-30 | 2018-05-31 | Solar | PV | 187.2 | 2021 | No
[6 empty] | 20INR0032 | IP Titan | Culberson | 2021-06-30 | 2019-02-04 | Solar | PV | 270 | 2021 | No
[6 empty] | 21INR0229 | Prospero Solar II | Andrews | 2021-07-01 | 2020-01-17 | Solar | PV | 250 | 2021 | No
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned | 20INR0241 | Crowded Star Solar | Jones | 2021-07-02 | 2019-12-17 | Solar | PV | 400 | 2021 | No
2010 | 15 | 15 | 0 | 0 | 0 | 19INR0042 | Long Point Solar | Brazoria | 2021-12-01 | 2019-10-24 | Solar | PV | 100 | 2021 | No
2011 | 42 | 42 | 0 | 0 | 0 | 21INR0261 | Horizon Solar | Frio | 2021-12-31 | 2019-07-12 | Solar | PV | 204.09 | 2021 | Yes
2012 | 82 | 82 | 0 | 0 | 0 | 19INR0001 | Texas Solar Nova | Kent | 2022-01-31 | 2019-07-01 | Solar | PV | 252.2 | 2022 | Yes
2013 | 121 | 121 | 0 | 0 | 0 | 16INR0049 | Nazareth Solar | Castro | 2022-05-31 | 2018-05-10 | Solar | PV | 201 | 2022 | Yes
2014 | 193 | 193 | 0 | 0 | 0
2015 | 287.7 | 287.7 | 0 | 0 | 0
2016 | 566.4 | 566.4 | 0 | 0 | 0
2017 | 1068.7 | 1068.7 | 0 | 0 | 0
2018 | 1857.7 | 1857.7 | 0 | 0 | 0
2019 | 2281.4 | 2281.4 | 0 | 0 | 0
2020 | 6178.83 | 2281.42 | 3897.41 | 0 | 0
2021 | 12776.43 | 2281 | 6796.4 | 3699.03 | 0
2022 | 13230.05 | 2281.42 | 7249.6 | 3699.03 | 0

## Battery Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 20INR0089 | Chisholm Grid | Tarrant | 2020-11-20 | 2019-08-16 | Battery | BA | 200 | 2020 | Yes
[6 empty] | 20INR0220 | Eunice Storage | Andrews | 2020-12-31 | 2019-12-11 | Battery | BA | 40.26 | 2020 | Yes
[6 empty] | 21INR0244 | Madero Grid | Hidalgo | 2021-05-31 | 2019-12-06 | Battery | BA | 201.96 | 2021 | Yes
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned
2012 | 36 | 36 | 0 | 0 | 0
2013 | 36 | 36 | 0 | 0 | 0
2014 | 36 | 36 | 0 | 0 | 0
2015 | 36 | 36 | 0 | 0 | 0
2016 | 37 | 37 | 0 | 0 | 0
2017 | 69 | 69 | 0 | 0 | 0
2018 | 89 | 89 | 0 | 0 | 0
2019 | 104 | 104 | 0 | 0 | 0
2020 | 405.91 | 123.7 | 240.26 | 0 | 41.95
2021 | 607.87 | 123.7 | 442.22 | 0 | 41.95

## Gas-Combined Cycle Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 16INR0054 | NA | Harris | 2018-09-01 | 2016-10-27 | Gas | CC | 12 | 2018 | Yes
[6 empty] | 20INR0272 | RIO NOGALES AGP UPGRADE CT3 | Guadalupe | 2020-04-20 | 2000-04-21 | Gas | CC | 19 | 2020 | Yes
[6 empty] | 18INR0077 | Colorado Bend 2 repower | Wharton | 2020-07-01 | 2015-12-17 | Gas | CC | 45 | 2020 | No
[6 empty] | 19INR0014 | Formosa Increase | Calhoun | 2020-07-01 | 2019-04-30 | Gas | CC | 240 | 2020 | Yes
[6 empty] | 20INR0286 | Wise County Power Repower (CT1, CT2) | Wise | 2020-12-01 | 2001-03-19 | Gas | CC | 21 | 2020 | Yes
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned
1999 | 2867 | 2867 | 0 | 0 | 0
2000 | 7381 | 7381 | 0 | 0 | 0
2001 | 13967 | 13967 | 0 | 0 | 0
2002 | 18443 | 18443 | 0 | 0 | 0
2003 | 24141 | 24141 | 0 | 0 | 0
2004 | 25641 | 25641 | 0 | 0 | 0
2005 | 25539 | 25539 | 0 | 0 | 0
2006 | 26258 | 26258 | 0 | 0 | 0
2007 | 26815 | 26815 | 0 | 0 | 0
2008 | 27376 | 27376 | 0 | 0 | 0
2009 | 28309 | 28309 | 0 | 0 | 0
2010 | 29770 | 29770 | 0 | 0 | 0
2011 | 30488 | 30488 | 0 | 0 | 0
2012 | 30488 | 30488 | 0 | 0 | 0
2013 | 30538 | 30538 | 0 | 0 | 0
2014 | 33080 | 33080 | 0 | 0 | 0
2015 | 33897 | 33897 | 0 | 0 | 0
2016 | 33515 | 33515 | 0 | 0 | 0
2017 | 35465 | 35465 | 0 | 0 | 0
2018 | 35465 | 35465 | 0 | 0 | 0
2019 | 35564 | 35564 | 0 | 0 | 0
2020 | 35901 | 35564 | 292 | 45 | 0

## Gas-Other Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 16INR0076 | Hudson (Ineos/Brazoria) | Brazoria | 2020-03-31 | 2017-12-05 | Gas | GT | 96 | 2020 | Yes
[6 empty] | 17INR0022 | MIRAGE | Harris | 2020-05-04 | 2016-08-31 | Gas | GT | 11 | 2020 | Yes
[6 empty] | 20INR0206 | PES1 | Harris | 2020-12-01 | 2019-12-20 | Gas | GT | 484 | 2020 | Yes
[6 empty] | 19INR0180 | Friendswood II | Brazoria | 2021-02-21 | 2019-09-09 | Gas | GT | 117 | 2021 | No
[6 empty] | 19INR0056 | Chamon 2 | Harris | 2021-05-01 | 2019-09-20 | Gas | GT | 100 | 2021 | No
[6 empty] | 20INR0267 | Greens Bayou Expansion | Harris | 2021-06-01 | 2019-10-31 | Gas | GT | 140 | 2021 | No
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned
1999 | 33703 | 33703 | 0 | 0 | 0
2000 | 33703 | 33703 | 0 | 0 | 0
2001 | 34170 | 34170 | 0 | 0 | 0
2002 | 34170 | 34170 | 0 | 0 | 0
2003 | 34118 | 34118 | 0 | 0 | 0
2004 | 32616 | 32616 | 0 | 0 | 0
2005 | 31217 | 31217 | 0 | 0 | 0
2006 | 30774 | 30774 | 0 | 0 | 0
2007 | 29048 | 29048 | 0 | 0 | 0
2008 | 28681 | 28681 | 0 | 0 | 0
2009 | 23651 | 23651 | 0 | 0 | 0
2010 | 20937 | 20937 | 0 | 0 | 0
2011 | 20575 | 20575 | 0 | 0 | 0
2012 | 20551 | 20551 | 0 | 0 | 0
2013 | 20026 | 20026 | 0 | 0 | 0
2014 | 19917 | 19917 | 0 | 0 | 0
2015 | 18538 | 18538 | 0 | 0 | 0
2016 | 19564 | 19564 | 0 | 0 | 0
2017 | 18818 | 18818 | 0 | 0 | 0
2018 | 19562 | 19562 | 0 | 0 | 0
2019 | 19320.7 | 19320.7 | 0 | 0 | 0
2020 | 20032.7 | 19441.7 | 591 | 0 | 0
2021 | 20389.7 | 19441.7 | 591 | 357 | 0