## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
March 25, 2020

## Slide 2
Project Portfolio Update
  Recent / Upcoming Project Implementations
  2020 Release Targets
  Planned Project Starts
  2020 Project Spending Forecast
  Revision Request Funding Placeholder Status
    Cost Estimate Accuracy
    Duration Estimate Accuracy
    Legend
    Report Exceptions
  Priority/Rank Options for Revision Requests with Impacts
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Implementations
2020 March Release – Off-Cycle – 3/1/2020 Complete
  NPRR863 Phase 1 – Creation of ECRS and Revisions to Responsive Reserve
    FFR portion only
  NPRR960 – Phased Approach and Clarifications for NPRR863, Creation of ERCOT Contingency Reserve Service and Revisions to Responsive Reserve
  NOGRR187 – Related to NPRR863, Creation of ERCOT Contingency Reserve Service and Revisions to Responsive Reserve
  OBDRR011 – ORDC OBD Revisions for PUCT Project 48551
2020 April Release – R2 – 3/31/2020 – 4/2/2020 In Flight
  NPRR928 – Cybersecurity Incident Notification
  NPRR929 – PTP Obligations with Links to an Option DAM Award Eligibility
  NPRR978 – Alignment with Amendments to PUCT Substantive Rule 25.505
    Partial Implementation – Decommission the following reports:
      36 Month Resource Capacity Report
        EMIL ID: NP3-775-M, Report Type ID: 11481
      Projected Transmission Constraints for Medium Term PASA
        EMIL ID: NP3-776-M, Report Type ID: 13041
  NPRR988 – Correction to Conditions for DAM Award Eligibility for PTP Obligations w/Links to an Option
  SCR802 – Enhance Communications of System Inertia
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2020 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/4 – 2/6 | April 3/31 – 4/2 | May 5/26 – 5/28 | August 8/4 – 8/6 | October 10/13 – 10/15 | December 12/8 – 12/10
NPRR873 SCR797 NPRR877 Ph2 NPRR968 NPRR943 EMIL Web Interface NPRR863 Ph1 NPRR960 NOGRR187 OBDRR011 | SCR802 NPRR928 NPRR929 NPRR978(a) NPRR988 | NPRR856 NPRR884 NPRR935(a) OBDRR006 SCR803 NPRR887 NPRR907 NPRR985 | NPRR902 NPRR905 NPRR951 MIS testing SCR804 SCR781(a) RRGRR016 RRGRR019 | NPRR936 MIS Go-Live MMS/OS Refresh | SCR799 NPRR857 NPRR863 Ph2 NPRR885 NPRR917 NPRR941 NPRR971 NPRR986 PGRR070(b) SCR781(b)
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
3/1
NPRR863 Ph1 – FFR
NPRR863 Ph2 – ECRS
NPRR935(a) – All changes except Section 4.2.3
NPRR935(b) – Section 4.2.3 changes
NPRR978(a) – Initial report decommissions
PGRR070(b) – Remaining PGRR language
SCR781(a) – View / Edit capability
SCR781(b) – Add capability
MMS/OS Upgrade “Chill”
MMS/OS Upgrade “Freeze”
E
E
E
NS
E
ü
ü
ü
E
E
P
P
P
E
E
E
November
Off-Cycle
1/1
Future Year Go-Live Targets
2021
2022
NS
NS
I
P
NS
NS
I
I
E
E
September
Off-Cycle
I
I
I
P
1/19
E
ü
ü
TBD Items | 2017 | 2018 | 2019
 | NPRR702, NPRR829 | NPRR825(b), NPRR867, NPRR841 | NPRR904, OBDRR009, NPRR879, NPRR918, NRR935(b), NPRR939, PGRR066, SCR800
ü
CMM Release 2a
1/30
August
October
Q3 RIOO
RARF Go-Live for View/Update
ü
ü
ü
ü

## Slide 5: Approved Revision Requests “Not Started” – Planned to Start in Future Months
Revision Request | Target Start Date | Release Target | Cost Estimate | Author
NPRR936 – CRR Account Holder Limits | TBD | TBD | $150k-$250k | Engie
NPRR977 – Create MIS Posting for RUC Cancellations | TBD | TBD | $30k-$40k | ERCOT
SCR799 – ERCOT Outage Study Cases in the System Operations Test Env. (SOTE) | May 2020 | 2020-R6 | $150k-$250k | Oncor
NPRR904 – Revisions to Real-Time On-Line Reliability Deployment Price Adder for ERCOT-Directed Actions Related to DC Ties and to Correct Design Flaws | TBD | TBD | $200k-$300k | Rainbow
OBDRR009 – ORDC OBD Revisions for ERCOT-Directed Actions Related to DC Ties | TBD | TBD | $30k-$50k | Rainbow
SCR800 – Addition of DC Tie Ramp to GTBD Calculation | TBD | TBD | $30k-$50k | ERCOT
SCR806 – Adding QSE and DME Information to Disclosure Reports | TBD | TBD | $65k-$95k | ERCOT
NPRR978 – Alignment with Amendments to PUCT Substantive Rule 25.505 | TBD | TBD | $65k-$95k | ERCOT
Project Initiations – Next 3 Months
Note: Target Start Dates are subject to change.
Based on recent developments, ERCOT is evaluating project capacity.

## Slide 6: 2020 Project Spending
2020 PPL Budget = $29.0M
“Potential Demand” represents internal ERCOT projects that have not been fully approved
May actuals not yet available
June-December forecasts are updated

## Slide 7: Revision Request Funding Placeholder Status
In ERCOT’s 2020/2021 proposed budget, the following amounts are allocated for Revision Request work
  2020 = $4M
  2021 = $4M
Yearly Revision Request Spending Forecast Summary
Project Status | 2020 | 2021
YTD Actuals | $0.51M | -
Approved – In-Flight / Complete | $2.85M | $1.28M
Approved – Not Started | $0.63M | $0.64M
Remaining Funding | $0.52M | $2.08M
Total Allocation | $4.00M | $4.00M
As of 2/29/2020

## Slide 8
2019 PERFORMANCE STATISTICS

## Slide 9: Variance from IA Cost Range – Revision Request Projects
10
Exceeds IA Range
12 Projects
Below IA Range
20 Projects
Within IA Range
17 Projects
If actual spend falls within the IA range the variance is 0
Actual $ Variance from IA Range
2017
17 Projects
22 Revision Requests
2018
13 Projects
14 Revision Requests
2019
19 Projects
29 Revision Requests
Note: Graph compares the posted IA cost range with the actual project spend
1
2
3
4
5
6
7
8
9
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
35
36
37
38
39
31
32
33
30
34
40
41
42
43
Chart: 
| -$35,000 | -$36,213 | -$21,105 | -$11,001 | $1,120 | -$5,333 | $6,569 | -$5,911 | -$3,242 | $11,991 | $0 | $0 | -$61,130 | $59,424 | $24,677 | $0 | $108,135 | -$18,649 | -$109,501 | -$24,103 | -$2,635 | -$6,979 | $0 | $0 | $27,046 | $0 | $18,276 | $23,113 | -$3,385 | $0 | -$17,092 | $0 | $0 | $0 | -$3,392 | -$2,703 | -$7,490 | $0 | $0 | -$4,343 | -$4,770 | $0 | $0 | $0 | $6,585 | $39,855 | $0 | $0 | $257,360 | No | No | No | No | No | No | No | No | No | No | Yes | Yes | No | No | No | Yes | No | No | No | No | No | No | Yes | Yes | No | Yes | No | No | No | Yes | No | Yes | Yes | Yes | No | No | No | Yes | Yes | No | No | Yes | Yes | Yes | No | No | Yes | Yes | No | $- | $3,787 | $38,895 | $38,999 | $41,120 | $44,667 | $46,569 | $49,089 | $56,758 | $56,991 | $81,915 | $111,390 | $113,870 | $179,424 | $184,677 | $213,921 | $508,135 | $6,351 | $10,499 | $15,897 | $17,365 | $18,021 | $19,780 | $29,623 | $67,046 | $83,360 | $108,276 | $123,113 | $146,615 | $189,937 | $7,908 | $18,383 | $18,684 | $20,161 | $21,608 | $22,297 | $22,510 | $23,433 | $25,134 | $25,657 | $30,230 | $45,476 | $45,767 | $77,821 | $86,585 | $189,855 | $212,674 | $262,939 | $742,360 | No | Yes | No | No | No | Yes | No | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 3 - $100k to $250k | 3 - $100k to $250k | 3 - $100k to $250k | 3 - $100k to $250k | 3 - $100k to $250k | 4 - $250k to $500k | 1 - Less than $50k | 3 - $100k to $250k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 2 - $50k to $100k | 2 - $50k to $100k | 2 - $50k to $100k | 3 - $100k to $250k | 3 - $100k to $250k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 2 - $50k to $100k | 1 - Less than $50k | 1 - Less than $50k | 2 - $50k to $100k | 2 - $50k to $100k | 3 - $100k to $250k | 3 - $100k to $250k | 4 - $250k to $500k | 4 - $250k to $500k | $5,000 | $10,000 | $20,000 | $25,000 | $20,000 | $25,000 | $10,000 | $20,000 | $30,000 | $10,000 | $30,000 | $50,000 | $60,000 | $20,000 | $15,000 | $50,000 | $100,000 | $15,000 | $40,000 | $20,000 | $10,000 | $10,000 | $10,000 | $25,000 | $10,000 | $20,000 | $20,000 | $30,000 | $50,000 | $60,000 | $10,000 | $10,000 | $10,000 | $10,000 | $20,000 | $20,000 | $10,000 | $20,000 | $10,000 | $20,000 | $20,000 | $20,000 | $10,000 | $20,000 | $20,000 | $10,000 | $65,000 | $80,000 | $120,000 | $40,000 | $50,000 | $80,000 | $75,000 | $40,000 | $75,000 | $40,000 | $75,000 | $90,000 | $45,000 | $85,000 | $150,000 | $235,000 | $120,000 | $160,000 | $250,000 | $400,000 | $40,000 | $160,000 | $60,000 | $30,000 | $35,000 | $25,000 | $50,000 | $40,000 | $90,000 | $90,000 | $100,000 | $200,000 | $190,000 | $35,000 | $20,000 | $25,000 | $25,000 | $45,000 | $45,000 | $40,000 | $40,000 | $30,000 | $50,000 | $55,000 | $50,000 | $50,000 | $80,000 | $80,000 | $150,000 | $215,000 | $290,000 | $485,000 | $37,500 | $45,000 | $70,000 | $62,500 | $30,000 | $62,500 | $35,000 | $65,000 | $75,000 | $40,000 | $70,000 | $125,000 | $205,000 | $110,000 | $152,500 | $225,000 | $350,000 | $32,500 | $140,000 | $50,000 | $25,000 | $30,000 | $20,000 | $37,500 | $35,000 | $80,000 | $80,000 | $85,000 | $175,000 | $160,000 | $30,000 | $15,000 | $20,000 | $20,000 | $35,000 | $35,000 | $35,000 | $30,000 | $25,000 | $40,000 | $45,000 | $40,000 | $45,000 | $70,000 | $70,000 | $145,000 | $182,500 | $250,000 | $425,000 | $35,000 | $40,000 | $60,000 | $50,000 | $20,000 | $50,000 | $30,000 | $55,000 | $60,000 | $35,000 | $55,000 | $100,000 | $175,000 | $100,000 | $145,000 | $200,000 | $300,000 | $25,000 | $120,000 | $40,000 | $20,000 | $25,000 | $15,000 | $25,000 | $30,000 | $70,000 | $70,000 | $70,000 | $150,000 | $130,000 | $25,000 | $10,000 | $15,000 | $15,000 | $25,000 | $25,000 | $30,000 | $20,000 | $20,000 | $30,000 | $35,000 | $30,000 | $40,000 | $60,000 | $60,000 | $140,000 | $150,000 | $210,000 | $365,000 | ERCOT | Market | Market | ERCOT | Market | Market | ERCOT | ERCOT | ERCOT | ERCOT | ERCOT | ERCOT | Mixed | Market | ERCOT | ERCOT | ERCOT | ERCOT | ERCOT | ERCOT | Market | Market | Market | ERCOT | ERCOT | Market | ERCOT | ERCOT | Market | ERCOT | ERCOT | ERCOT | ERCOT | ERCOT | Market | Market | Market | ERCOT | ERCOT | Market | ERCOT | Market | Market | ERCOT | ERCOT | Market | Mixed | ERCOT | Mixed | NPRR785 | NPRR808 | NPRR789, NPRR797 | NPRR649 | SCR790 | NPRR778 | RMGRR134 | NPRR764 | NPRR782 | NPRR746 | NPRR573, NPRR801 | NPRR831 | RRGRR003, RRGRR006, RRGRR007, RRGRR009 | RMGRR140 | NPRR272 | NPRR744 | NPRR758 | NPRR810 | NPRR830 | SCR792 | NPRR854 | SCR791 | NPRR844 | NPRR819 | SCR795 | NPRR815 | NPRR843 | NPRR776 | NPRR864 | OBDRR002, NPRR768 | SCR794 | NPRR925, SCR798 | NPRR899 | NPRR914 | NPRR877 | NPRR858 | NPRR865, NPRR880 | NPRR866, RRGRR017 | VCMRR022 | NOGRR174 | SCR796, OBDRR003, OBDRR014 | NPRR821 | SCR793 | NPRR842 | NPRR845 | NPRR809 | NPRR817, NPRR847, VCMRR021 | NPRR901, NPRR910, OBDRR010 | NPRR833, NPRR749 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | No | No | No | No | No | No | No | Yes | No | Yes | Yes | No | No | No | No | No | No | Yes | No | Yes | No | No | No | No | No | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | Yes | Yes | Synchronizing WGR and PVGR COPs with the Short Term Wind and PhotoVoltaic Forecasts | Three Year CRR Auction | NPRR797 & NPRR789 Load Forecast Enhancements | Addressing Issues Surrounding High Dispatch Limit (HDL) Overrides | Wind Resource Power Production and Forecast Transparency | Modifications to Date Change and Cancellation Evaluation Window | Allow AMS Data Submittal Process for TDSP-Read Non-Modeled Generators | QSE Capacity Short Calculations Based on an 80% Probability of Exceedance (P80) | Settlement of Infeasible Ancillary Services Due to Transmission Constraints | Adjustments Due to Negative Load | Implementation of NPRR573 & NPRR801 | Inclusion of Private Use Networks in Load Zone Price Calculations | 2016 RARF Enhancements | Mass Transition/Acquisition Enhancements (MTAQ) | Definition and Participation of Quick Start Generation Resources | RUC Trigger for the Reliability Deployment Price Adder and Alignment with RUC Settlement | Improved Transparency for Outages Potentially Having a High Economic Impact | Applicability of RMR Incentive Factor on Reservation and Transportation Costs Associated with Firm Fuel Supplies | Revision of 4-Coincident Peak Methodology | Enhance Communications of BAAL Exceedances | NOIE TDSP Submittal of Meters with Bidirectional Flow Caused by Generation Interconnected at Distribution Voltage | Correction of 60-day SCED GRD Disclosure Report | Clarification to Outage Report | Modification of Non-Price Error Resettlement Thresholds and Resettlement Clean-Ups | Addition of Intra-Hour Wind Forecast to GTBD Calculation | Revise the Limitation of Load Resources Providing Responsive Reserve (RRS) Service | Short-Term System Adequacy and AS Offer Disclosure Reports Additions | Voltage Set Point Communication | RUC Modifications to Consider Market-Based Solutions | Revisions to Real-Time On-Line Reliability Deployment Price Adder Categories | Update SCED Limit Calculation | PTP Obligation Bid ID Limit | Digital Certificate and User Security Administrator Clarifications and Opt Out Procedure | Addition of Controllable Load Resources to 60-Day Reports | Use of Actual Interval Data for IDR ESI IDs for Initial Settlement - Phase 2 | Provide Complete Current Operating Plan (COP) Data | Publish RTM Shift Factors for Hubs, Load Zones, and DC Ties | RRGRR Related to NPRR866, Mapping Registered Distributed Generation and Load Resources to Transmission Loads in the Network Operations Model | Determination of Fuel Adder Price for Coal and Lignite Resources | AVR and PSS Testing Requirements | Change Validation Rules to Preclude Certain Transactions at Resource Nodes within Private Use Networks | Elimination of the CRR Deration Process | SSR Related Telemetry for Transmission Service Provider (TSP) Operators | Study Area Load Information | RMR Process and Agreement Revisions | GTC or GTL for New Generation Interconnection | Create a Panhandle Hub | Switchable Generation Resource Status Code | Modify PTP Obligation Bid Clearing Change | 231-01 | 252-01 | 236-01 | 213-01 | 207-01 | 248-01 | 232-01 | 201-01 | 237-01 | 226-01 | 159-01 | 251-01 | 200-01 | 188-01 | 194-01 | 225-01 | 215-01 | 233-31 | 270-01 | 273-01 | 276-02 | 281-01 | 276-01 | 283-01 | 289-01 | 278-01 | 285-01 | 256-01 | 284-01 | 277-01 | 276-03 | 302-04 | 302-02 | 302-07 | 302-08 | 276-07 | 300-01 | 276-09 | 276-06 | 276-08 | 304-01 | 299-01 | 302-01 | 290-01 | 298-01 | 233-28 | 294-01 | 303-01 | 264-01 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019
Actual Variance from IA Estimate Range | -35000 | -36213 | -21105 | -11000.8 | 1119.97 | -5333 | 6568.52 | -5911.38 | -3242 | 11991.1 | 0 | 0 | -61130.26 | 59424.36 | 24677.15 | 0 | 108135 | -18649 | -109500.9 | -24102.73 | -2634.93 | -6979.45 | 0 | 0 | 27046.01 | 0 | 18276 | 23113.12 | -3385.08 | 0 | -17092 | 0 | 0 | 0 | -3392 | -2703 | -7490 | 0 | 0 | -4343 | -4770 | 0 | 0 | 0 | 6585 | 39855 | 0 | 0 | 257360




## Slide 10: Variance from IA Duration Range – Revision Request Projects
34
12
Exceeds IA Range
23 Projects
Below IA Range
1 Projects
Within IA Range
25 Projects
2017
17 Projects
22 Revision Requests
2018
13 Projects
14 Revision Requests
2019
19 Projects
29 Revision Requests
If actual duration falls within the IA range the variance is 0.
Note: Graph compares the posted IA duration range with the actual project duration
Number of Months from IA Range
1
2
3
4
5
6
8
9
10
11
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
35
36
37
38
7
39
41
40
42
43
44
46
47
45
Chart: 
| 1 | 2 | 4 | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 25 | 26 | 28 | 37 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 55 | 59 | 60 | 61 | 62 | 64 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 89 | 90 | 91 | 92 | 94 | 95 | 97 | 98 | 100 | 105 | -$35,000 | -$36,213 | -$21,105 | -$11,001 | $1,120 | -$5,333 | $6,569 | -$5,911 | -$3,242 | $11,991 | $0 | $0 | -$61,130 | $59,424 | $24,677 | $0 | $108,135 | -$18,649 | -$109,501 | -$24,103 | -$2,635 | -$6,979 | $0 | $0 | $27,046 | $0 | $18,276 | $23,113 | -$3,385 | $0 | -$17,092 | $0 | $0 | $0 | -$3,392 | -$2,703 | -$7,490 | $0 | $0 | -$4,343 | -$4,770 | $0 | $0 | $0 | $6,585 | $39,855 | $0 | $0 | $257,360 | No | No | No | No | No | No | No | No | No | No | Yes | Yes | No | No | No | Yes | No | No | No | No | No | No | Yes | Yes | No | Yes | No | No | No | Yes | No | Yes | Yes | Yes | No | No | No | Yes | Yes | No | No | Yes | Yes | Yes | No | No | Yes | Yes | No | $- | $3,787 | $38,895 | $38,999 | $41,120 | $44,667 | $46,569 | $49,089 | $56,758 | $56,991 | $81,915 | $111,390 | $113,870 | $179,424 | $184,677 | $213,921 | $508,135 | $6,351 | $10,499 | $15,897 | $17,365 | $18,021 | $19,780 | $29,623 | $67,046 | $83,360 | $108,276 | $123,113 | $146,615 | $189,937 | $7,908 | $18,383 | $18,684 | $20,161 | $21,608 | $22,297 | $22,510 | $23,433 | $25,134 | $25,657 | $30,230 | $45,476 | $45,767 | $77,821 | $86,585 | $189,855 | $212,674 | $262,939 | $742,360 | No | Yes | No | No | No | Yes | No | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 3 - $100k to $250k | 3 - $100k to $250k | 3 - $100k to $250k | 3 - $100k to $250k | 3 - $100k to $250k | 4 - $250k to $500k | 1 - Less than $50k | 3 - $100k to $250k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 2 - $50k to $100k | 2 - $50k to $100k | 2 - $50k to $100k | 3 - $100k to $250k | 3 - $100k to $250k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 2 - $50k to $100k | 1 - Less than $50k | 1 - Less than $50k | 2 - $50k to $100k | 2 - $50k to $100k | 3 - $100k to $250k | 3 - $100k to $250k | 4 - $250k to $500k | 4 - $250k to $500k | $5,000 | $10,000 | $20,000 | $25,000 | $20,000 | $25,000 | $10,000 | $20,000 | $30,000 | $10,000 | $30,000 | $50,000 | $60,000 | $20,000 | $15,000 | $50,000 | $100,000 | $15,000 | $40,000 | $20,000 | $10,000 | $10,000 | $10,000 | $25,000 | $10,000 | $20,000 | $20,000 | $30,000 | $50,000 | $60,000 | $10,000 | $10,000 | $10,000 | $10,000 | $20,000 | $20,000 | $10,000 | $20,000 | $10,000 | $20,000 | $20,000 | $20,000 | $10,000 | $20,000 | $20,000 | $10,000 | $65,000 | $80,000 | $120,000 | $40,000 | $50,000 | $80,000 | $75,000 | $40,000 | $75,000 | $40,000 | $75,000 | $90,000 | $45,000 | $85,000 | $150,000 | $235,000 | $120,000 | $160,000 | $250,000 | $400,000 | $40,000 | $160,000 | $60,000 | $30,000 | $35,000 | $25,000 | $50,000 | $40,000 | $90,000 | $90,000 | $100,000 | $200,000 | $190,000 | $35,000 | $20,000 | $25,000 | $25,000 | $45,000 | $45,000 | $40,000 | $40,000 | $30,000 | $50,000 | $55,000 | $50,000 | $50,000 | $80,000 | $80,000 | $150,000 | $215,000 | $290,000 | $485,000 | $37,500 | $45,000 | $70,000 | $62,500 | $30,000 | $62,500 | $35,000 | $65,000 | $75,000 | $40,000 | $70,000 | $125,000 | $205,000 | $110,000 | $152,500 | $225,000 | $350,000 | $32,500 | $140,000 | $50,000 | $25,000 | $30,000 | $20,000 | $37,500 | $35,000 | $80,000 | $80,000 | $85,000 | $175,000 | $160,000 | $30,000 | $15,000 | $20,000 | $20,000 | $35,000 | $35,000 | $35,000 | $30,000 | $25,000 | $40,000 | $45,000 | $40,000 | $45,000 | $70,000 | $70,000 | $145,000 | $182,500 | $250,000 | $425,000 | $35,000 | $40,000 | $60,000 | $50,000 | $20,000 | $50,000 | $30,000 | $55,000 | $60,000 | $35,000 | $55,000 | $100,000 | $175,000 | $100,000 | $145,000 | $200,000 | $300,000 | $25,000 | $120,000 | $40,000 | $20,000 | $25,000 | $15,000 | $25,000 | $30,000 | $70,000 | $70,000 | $70,000 | $150,000 | $130,000 | $25,000 | $10,000 | $15,000 | $15,000 | $25,000 | $25,000 | $30,000 | $20,000 | $20,000 | $30,000 | $35,000 | $30,000 | $40,000 | $60,000 | $60,000 | $140,000 | $150,000 | $210,000 | $365,000 | ERCOT | Market | Market | ERCOT | Market | Market | ERCOT | ERCOT | ERCOT | ERCOT | ERCOT | ERCOT | Mixed | Market | ERCOT | ERCOT | ERCOT | ERCOT | ERCOT | ERCOT | Market | Market | Market | ERCOT | ERCOT | Market | ERCOT | ERCOT | Market | ERCOT | ERCOT | ERCOT | ERCOT | ERCOT | Market | Market | Market | ERCOT | ERCOT | Market | ERCOT | Market | Market | ERCOT | ERCOT | Market | Mixed | ERCOT | Mixed | NPRR785 | NPRR808 | NPRR789, NPRR797 | NPRR649 | SCR790 | NPRR778 | RMGRR134 | NPRR764 | NPRR782 | NPRR746 | NPRR573, NPRR801 | NPRR831 | RRGRR003, RRGRR006, RRGRR007, RRGRR009 | RMGRR140 | NPRR272 | NPRR744 | NPRR758 | NPRR810 | NPRR830 | SCR792 | NPRR854 | SCR791 | NPRR844 | NPRR819 | SCR795 | NPRR815 | NPRR843 | NPRR776 | NPRR864 | OBDRR002, NPRR768 | SCR794 | NPRR925, SCR798 | NPRR899 | NPRR914 | NPRR877 | NPRR858 | NPRR865, NPRR880 | NPRR866, RRGRR017 | VCMRR022 | NOGRR174 | SCR796, OBDRR003, OBDRR014 | NPRR821 | SCR793 | NPRR842 | NPRR845 | NPRR809 | NPRR817, NPRR847, VCMRR021 | NPRR901, NPRR910, OBDRR010 | NPRR833, NPRR749 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | No | No | No | No | No | No | No | Yes | No | Yes | Yes | No | No | No | No | No | No | Yes | No | Yes | No | No | No | No | No | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | Yes | Yes | Synchronizing WGR and PVGR COPs with the Short Term Wind and PhotoVoltaic Forecasts | Three Year CRR Auction | NPRR797 & NPRR789 Load Forecast Enhancements | Addressing Issues Surrounding High Dispatch Limit (HDL) Overrides | Wind Resource Power Production and Forecast Transparency | Modifications to Date Change and Cancellation Evaluation Window | Allow AMS Data Submittal Process for TDSP-Read Non-Modeled Generators | QSE Capacity Short Calculations Based on an 80% Probability of Exceedance (P80) | Settlement of Infeasible Ancillary Services Due to Transmission Constraints | Adjustments Due to Negative Load | Implementation of NPRR573 & NPRR801 | Inclusion of Private Use Networks in Load Zone Price Calculations | 2016 RARF Enhancements | Mass Transition/Acquisition Enhancements (MTAQ) | Definition and Participation of Quick Start Generation Resources | RUC Trigger for the Reliability Deployment Price Adder and Alignment with RUC Settlement | Improved Transparency for Outages Potentially Having a High Economic Impact | Applicability of RMR Incentive Factor on Reservation and Transportation Costs Associated with Firm Fuel Supplies | Revision of 4-Coincident Peak Methodology | Enhance Communications of BAAL Exceedances | NOIE TDSP Submittal of Meters with Bidirectional Flow Caused by Generation Interconnected at Distribution Voltage | Correction of 60-day SCED GRD Disclosure Report | Clarification to Outage Report | Modification of Non-Price Error Resettlement Thresholds and Resettlement Clean-Ups | Addition of Intra-Hour Wind Forecast to GTBD Calculation | Revise the Limitation of Load Resources Providing Responsive Reserve (RRS) Service | Short-Term System Adequacy and AS Offer Disclosure Reports Additions | Voltage Set Point Communication | RUC Modifications to Consider Market-Based Solutions | Revisions to Real-Time On-Line Reliability Deployment Price Adder Categories | Update SCED Limit Calculation | PTP Obligation Bid ID Limit | Digital Certificate and User Security Administrator Clarifications and Opt Out Procedure | Addition of Controllable Load Resources to 60-Day Reports | Use of Actual Interval Data for IDR ESI IDs for Initial Settlement - Phase 2 | Provide Complete Current Operating Plan (COP) Data | Publish RTM Shift Factors for Hubs, Load Zones, and DC Ties | RRGRR Related to NPRR866, Mapping Registered Distributed Generation and Load Resources to Transmission Loads in the Network Operations Model | Determination of Fuel Adder Price for Coal and Lignite Resources | AVR and PSS Testing Requirements | Change Validation Rules to Preclude Certain Transactions at Resource Nodes within Private Use Networks | Elimination of the CRR Deration Process | SSR Related Telemetry for Transmission Service Provider (TSP) Operators | Study Area Load Information | RMR Process and Agreement Revisions | GTC or GTL for New Generation Interconnection | Create a Panhandle Hub | Switchable Generation Resource Status Code | Modify PTP Obligation Bid Clearing Change | 231-01 | 252-01 | 236-01 | 213-01 | 207-01 | 248-01 | 232-01 | 201-01 | 237-01 | 226-01 | 159-01 | 251-01 | 200-01 | 188-01 | 194-01 | 225-01 | 215-01 | 233-31 | 270-01 | 273-01 | 276-02 | 281-01 | 276-01 | 283-01 | 289-01 | 278-01 | 285-01 | 256-01 | 284-01 | 277-01 | 276-03 | 302-04 | 302-02 | 302-07 | 302-08 | 276-07 | 300-01 | 276-09 | 276-06 | 276-08 | 304-01 | 299-01 | 302-01 | 290-01 | 298-01 | 233-28 | 294-01 | 303-01 | 264-01 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019
Actual Variance from IA Duration Range | 0 | 1.4333 | 0 | 0 | 2.4333 | 0 | 0 | 0.8 | 3.3667 | 0.46667 | 0 | 0 | 0.2 | 4.8 | 5 | 0 | 0 | 1.1667 | -0.066667 | 0 | 0.76667 | 0.63333 | 0.066667 | 0 | 0 | 0 | 1.5 | 0.9 | 0 | 0 | 0.93333 | 0 | 1.4667 | 0 | 0 | 0 | 0 | 0.033333 | 0 | 1.0667 | 1.6 | 0.4 | 1.1667 | 0.7 | 0 | 3.0667 | 0 | 0 | 6.4667

## Slide 11: Statistics Report Exceptions- 2018
Type | Revision Requests | Reason for Exclusion from Report
CMM Phase 1a | NPRR863, NPRR743, NPRR760, NPRR800 | Difficult to apply metrics – multiple RRs in a multi-phase project
O&M Revision Requests | NPRR659, NPRR846, NPRR562(b), NPRR875, PGRR063, NOGRR167, PGRR042 | O&M Revision Requests do not have IA estimates
Project Not Complete | PGRR057(a), RRGRR015 | Early releases of projects that are still in flight
Partial Scope Delivered | NPRR825(a), NPRR702 | Partial scope delivered – Remaining scope to be delivered in future projects
Combined with System Upgrade | SCR777, NPRR831(b) | Small additions to CRR Framework Upgrade project
The following Revision Requests aren’t included in the IA Statistics Report

## Slide 12: Statistics Report Exceptions- 2019
Type | Revision Requests | Reason for Exclusion from Report
2015 CMM NPRRs | NPRR648, NPRR660, NPRR519, NPRR620, NPRR683, NPRR741, NPRR760, NPRR755, NPRR743, NPRR800, NOGRR154 | Difficult to apply metrics – multiple RRs in a multi-phase project
O&M Revision Requests | NPRR878, OBDRR011, RMGRR156, NPRR916, NPRR912, NPRR909, NPRR923, NPRR889, RMGRR155, RRGRR018 | O&M Revision Requests do not have IA estimates
Project Not Complete | PGRR057(b), PGRR066, NPRR895, OBDRR007, PGRR070(a), NPRR911, NPRR952, NPRR920 | Early releases of projects that are still in flight
No Project Required | PGRR062, NPRR972, PGRR072, NPRR921, NOGRR185, PGRR069 | Project not required to implement Revision Request
Project to Deliver NPRR866 | PGRR061 | This PGRR updated the Annual Load Data Request (ALDR) process so it was timed to coincide with the next occurrence of the ALDR.
The following Revision Requests aren’t included in the IA Statistics Report

## Slide 13: Revision Request Project Legend
NPRR785, Synchronizing WGR and PVGR COPs with the Short Term Wind and PhotoVoltaic Forecasts, (E)
NPRR808, Three Year CRR Auction, (M)
NPRR789, NPRR797 Load Forecast Enhancements, (M)
NPRR649, Addressing Issues Surrounding High Dispatch Limit (HDL) Overrides, (E)
SCR790, Wind Resource Power Production and Forecast Transparency, (M)
NPRR778, Modifications to Date Change and Cancellation Evaluation Window, (M)
RMGRR134, Allow AMS Data Submittal Process for TDSP – Read Non-Modeled Generators, (E)
NPRR764, QSE Capacity Short Calculations Based on an 80% Probability of Exceedance (P80), (E)
NPRR782, Settlement of Infeasible Ancillary Services Due to Transmission Constraints, (E)
NPRR746, Adjustments Due to Negative Load, (E)
NPRR573, NPRR801, Implementation of NPRR573 & NPRR801, (E)
NPRR831, Inclusion of Private Use Networks in Load Zone Price Calculations, (E)
RRGRR003, RRGRR006, RRGRR007, RRGRR009, 2016 RARF Enhancements, (V)
RMGRR140, Mass Transition/Acquisition Enhancements (MTAQ), (M)
NPRR272, Definition and Participation of Quick Start Generation Resources, (E)
NPRR744, RUC Trigger for the Reliability Deployment Price Adder and Alignment with RUC Settlement, (E)
NPRR758, Improved Transparency for Outages Potentially having a High Economic Impact, (E)
NPRR810, Applicability of RMR Incentive Factor on Reservation and Transportation Costs Associated with Firm Fuel Supplies, (E)
NPRR830, Revision of 4-Coincident Peak Methodology, (E)
SCR792, Enhance Communications of BAAL Exceedances, (E)
NPRR854, NOIE TDSP Submittal of Meters with Bidirectional Flow Caused by Generation Interconnected at Distribution Voltage, (M)
SCR791, Correction of 60-day SCED GRD Disclosure Report, (M)
NPRR844, Clarification to Outage Report, (M)
NPRR819, Modification of Non-Price Error Resettlement Thresholds and Resettlement Clean-Ups, (E)
SCR795, Addition of Intra-Hour Wind Forecast to GTBD Calculation, (E)
NPRR815, Revise the Limitation of Load Resources Providing Responsive Reserve (RRS) Service, (M)
NPRR843, Short-Term System Adequacy and AS Offer Disclosure Reports Additions, (E)
NPRR776, Voltage Set Point Communication, (E)
NPRR864, RUC Modifications to Consider Market-Based Solutions, (M)
OBDRR002, NPRR768, Revisions to Real-Time On-Line Reliability Deployment Price Adder Categories, (E)
SCR794, Update SCED Limit Calculation, (E)
NPRR925, SCR798, PTP Obligation Bid ID Limit, (E)
NPRR899, Digital Certificate and User Security Administrator Clarifications and Opt Out Procedure, (E)
NPRR914, Addition of Controllable Load Resources to 60-Day Reports, (E)
NPRR877, Use of Actual Interval Data for IDR ESI IDs for Initial Settlement - Phase 2, (M)
NPRR858, Provide Complete Current Operating Plan (COP) Data, (M)
NPRR865, NPRR880, Publish RTM Shift Factors for Hubs, Load Zones, and DC Ties, (M)
NPRR866, RRGRR017, RRGRR Related to NPRR866, Mapping Registered Distributed Generation and Load Resources to Transmission Loads in the Network Operations Model, (E)
VCMRR022, Determination of Fuel Adder Price for Coal and Lignite Resources, (E)
NOGRR174, AVR and PSS Testing Requirements, (M)
SCR796, OBDRR003, OBDRR014, Change Validation Rules to Preclude Certain Transactions at Resource Nodes within Private Use Networks, (E)
NPRR821, Elimination of the CRR Deration Process, (M)
SCR793, SSR Related Telemetry for Transmission Service Provider (TSP) Operators, (M)
NPRR842, Study Area Load Information, (E)
NPRR845, RMR Process and Agreement Revisions, (E)
NPRR809, GTC or GTL for New Generation Interconnection, (M)
NPRR817, NPRR847, VCMRR021, Create a Panhandle Hub, (V)
NPRR901, NPRR910, OBDRR010, Switchable Generation Resource Status Code, (E)
NPRR833, NPRR749, Modify PTP Obligation Bid Clearing Change, (V)
(E) ERCOT Sponsored
(M) Market Sponsored
(V) Various

## Slide 14: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR998 | ERS Deployment & Recall Messages | 2020 | 2990 | Add to end of 2020 list and work into plan without disrupting in-flight projects
Options for…
PPL Rank Information
Next available 2020 Rank in Business Strategy = 2990
Next available Rank in Regulatory = 260
Note
Items in the Regulatory section of the PPL are not tracked against the market Revision Request funding allocation