## Principle Concept Development
RTCTF Meetings in 2019/2020
Key Principle | Decision Points and Issues for Developing Principle Concepts | Date Topic was First Presented to the RTC Task Force | Related Principle Concepts under Dicussion (Y, with Principle Concept Number(s), or N)? | Related Principle Concepts Approved by TAC (Y,with Date and Principle Concept Number(s), or N)? | Estimated Date for First/Next Discussion | Estimated Final Meeting for Moving to TAC for Vote | 2019-05-13 | 2019-06-07 | 2019-06-21 | 2019-07-12 | 2019-08-09 | 2019-08-27 | 2019-09-19 | 2019-10-09 | 2019-10-30 | 2019-11-19 | 2019-12-03 | 2019-12-19 | 1/10/2020 (Cancelled) | 2020-01-22
Key Principle 1.1 – Ancillary Service Demand Curves and Current Market Price Adders | Determining the shape and price points for the demand curves for each of the AS products, not including Regulation Down | 2019-08-09 | Y (4, 5) | Y (4 - 9/25/19, 5 - 10/23/19) | n/a | n/a | bar: 2019-08-09 to 2019-09-19
| Periodic review of RTC pricing outcomes relative to ORDC | 2019-12-03 | Y(8) | Y (8 - 1/29/20) | n/a | n/a | bar: 2019-12-03 to 2019-12-19
| Determining the shape and price points for the Regulation Down demand curve | 2019-10-30 | Y(7) | Y (7 - 1/29/20) | n/a | n/a | bar: 2019-10-30 to 2019-12-03
| Elimination of the ORDC price adders | 2019-08-09 | Y (1) | Y (1 - 9/25/19) | n/a | n/a | bar: 2019-08-09 to 2019-08-27
| Continuation of the Reliability Deployment Price Adder process | 2019-08-09 | Y (2, 3, 6) | Y (3- 9/25/19, 2 and 6 - 1/29/20) | n/a | n/a | bar: 2019-08-09; 2019-10-09 to 2019-12-03
Key Principle 1.2 – System-Wide Offer Cap and Power Balance Penalty Curve | New value for SWOC | 2019-08-09 | Y (1, 2) | Y (1, 2 - 9/25/19) | n/a | n/a | bar: 2019-08-09 to 2019-08-27
| Need for separate SWOC in DAM | 2019-08-27 | Y (3) | Y (3 - 1/29/20) | n/a | n/a | bar: 2019-08-27; 2019-10-30 to 2019-11-19
| New value and shape for the PBPC | 2019-08-09 | Y (1, 2) | Y (1, 2 - 9/25/19) | n/a | n/a | bar: 2019-08-09 to 2019-08-27
| Capping of energy prices | 2019-08-09 | Y (1, 2) | Y (1, 2 - 9/25/19) | n/a | n/a | bar: 2019-08-09 to 2019-08-27
| Effect of energy price capping on AS prices | 2019-08-09 | Y (3) - Later deleted | N | Following dicussion, RTCTF came to consensus that adjustments would not be made to AS prices when energy prices are capped. | n/a | bar: 2019-08-09 to 2019-10-09
Key Principle 1.3 - Offering and Awarding of Ancillary Services in Real-Time | Constraint formulation for RTC (e.g., Resource constraints, rules for RRS, ramp sharing, NFRC etc.) | 2019-06-21 | Y (3, 4, 5, 6, 7, 8) | Y (3, 4, 5, 6, 7, 8(a and b) - 10/23/19, 8c - 11/20/19) | n/a | n/a | bar: 2019-06-21 to 2019-11-19
| Any cases in which AS isn't re-awarded in RTC (e.g., discussion on RRS being provided by Load Resources on UFR). | 2019-06-21 | Y (2) | Y (2 - 10/23/19) | n/a | n/a | bar: 2019-06-21 to 2019-09-19
| Method for QSEs to indicate temporary inability to provide AS | 2019-06-21 | Y (1) | Y (1 - 10/23/19) | n/a | n/a | bar: 2019-06-21 to 2019-08-09; 2019-10-09
| ERCOT management of cases where AS is infeasible (e.g., deployment of Regulation resulting in physical transmission constraint over-loading) | 2019-08-09 | Y (9) | Y (9 - 11/20/19) | n/a | n/a | bar: 2019-08-09 to 2019-09-19; 2019-10-30
| Offer structure for AS offer in Real-Time | 2019-04-30 | Y (10) | Y (10 - 10/23/19) | n/a | n/a | bar: 2019-08-27 to 2019-10-09
| Timeline for submission of AS offers for Real-Time | 2019-04-30 | Y (11) | Y (11 - 10/23/19 with update on 1/29/20) | n/a | n/a | bar: 2019-08-27; 2019-10-09; 2019-11-19 to 2019-12-03
| Are changes to Verifiable Costs needed? | n/a | N | N | After additional discussion, ERCOT staff doesn’t believe any changes are needed for RTC. | After additional discussion, ERCOT staff doesn’t believe any changes are needed for RTC.
| Creation of proxy AS offers | 2019-08-27 | Y (12, 13) | Y (12, 13 - 11/20/19) | n/a | n/a | bar: 2019-08-27 to 2019-10-30
| Changes to validation of AS trades (related to AS self-provision in real-time) | 2019-10-30 | Y (14) | Y (14 - 1/29/20) | n/a | n/a | bar: 2019-10-30 to 2019-12-19
| Behavioral rules for AS Offer submittals | 2019-11-19 | Y (15) | N | Related Principle Concepts withdrawn | n/a | bar: 2019-11-19 to 2019-12-03
Key Principle 1.4 – Systems that Input into the Real-Time Optimization | Changes to RLC calculations | 2019-04-30 | Y (1, 2) | Y (1 - 7/24/19, 2 - 8/28/19) | n/a | n/a | bar: 2019-05-13 to 2019-06-21
| Telemetry changes, like those associated with any change to the RLC logic, both from the QSEs to ERCOT and from ERCOT to the QSEs | 2019-06-21 | Y (2, 3, 4) | Y (2 - 8/28/19, 3 and 4 - 1/29/20) | n/a | n/a | bar: 2019-06-21 to 2019-08-09; 2019-10-09 to 2019-12-03
Key Principle 1.5 – Process for Deploying Ancillary Services | Maintaining of existing RTM clearing timeframe | 2019-04-30 | Y (2) | Y (2 - 7/24/19) | n/a | n/a | bar: 2019-05-13 to 2019-06-21
| Changes to the AS Manager | 2019-05-13 | Y (1) | Y (1 - 7/24/19) | n/a | n/a | bar: 2019-05-13 to 2019-06-21
| LFC - Changes to existing UDBP framework | 2019-04-30 | Y (4, 5) | Y (4, 5 - 7/24/19) | n/a | n/a | bar: 2019-05-13 to 2019-07-12
| LFC - Portfolio vs. Resource-specific deployment, particularly for Regulation | 2019-04-30 | Y (3) | Y (3 - 7/24/19) | n/a | n/a | bar: 2019-05-13 to 2019-07-12
| LFC - Distribution of Regulation instructions | 2019-04-30 | Y (5, 6) | Y (5, 6 - 7/24/19) | n/a | n/a | bar: 2019-05-13 to 2019-07-12
| LFC - Process for deploying RRS | 2019-07-12 | Y (7, 8, 9) | Y (7, 8, 9 - 8/30/19) | n/a | n/a | bar: 2019-07-12 to 2019-08-09
| Impact of ASDCs | 2019-07-12 | Y (9, 10) | Y (9, 10 - 8/30/19) | n/a | n/a | bar: 2019-07-12 to 2019-08-09
| Removal of the existing process for QSEs to update telemetered AS schedules following manual deployment (specifically for Generation Resource and CLRs) | 2019-07-12 | Y (9) | Y (9 - 8/30/19) | n/a | n/a | bar: 2019-07-12 to 2019-08-09
| Elimination of Non-Spin Offer Floor | 2019-07-12 | Y (11) | Y (11 - 8/30/19) | n/a | n/a | bar: 2019-07-12 to 2019-08-09
| Continued ability of the Real-Time optimization (i.e., RTC) to be executed off-cycle, between regularly scheduled 5-minute executions. | 2019-04-30 | Y (12) | Y (12 - 8/30/19) | n/a | n/a | bar: 2019-07-12 to 2019-08-09
| RTC failure process | 2019-07-12 | Y (13) | Y (13 - 8/30/19) | n/a | n/a | bar: 2019-07-12 to 2019-08-09
| Changes to Emergency Operation Settlement | 2019-10-30 | Y (14, 15) | Y (14 and 15 - 1/29/20) | n/a | n/a | bar: 2019-10-30 to 2019-12-03
| Removal of separate Regulation and FRRS signals | 2019-10-30 | Y (16) | Y (16 - 1/29/20) | n/a | n/a | bar: 2019-10-30 to 2019-12-03
Key Principle 1.6 – Ancillary Service Imbalance Settlement with RTC | Potential use of existing energy imbalance calculations as basis | 2019-04-30 | Y (1) | Y (1 - 7/24/19) | n/a | n/a | bar: 2019-05-13 to 2019-07-12
| Separate AS imbalance calculation for each AS product | 2019-04-30 | Y (2) | Y (2 - 7/24/19) | n/a | n/a | bar: 2019-05-13 to 2019-07-12
| Allocation of non-zero AS imbalance amounts | 2019-04-30 | Y (3, 4) | Y (3, 4 - 7/24/19) | n/a | n/a | bar: 2019-05-13 to 2019-07-12
| Credit exposure changes associated with AS Imbalance | 2019-10-30 | Y (5) | Y (5 - 1/29/20) | n/a | n/a | bar: 2019-10-30 to 2019-12-03
| Update the Default Uplift calculation to include RT Awards as Market activity | n/a | N | N | Moved to KP5 as topic is actually associated with having virtual AS offers in the DAM | Moved to KP5 as topic is actually associated with having virtual AS offers in the DAM
| Additional details associated with having virtual AS Offers and/or Bids in the DAM, if needed. | n/a | N | N | PUCT direction received 7/18/19 (no further detailed RTCTF discussion expected) | PUCT direction received 7/18/19 (no further detailed RTCTF discussion expected)
Key Principle 2 – Suite of Ancillary Service Products | List of AS products and what type of Resources can provide them | 2019-09-19 | Y (1) | Y (1 - 11/20/19) | n/a | n/a | bar: 2019-09-19 to 2019-10-30
| Definition of AS products to align with the Real-Time Co-optimization (RTC) framework, specifically time limitations (E.g., can a 10 MWh hour battery offer 120 MW of AS for a 5-minute interval?) | 2019-09-19 | Y (2, 3, 4, 5, 6) | Y (2, 3, 4, 5, 6 - 11/20/19) | n/a | n/a | bar: 2019-09-19 to 2019-10-30
| Changes to the qualification process with RTC processes and any definition changes | 2019-09-19 | Y (2, 3, 4, 5, 6) | Y (2, 3, 4, 5, 6 - 11/20/19) | n/a | n/a | bar: 2019-09-19 to 2019-10-30
Key Principle 3 – Reliability Unit Commitment | Functionality and Process Concepts - RUC AS penalties | 2019-05-13 | Y (2) | Y (2 - 7/24/19) | n/a | n/a | bar: 2019-05-13 to 2019-07-12
| Functionality and Process Concepts - Details on changes to COP or alternative source of Resource information | 2019-05-13 | Y (3, 4) | Y (3, 4 - 7/24/19) | n/a | n/a | bar: 2019-05-13 to 2019-07-12
| Functionality and Process Concepts - Source of AS Offers that RUC will use | 2019-05-13 | Y (5, 6) | Y (5, 6 - 7/24/19) | n/a | n/a | bar: 2019-05-13 to 2019-07-12
| Functionality and Process Concepts - Consider qualified OFF and OFFQS Generation Resources when determining non-binding AS awards | 2019-05-13 | Y (7, 8) | Y (7, 8 - 7/24/19) | n/a | n/a | bar: 2019-05-13 to 2019-07-12
| Functionality and Process Concepts - Current RUC recommendation deferral process | 2019-05-13 | Y (9) | Y (9 - 7/24/19) | n/a | n/a | bar: 2019-05-13 to 2019-07-12
| RUC Settlement - Capacity short calculation and allocation of RUC make-whole, including the potential consideration of QSEs who are short on their AS Supply Responsibility. | 2019-06-21 | Y (12) | Y (12 - 8/30/19) | n/a | n/a | bar: 2019-06-21 to 2019-08-09
| RUC Settlement - Changes to RUC claw-back and make-whole | 2019-06-21 | Y (10, 11) | Y (10, 11 - 8/30/19) | n/a | n/a | bar: 2019-06-21 to 2019-08-09
| Additional detail on COP information changes | 2019-10-09 | Y (15) | Y (15 - 1/29/20) | n/a | n/a | bar: 2019-10-09 to 2019-12-03
| Potential floors for AS Offers on Resources committed through the RUC process | 2019-10-09 | Y (16, 17, 18, 19) | Y (16, 17, 18, 19 - 1/29/20) | n/a | n/a | bar: 2019-10-09 to 2019-12-03
| Process for determining the amount of individual AS products that can be provided by a Resource | 2019-10-09 | Y (13, 14) | Y (13, 14 - 1/29/20) | n/a | n/a | bar: 2019-10-09 to 2019-12-03
| QSEs instructed to be committed by RUC may elect to forgo RUC Settlement | 2019-10-09 | Y (20) | Y (20 - 1/29/20) | n/a | n/a | bar: 2019-10-09 to 2019-12-03
Key Principle 4 – The Supplemental Ancillary Service Market Process | Elimination and replacement of the SASM process | 2019-05-13 | Y (1) | Y (1 - 7/24/19) | n/a | n/a | bar: 2019-05-13 to 2019-06-21
Key Principle 5 – Day-Ahead Market | Functionality and Process Concepts - Ancillary Service Demand Curves (ASDCs) in the DAM | 2019-08-27 | Y (1, 2) | Y (1, 2 - 10/23/19) | n/a | n/a | bar: 2019-08-09 to 2019-10-09
| Effect of negative self-arrangement of AS on DAM ASDCs | 2019-12-03 | Y (2a) | Y (2(a) - 1/29/20) | n/a | n/a | bar: 2019-08-09 to 2019-10-09; 2019-12-03 to 2019-12-19
| Functionality and Process Concepts - Ancillary Service (AS) Offers that aren’t directly associated with a Resource (“Virtual” or “Financial-only” AS Offers) | 2019-09-19 | Y (7(a-i)) | Y (7(a-i) - 11/20/19) | n/a | n/a | bar: 2019-09-19 to 2019-10-30
| Functionality and Process Concepts - AS Bids to Buy | n/a | N | N | PUCT direction received 7/18/19 (no further detailed RTCTF discussion expected) | PUCT direction received 7/18/19 (no further detailed RTCTF discussion expected)
| Functionality and Process Concepts - Changes to the current DAM AS insufficiency process | 2019-08-27 | Y (3) | Y (3 - 10/23/19) | n/a | n/a | bar: 2019-08-09 to 2019-10-09
| Credit exposure changes associated with any changes to DAM submittals | 2019-10-09 | Y (7(a-i)) | Y (7(a-i) - 11/20/19, edit to 7(b) on 1/29/20) | n/a | n/a | bar: 2019-10-09 to 2019-10-30
| Settlement Concepts - Impacts on AS Obligation process for Load-Serving Entities (LSEs) if ASDCs in the DAM | 2019-08-27 | Y (4, 5, 6) | Y (4, 5, 6 - 10/23/19) | n/a | n/a | bar: 2019-08-09 to 2019-10-09
| Settlement Concepts - Settlement of AS Offers that aren’t directly associated with a Resource (“Virtual” or “Financial-only” AS Offers) | 2019-09-19 | Y (7(a-i)) | Y (7(a-i) - 11/20/19, edit to 7(b) on 1/29/20) | n/a | n/a | bar: 2019-09-19 to 2019-10-30
| Settlement Concepts - Settlement of AS Bids to Buy and how those AS Bids would impact the AS Obligation calculation for LSEs | n/a | N | N | PUCT direction received 7/18/19 (no further detailed RTCTF discussion expected) | PUCT direction received 7/18/19 (no further detailed RTCTF discussion expected)
| Update the Default Uplift calculation to include RT Awards as Market activity | 2019-11-19 | Y (7(j)) | Y (7(j) - 1/29/20) | n/a | n/a | bar: 2019-11-19 to 2019-12-03
| Continued need for negative self-arrangment of AS in the DAM | n/a | N | N | After additional discussion, RTCTF doesn't believe any changes are needed for RTC. | n/a | bar: 2019-11-19 to 2019-12-03
Key Principle 6 – Market-Facing Reports | Posting of Ancillary Service Demand Curves (ASDCs) | 2019-11-19 | Y (1, 2) | Y (1, 2 - 1/29/20) | n/a | n/a | bar: 2019-11-19 to 2019-12-19
| Real-Time Market (RTM) Ancillary Service (AS) awards and prices | 2019-11-19 | Y (1, 2) | Y (1, 2 - 1/29/20) | n/a | n/a | bar: 2019-11-19 to 2019-12-19
| Reports related to system conditions using Resources’ High Ancillary Service Limits (HASLs) | 2019-11-19 | Y (1, 2) | Y (1, 2 - 1/29/20) | n/a | n/a | bar: 2019-11-19 to 2019-12-19
| Day-Ahead Market (DAM) awards information if there are AS Offers that aren’t directly associated with a Resource (“Virtual” or “Financial-only” AS Offers) | 2019-11-19 | Y (1, 2) | Y (1, 2 - 1/29/20) | n/a | n/a | bar: 2019-11-19 to 2019-12-19
| Day-Ahead Market (DAM) awards information if there are AS Bids to Buy | n/a | N | N | PUCT direction received 7/18/19 (no further detailed RTCTF discussion expected) | PUCT direction received 7/18/19 (no further detailed RTCTF discussion expected)
| Changes to RTM and DAM disclosure reporting | 2019-11-19 | Y (1, 2) | Y (1, 2 - 1/29/20) | 2020-01-22 | 2020-01-22 | bar: 2019-11-19 to 2019-12-19
| New Reliability Unit Commitment (RUC) reporting associated with changes in functionality(e.g., on sufficiency of AS-qualified capacity in RUC in optimization) | 2019-11-19 | Y (1, 2) | Y (1, 2 - 1/29/20) | n/a | n/a | bar: 2019-11-19 to 2019-12-19
| New elements and changes to Settlement extracts | 2019-11-19 | Y (1, 2) | Y (1, 2 - 1/29/20) | n/a | n/a | bar: 2019-11-19 to 2019-12-19
| Changes to performance monitoring reports to align with any changes in performance metrics | 2019-11-19 | Y (1, 2) | Y (1, 2 - 1/29/20) | n/a | n/a | bar: 2019-11-19 to 2019-12-19
| Reports assoicated with AS Supply Responsbility | 2019-11-19 | Y (1, 2) | Y (1, 2 - 1/29/20) | n/a | n/a | bar: 2019-11-19 to 2019-12-19
| Removal of Supplemental Ancillary Service Market (SASM) reporting | 2019-11-19 | Y (1, 2) | Y (1, 2 - 1/29/20) | n/a | n/a | bar: 2019-11-19 to 2019-12-19
| Removal of Operating Reserve Demand Curve (ORDC) reporting | 2019-11-19 | Y (1, 2) | Y (1, 2 - 1/29/20) | n/a | n/a | bar: 2019-11-19 to 2019-12-19
Key Principle 7 – Performance Monitoring | Change in GREDP formulation to account for potential LFC changes | 2019-10-30 | Y (1) | Y (1 - 1/29/20) | n/a | n/a | bar: 2019-10-30 to 2019-12-19
| Changes to base point deviation charge calculations that align with changes to GREDP | 2019-12-03 | Y (4) | Y (4 - 1/29/20) | n/a | n/a | bar: 2019-12-03 to 2019-12-19
| Performance related to a release of a Resource's HASL through a change in AS schedule | 2019-11-19 | Y (3) | Y (3 - 1/29/20) | n/a | n/a | bar: 2019-11-19 to 2019-12-19
| Removal of the concept of AS Responsibility in RT | 2019-11-19 | Y (2) | Y (2 - 1/29/20) | n/a | n/a | bar: 2019-11-19 to 2019-12-19
| Performance monitoring during the transition into RTC during the time period immediately following implementation | 2019-12-03 | N, principal concept not need for intial Protocol development | N, principal concept not need for intial Protocol development | n/a | n/a | bar: 2019-12-03 to 2019-12-19
Key Principle 8 – Out of Scope Items | Identifying proposals that are out of scope for the RTC project and/or may warrant post-RTC review | Discussion will be on-going thoughout the year | Y (Noted in the KP document with history/rationale) | n/a | n/a | n/a

## Other Raised Issues
Issue | Meeting Raised
Triggers for automatically initiated an off-cycle execution of RTC (e.g., deploying a certain percent of the total Regulation amount, unit trips, etc.) | 5/13/19 RTCTF Meeting
AS Demand Curves for RUC | 7/12/19 RTCTF Meeting
Review of Real-Time Shadow Price Caps for Transmission Constraints | Expect to note at 8/9/19 RTCTF Meeting