## Sheet1
TX SET Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2020-02-19
Agenda Item: | Decision / Resolution | Action Items :
January Meeting Notes | No changes were made to the notes. | The Texas SET Vice Chair will have the final version posted to the January meeting page.
Flight Update | ERCOT presented the Flight 0220 update.
The ERCOT Flight Administrator noted that some of the CRs are late in completing the penny test that is supposed to be complete prior to beginning the Day 1 transaction flow. The ERCOT Flight Administrator requested that CRs complete this during the pre-flight period as stated in the documented requirements.
ERCOT Discussion Items
Texas SET EDI Questions—Living Document Discussion | 1. Texas SET discussed the spreadsheet and made recommendations as needed. 2. Texas SET requested ERCOT to investigate if the change to the ANSI section of the 867_03 PTD loop and segment could be changed to "Conditional" instead of "Optional". | ERCOT to provide feedback on the question 2.
NAESB (project number: TBD); Business driver is security—Possible testing specs collaboration with TDTMS | ERCOT stated that there are no changes to the timeline for the Transport Layer Security (TLS) upgrade since the last meeting.
RMS Update
Mass Transition Testing Workshop | The Texas SET Chair noted that there will be a workshop held after the March Retail Market Subcommittee (RMS) meeting. | RMS Leadership will request ERCOT to reach out to the POLRs and VREPs to attend the workshop.
Summer Preparedness Workshop | The RMS Chair noted that this workshop will be held after the April 7th RMS meeting. The RMS Chair noted that the March 4 Summer Preparedness workshop key documents contain information that the Market may be interested in reviewing.
ERCOT Guidance on Texas SET Project | The Texas SET Chair stated that RMS guidance for the Texas SET release timeline was to complete the changes and return with the recommendations before RMS can provide the guidance.
No RMS Assignments this month
Change Control Call-- No Call for the Month | Change Controls on the ERCOT Website. http://www.ercot.com/mktrules/issues/txsetcc
Issues--No new Issues Submitted for this Month | Issues on the ERCOT Website http://www.ercot.com/mktrules/issues/txset
Discussion Items
Texas SET Enhancement Matrix | 1. The Texas SET Chair conducted a discussion on the Matrix and the related change controls written; then made changes where needed. | 1. The AEP meeting attendee will send the 650_04 change for 4.0A to ERCOT to include with their change controls to be discssed at the March Texas SET Meeting. 2. The CenterPoint attendee will update the 814_20 Meter = "NONE", Change Control to leave the order of some of the items in the gray box as they were.
4.0A Change Controls |  | ERCOT to incorporate the 650 change discussed into the change controls for TX SET 4.0A and return with these for the Change Control call at the March meeting.
Future Release Change Controls 650_04 CC Review |  | Texas SET will continue to review and create the Change Controls needed based on the needs listed in the matrix.
Parking Lot
MISP Workshop Action Items • Add a MISP definition in RMG (RMGRR) | Still on Hold
Next Meeting--ERCOT MET Center 102 | 2020-03-26
Attendees F-T-F
Diana Rehfeldt TNMP | Stephen Wilson TXUE | Jordon Troublefield ERCOT
Kathy Scott CenterPoint Energy | Jim Lee AEP
Tyler Krueger Big Data Energy | Sam Pak ONCOR
Kyle Patrick NRG | Eric Blakey Just Energy
Attendees Webex
Kathryn Thurman ERCOT
Deb Belin MarkeWise
Paul Yockey ERCOT
Tracie Gaetano Accent Energy
Kim Wall Hansen Technology
Dave Michelsen ERCOT