## Slide 1
Resource Integration Workshop
Resource Integration Topics
ERCOT
Jay Teixeira
April 23, 2020

## Slide 2: Quarterly Stability Assessment (QSA)
Planning Guide 5.9
Next Deadline for QSA
If a GINR is not included in QSA, its Initial Synchronization date will be automatically delayed to the next quarter
All-Inclusive Generation Resource Initial Synchronization Date | Last Day for an IE to meet prerequisites as listed in paragraph (4) below | Completion of Quarterly Stability Assessment
Upcoming January, February, March | Prior August 1 | End of October
Upcoming April, May, June | Prior November 1 | End of January
Upcoming July, August, September | Prior February 1 | End of April
Upcoming October, November, December | Prior May 1 | End of July

## Slide 3: Quarterly Stability Assessment (QSA)
Planning Guide 5.9, Quarterly Stability Assessment
Issue’s seen in previous QSA’s
  10 day comment period for FIS
    Needs to be complete before QSA deadline
    TSPs need to plan for it
  Dynamic Model Review
    Dependent on FIS Stability study
    Need to meet PG 6.9 15 to 30 days prior to QSA deadline

## Slide 4: GINR Time Line (Fastest)

## Slide 5: New Reactive Study Scope Posted
http://www.ercot.com/content/wcm/lists/168310/Reactive_Study_Guide_v10_April2020.docx
Reflects changes due to NPRR849, approved by BOD on 12/10/2019.
Use for all new Reactive Studies going forward or in progress.

## Slide 6: Active PGRR’s
NPRR973, NOGRR196, PGRR074, RRGRR022 – Add Definitions for Generator Step-Up and Main Power Transformer - TAC at some point.
PGRR076 – Improvements to Generation Resource Interconnection or Change Request (GINR) Process – ROS at some point.

## Slide 7: Other contact information
ResourceIntegrationDepartment@ercot.com is distribution list for Resource Integration department

## Slide 8: Questions?
Thank you!