## Slide 1: CNP’s CIS Conversion Final Project Update to RMS
April 7, 2020
Retail Market Subcommittee (RMS)

## Slide 2
Release Name/Number | Release Start Date | Release End Date | Release Projected Volumes | Release Completed Volumes | 
Technical Go-Live | Friday, October 4, 2019 | Monday, October 7, 2019 | NONE- System Hardware and Software Changes | NONE- System Hardware and Software Changes | 
Release 1 | Friday, October 11, 2019 | Monday, October 14, 2019 | 10,000 ESI IDs | 10,500 ESI IDs | 
Release 2 | Friday, October 25, 2019 | Monday, October 28, 2019 | 140, 740 ESI IDs | 123,733 ESI IDs | 
Release 3 | Cancelled due to major weather event affecting Houston and surrounding service areas on Saturday, Jan. 11, 2020 – Sunday, Jan. 12, 2020 |  |  |  | 
Release 4 | Friday, January 31, 2020 | Monday, February 3, 2020 | 700,000 ESI IDs | 619,562 ESI IDs | 
Release 5 | Friday, February 21, 2020 | Monday, February 24, 2020 | 1.6 Million ESI IDs | 1,513,796 ESI IDs | 
New Name: March 9th Release | Friday, March 6, 2020 | Monday, March 9, 2020 | 305,000 to 325,000 ESI IDs | 311,337 ESI IDs | 
New Name: March 23rd Release | Friday, March 20, 2020 | Monday, March 23, 2020 | Approximately 101,000 ESI IDs | 100,744 ESI IDs | 
Release and ESI ID Totals | Successfully Completed 7 Releases |  |  | 2,679,672 ESI IDs | 

## Slide 3: Conversion Key Highlights
Production system impacts with March 23rd Final Release:
  Dual Mode between CIS and SAP Systems were Turned Off
  CIS (Legacy System) is Inquiry Only
  SAP HyperCare and System Stabilization Continues!
Decommissioning of CIS (Legacy System) will begin July 2020
CNP will continue the following email address and webpage:
  CISConversionGroup@CenterpointEnergy.com
    Available for market questions, issues and/or concerns
  CIS Conversion Information
    CIS Conversion FAQs Updates
    Market Information and Key Documents

## Slide 4: Questions