## Sheet1
TX SET Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2020-04-15
Agenda Item: | Decision / Resolution | Action Items :
February Meeting Notes | The Texas SET Vice Chair noted that there were some minor adjustments made to the notes, but there were no corrections received from the Working Group attendees. | The Vice Chair will have the notes posted to the March meeting page.
Flight Update | ERCOT Staff provided the update stating that the notes were basically the same as last time with the exception of the completion of the Out of Flight OOF0320 Service Provider change by two Competitive Retailers.
ERCOT Staff conducted the Change Control Call at 10 AM | Change Controls on the ERCOT Website. http://www.ercot.com/mktrules/issues/txsetcc
Change Control 2020-812: Administrative updates to the TX SET 814_20 and 814_21 Guides in order to reflect actual transaction processing. | Texas SET reached consensus on the agreement to forward this Change Control to the Retail Market Subcommittee (RMS) and request a vote to approve for Version 4.0A. | ERCOT Staff will present this at the next RMS meeting and request an email vote.
Change Control 2020-813: Administrative updates to the TX SET 867_02, 867_03 and 867_04 Guides in order to reflect actual transaction processing. | Texas SET reached consensus on the agreement to forward this Change Control to the Retail Market Subcommittee (RMS) and request a vote to approve for Version 4.0A. | ERCOT Staff will present this at the next RMS meeting and request an email vote.
Change Control 2020-814: Administrative updates to the TX SET 814_09 Guide. | Texas SET reached consensus on the agreement to forward this Change Control to the Retail Market Subcommittee (RMS) and request a vote to approve for Version 4.0A. | ERCOT Staff will present this at the next RMS meeting and request an email vote.
Change Control 2020-815: Update the 650_01 Guide as a result of the market recommendations following Hurricane Harvey. | Texas SET reached consensus on the agreement to request approval from RMS for the next Texas SET Release. | ERCOT Staff will hold this Change Control to be presented to RMS as a group with other Change Controls for the next Texas SET Release.
Change Control 2020-816: Update the 650_02 Guide as a result of the market recommendations following Hurricane Harvey. | Texas SET reached consensus on the agreement to request approval from RMS for the next Texas SET Release. | ERCOT Staff will hold this Change Control to be presented to RMS as a group with other Change Controls for the next Texas SET Release.
Change Control 2020-817: Update the 650_41 Guide as a result of the market recommendations following Hurricane Harvey. | Texas SET reached consensus on the agreement to request approval from RMS for the next Texas SET Release. | ERCOT Staff will hold this Change Control to be presented to RMS as a group with other Change Controls for the next Texas SET Release.
Change Control 2020-818: Update the 814_28 Guide as a result of the market recommendations following Hurricane Harvey. | Texas SET reached consensus on the agreement to request approval from RMS for the next Texas SET Release. | ERCOT Staff will hold this Change Control to be presented to RMS as a group with other Change Controls for the next Texas SET Release.
Change Control 2020-819: Clarify REF~4P and REF~IX are not provided when the NM109 is NONE or UNMETERED in the 814_20. | Texas SET reached consensus on the agreement to request approval from RMS for the next Texas SET Release. | ERCOT Staff will hold this Change Control to be presented to RMS as a group with other Change Controls for the next Texas SET Release.
ERCOT Discussion Items
PR288-01 EDI Map and Translator Replacement Texas SET EDI Questions—Living Document Discussion | Texas SET agreed to the change presented to the group related to the 814_20 use of the REF~TZ & DTM~313. Only one or the other should be used in this transaction that will clarify what ERCOT is validating currently. The language will be updated to match the language in the 814_04.
PR288-02 NAESB Application Tech Refresh Business driver is security—Possible testing specs collaboration with TDTMS | No new updates were noted.
The Texas SET Chair provided the Retail Market Subcommittee (RMS) Update on the following topics.
Notice given for a proposed Settlements Timelines Workshop
Summer Preparedness Workshop
Email Vote: IA for RMGRR163, Discontinue Generation of Legacy Retail Reports
No RMS Assignments this month
Issues--No new Issues Submitted for this Month | Issues on the ERCOT Website http://www.ercot.com/mktrules/issues/txset
Discussion Items
Texas SET Enhancement Matrix | It was determined that ERCOT will move forward with presenting the 4.0A changes at the next RMS meeting and request an email vote for the same. Texas SET agreed that all the 5.0 Change controls will be held until all are submitted and consensus reached before subitting them to RMS for a vote.
4.0A Change Controls | See Change Control Call notes.
5.0 Release Change Controls 1. Feedback for A83--Information provided was not supported in the Texas SET standards reject code to be used with additional reference to special characters not allowed in the REF03 as opposed to creating a new code. 2. Feedback on how to populate the date field for Continuous Service Agreement (CSA) start times in transactions and ERCOT CSA database. 3. Feedback on Texas SET Leadership review of Market guides (Solution to Stacking, REP Rule 13, Retail Market Guide, Protocols) to determine if the short term existing language in REP Rule 13 is sufficient or if additional language is needed to allow ERCOT to validate for the inappropriate use the REF~2W Ignore CSA code in the 814_24 Move Out Request. 4. County name addition to the 814_03 and 814_20 address fields. 5. Optional email field and additional outage information (12a and 12b of matrix). | The Texas SET Chair conducted a discussion and review of the matrix/ then made updates as needed. 1. Texas SET agreed to have ERCOT validate this at the 997 level on all transactions flowing through ERCOT and the TDSPs to validate this for point-to-point transactions at the 997 level; then Texas SET agreed to have ERCOT add this as a change control for the Version 4.0A. 2. The Texas SET Chair reviewed the scenario where a start and stop time date would be added to the 814_18 / 19 to allow ERCOT to send the MVO to CSA to the appropriate CSA CR. 3. No discussion was held on this topic at this meeting. 4. Texas SET agreed to move forward on the change to add the county to the customer service address. 5. Nothing was decided on this topic at this meeting. | 1. ERCOT Staff will provide a new change control for next month's meeting. 2. The Texas SET Chair agreed to research further and bring the findings to the next Texas SET meeting. 4. The Texas SET Chair will insert the redlined change into a Change Control and submit this for review at next month's meeting. 5. The Texas SEt Chair and the ONCOR meeting attendee will review this together to determine how to move forward; then bring those results to the next meeting.
Vistra / TXUE Proposed 5.0 Enhancements Spreadsheet | No discussion was held at this month's meeting.
Other Business
Mass Transition Testing | • ERCOT stated that they are sympathetic to the challenges that the Market is experiencing as a result of the required systems changes related to PUCT Order #50664. • No testing will be held that will interfere with the Market's ability to make these system changes. • ERCOT will re-evaluate once the changes are made. • It is possible a test could occur beginning the last week of April.
Parking Lot
MISP Workshop Action Items • Add a MISP definition in RMG (RMGRR) | Still on Hold
Next Meeting--ERCOT MET Center 102 or WebEx Only | 2020-05-20
Attendees F-T-F
Attendees Webex
Diana Rehfeldt TNMP | Tracie Gaetano Accent
Kyle Patrick NRG | Fraank Nunes ECInfoSystems
Kathy Scott Centerpoint Energy | Eric Blakey Just Energy
Jim Lee AEP | Adebaya Fapohunda
Sam Pak ONCOR | Paul Yockey ERCOT
Stephen Wilson TXUE | Barbara White Ambit
Deb Belin MarketWise | Jim Wade
Jordon Troublefield ERCOT | Michael Heselton
Kathryn Thurman ERCOT | Sai Maddadi
Dave Michelsen ERCOT
Becky Taylor Centerpoint Energy
Kim Wall Hansen Technologies
Dee Lowerre NRG