## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
May 13, 2020

## Slide 2
Project Portfolio Update
  Recent / Upcoming Project Implementations
  2020 Release Targets
  Planned Project Starts
  2020/2021 Project Spending Forecast
  Priority/Rank Options for Revision Requests with Impacts
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Implementations
2020 May Release – R3 – 5/26/2020 – 5/28/2020 In Flight
  NPRR856 – Treatment of OFFQS Status in Day-Ahead Make Whole and RUC Settlements
  NPRR884 – Adj. to Pricing and Settlement for RUCs of On-Line Combined Cycle Gen. Resources
  OBDRR006 – Alignment of ORDC OBD with NPRR884
  RMGRR163 – Discontinue Generation of Legacy Retail Reports
  SCR803 – Enhance Wind Integration Report & Create Solar Integration Report and Solar Dashboard
  CMM Release 2a
    NPRR887 – Monthly Posting of Default Uplift Exposure Information
    NPRR907 – Revise Definition of M1a to Reflect Actual Calendar Days
    NPRR985 – Modify Forward Adjustment Factors to Include Pricing for the Current Operating Day
2020 August Release – R4 – 8/4/2020 – 8/6/2020 In Flight
  NPRR902 – ERCOT Critical Energy Infrastructure Information
  NPRR905 – CRR Balancing Account Resettlement
  NPRR935(a) – Post All Wind and Solar Forecasts
    All Changes Except Section 4.2.3
  NPRR951 – Active and Inactive SCED Constraint Reporting
  NPRR977 – Create MIS Posting for RUC Cancellations
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2020 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/4 – 2/6 | April 3/31 – 4/2 | May 5/26 – 5/28 | August 8/4 – 8/6 | October 10/13 – 10/15 | December 12/8 – 12/10
NPRR873 SCR797 NPRR877 Ph2 NPRR968 NPRR943 EMIL Web Interface NPRR863 Ph1 NPRR960 NOGRR187 OBDRR011 | SCR802 NPRR928 NPRR929 NPRR978(a) NPRR988 NPRR953 | NPRR856 NPRR884 OBDRR006 SCR803 NPRR887 NPRR907 NPRR985 RMGRR163 NPRR930(a) MIS Testing | NPRR902 NPRR905 NPRR935(a) NPRR951 NPRR977 SCR804 SCR781(a) RRGRR016 RRGRR019 | NPRR998 MIS Go-Live MMS/OS Refresh NPRR863 Ph2 | NPRR978 SCR806 SCR799 NPRR857 NPRR885 NPRR904 NPRR917 NPRR936 NPRR941 NPRR963 NPRR971 NPRR986 OBDRR009 PGRR070(b) SCR781(b) SCR799
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
NS
R1
R2
R3
R4
R5
R6
3/1
NPRR863 Ph1 – FFR
NPRR863 Ph2 – ECRS
NPRR930(a) – O&M portion
NPRR935(a) – All changes except Section 4.2.3
NPRR935(b) – Section 4.2.3 changes
NPRR978(a) – Initial report decommissions
PGRR070(b) – Remaining PGRR language
SCR781(a) – View / Edit capability
MMS/OS Upgrade “Chill”
MMS/OS Upgrade “Freeze”
ü
ü
ü
E
E
E
E
E
E
E
November
Off-Cycle
1/1
2021 Go-Lives
NS
NS
NS
P
NS
NS
NS
NS
NS
P
P
NS
E
E
NS
September
Off-Cycle
P
P
P
P
E
P
1/19
E
ü
ü
TBD Items | 2017 | 2018 | 2019 / 2020
 | NPRR702, NPRR829 | NPRR825(b), NPRR867, NPRR841 | NPRRs: 826, 879, 918, 930, 935(b), 939, 962, 965, 974, PGRR066, SCR800, SCR805
ü
CMM Release 2a
1/30
August
October
Q3 RIOO
RARF Go-Live for View/Update
ü
ü
ü
ü
ü
ü
ü
ü
ü
2022 Go-Lives
I
5/1
ü
7/1

## Slide 5: Approved Revision Requests “Not Started” – Planned to Start in Future Months
Revision Request | Target Start Date | Release Target | Cost Estimate | Author
NPRR998 – ERS Deployment and Recall Messages | May 2020 | 2020-R5 | $15k-$25k | ERCOT
SCR806 – Adding QSE and DME Information to Disclosure Reports | June 2020 | 2020-R6 | $65k-$95k | ERCOT
NPRR978 – Alignment with Amendments to PUCT Substantive Rule 25.505 | June 2020 | 2020-R6 | $65k-$95k | ERCOT
NPRR963 – Creation of Generation & Controllable Load Resource Group (GCLR Group) | Q3 2020 | TBD | $150k-$200k | Tenaska
NPRR904 – Revisions to Real-Time On-Line Reliability Deployment Price Adder for ERCOT-Directed Actions Related to DC Ties and to Correct Design Flaws | Q3 2020 | TBD | $200k-$300k | Rainbow
OBDRR009 – ORDC OBD Revisions for ERCOT-Directed Actions Related to DC Ties | Q3 2020 | TBD | $30k-$50k | Rainbow
SCR800 – Addition of DC Tie Ramp to GTBD Calculation | Q3 2020 | TBD | $30k-$50k | ERCOT
NPRR962 – Publish Approved DC Tie Schedules | Q3 2020 | TBD | $15k-$30k | ERCOT
NPRR930 – Process Pricing and Cost Recovery for Delayed Resource Outages | Q3 2020 | TBD | $100k-$200k | Citigroup
NPRR936 – CRR Account Holder Limits | Q3 2020 | TBD | $150k-$250k | Engie
SCR799 – ERCOT Outage Study Cases in the System Operations Test Env. (SOTE) | Q3 2020 | TBD | $150k-$250k | Oncor
Project Initiations – Next 3 Months
Note: Target Start Dates are subject to change.
Based on recent developments, ERCOT is evaluating project capacity.
REGULATORY
REGULATORY

## Slide 6: 2020 Project Spending
2020 PPL Budget = $29.0M
“Potential Demand” represents internal ERCOT projects that have not been fully approved
May actuals not yet available
June-December forecasts are updated

## Slide 7: Revision Request Funding Placeholder Status
In ERCOT’s 2020/2021 proposed budget, the following amounts are allocated for Revision Request work
  2020 = $4M
  2021 = $4M
Yearly Revision Request Spending Forecast Summary
Project Status | 2020 | 2021
YTD Actuals | $0.90M | -
Approved – In-Flight / Complete | $2.91M | $1.71M
Approved – Not Started | $0.57M | $1.81M
Remaining Funding | $0.52M | $0.48M
Total Allocation | $4.00M | $4.00M
As of 4/30/2020

## Slide 8: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR987 | BESTF-3 Energy Storage Resource Contribution to Physical Responsive Capability and Real-Time On-Line Reserve Capacity Calculations | 2020 | 3010 | MMS impacts - Consider delivering after MMS/OS Tech Refresh Target go-live: mid- to late-2021 Relates to both “combo” model and “single” model
NPRR1006 | Update Real-Time On-Line Reliability Deployment Price Adder Inputs to Match Actual Data | 2020 | 3020 | Targeting completion of IA prior to May PRS meeting MMS impacts - Consider delivering after MMS/OS Tech Refresh Target start late in 2020 for a mid-2021 go-live
NPRR1019 | Pricing and Settlement Changes for Switchable Generation Resources (SWGRs) Instructed to Switch to ERCOT | 2020 | 3030 | MMS impacts - Consider delivering after MMS/OS Tech Refresh Target start late in 2020 for a mid-2021 go-live
Options for…
PPL Rank Information
Next available 2020 Rank in Business Strategy = 3010
Next available Rank in Regulatory = 260
Note
Items in the Regulatory section of the PPL are not tracked against the market Revision Request funding allocation