## Slide 1
Real-Time Co-optimization Task Force (RTCTF) Update
Matt Mereness
RTCTF Chair
TAC
May 27, 2020

## Slide 2: Outline of RTCTF Update
RTC Revision Requests (RTCRRs)
RTCRR Review Schedule and Process
Discussion of process for RTCRR comments and alignment with Key Principles
Other RTC Considerations
Next Steps

## Slide 3: RTC Revision Requests
Reminder that based on the Board-approved RTC Key Principles (KPs), ERCOT developed and released the following NPRRs, NOGRR, and OBDRR with a single Impact Analysis (IA).
RTCRRs released March 25, 2020 | Pages 549 total
NPRR1007- RTC NP3- Management Activities for the ERCOT System | 62
NPRR1008- RTC NP4- Day-Ahead Operations | 65
NPRR1009- RTC NP5- Transmission Security Analysis and Reliability Unit Commitment | 39
NPRR1010- RTC NP6- Adjustment Period and Real-Time Operations | 248
NPRR1011- RTC NP8- Performance Monitoring | 49
NPRR1012- RTC NP9- Settlement and Billing | 15
NPRR1013- RTC NP 1, 2, 16, 25- Overview, Definitions/Acronyms, Registration and Qualification of MPs, and Market Suspension and Restart | 24
NOGRR211- RTC Nodal Operating Guides 2 and 9- System Operations and Control Requirements and Monitoring Programs | 21
OBDRR020- RTC - Methodology for Setting Maximum Shadow Prices for Network and Power Balance Constraints | 26

## Slide 4: RTCRR Review Schedule and Process
Schedule of 2020 meetings for RTCRRs:
Mar. 11 – RTCTF (Plan and logistics for RR review)
Apr. 8 – RTCTF (Review detailed plan, and begin review process)
Apr. 30 – RTCTF
May 11 – Special RTCTF for Potential Design Flaw- AS Price Cap discussion
May 20 – RTCTF
Jun. 10 – RTCTF
Jun. 29 – RTCTF
Jul. 22 – RTCTF
Aug. 12 – RTCTF
Sep. 9 – RTCTF
Sep. 28 – RTCTF
Oct. 21 – RTCTF
Nov. 5 – ROS
Nov. 11 – PRS
Nov. 12 – RTCTF (if needed)
Nov. 17 – CWG
Nov. 18 – TAC
Dec. 8 – ERCOT Board

## Slide 5: RTCRR Review Process
7-days prior #1
ERCOT posts agenda and RTCRRs to be reviewed
7-days prior #2
MP comments and redlines due and posted to address concerns or alternatives
During meeting, MPs discuss any concerns or alternatives
7-days prior #3
MPs must document concerns and alternative language prior to meeting, and be prepared to discuss.
7-days prior #3
Non-consensus materials posted for options on language to be considered.
Meeting #1 Meeting #2 Meeting #3
TAC will be updated monthly. If irresolvable issues occur at RTCTF, the RTCTF Chair can request TAC endorsement to resolve.
2-days prior #2
ERCOT responds to MP comments with redlines
Consensus Items Tracked in Spreadsheet as Complete
Resolved Items Tracked in Spreadsheet as Complete
ERCOT will file cumulative RTCRR comments reflecting when consensus on sections achieved. (Also tracked in summary spreadsheet)

## Slide 6: RTCRR Review Schedule and Process
Detailed schedule for reviewing the RTCRR language with RTCTF (posted on the RTCTF page, and excerpt below).
Of the total 187 binding document sections under review, the task force has already reviewed 68 sections and reached consensus on 27.

## Slide 7: RTCRR Review Schedule and Process
4/30/2020 RTCTF Consensus:
  SWCAP/VOLL - OBDRR020 (Sections 2 and 4)
  AS Proxy Offers and General SCED – NPRR1010 (6.4.9.1.1)
  Reliability Deployment Pricing Run - NPRR1010 (6.5.7.3.1)
  COP Changes - NPRR1007 (3.9, 3.9.1, and 3.9.2)
  RUC General Update - NPRR1009 (5.1, 5.2.2.1, 5.2.2.2, 5.3, 5.4, 5.4.1, and 5.5.2)
5/20/2020 RTCTF Consensus:
  SWCAP/VOLL- NPRR1008 (4.4.11 and 4.4.11.1)
  ASDC Creation- NPRR1008 (4.4.12)
  AS Proxy Offers and General SCED- NPRR1010 (6.5.7.3)
  Market Restart- NPRR1013 (25.3)
  SASM Removal- NPRR1008 (4.5.2) & NPRR1010 (6.4.9, 6.4.9.1.3, 6.4.9.2, 6.4.9.2.1, 6.4.9.2.2, and 6.4.9.2.3)
  DAM General Update- OBDRR020 (Appendix 1)

## Slide 8: Discussion of process for RTCRR comments and alignment with Key Principles
During the May 11 Special RTCTF meeting LCRA described the AS price cap “design flaw” and proposed a solution that is different than the approved Key Principles (related to KP1.2 and KP8).
RTC KPs were approved by the Board in February 2020 to create foundational design elements to help narrow development of RTC NPRRs and OBDRRs (RTCRRs).
ERCOT proposes the following criteria to modify RTCRRs beyond the scope of the RTC KPs if a market design flaw or error was discovered following Board approval of the RTC KPs:
  The modification complies with PUC directives;
  The modification will not incur additional RTC project costs or schedule delays; and
  The modification will not delay timely implementation of RTCRRs (i.e., will not prevent the Board from considering the NPRR at the December 8, 2020 Board meeting).

## Slide 9: Discussion of process for RTCRR comments and alignment with Key Principles
Proposed process for modifying RTCRRs beyond scope of Board-approved KPs:
  A Market Participant has the right to express concerns with a RTCRR.
    A Market Participant may file comments to modify a RTCRR beyond the scope of the Board-approved KPs.
    In comments to modify an RTCRR, the submitting party shall explain how the revisions meet the criteria proposed on the previous slide.
  RTCTF will provide:
    The technical forum (e.g., an extra off-cycle meeting) for discussion of the proposed RTCRR changes with the understanding that RTCTF consensus is not practical and will not occur.
  At TAC:
    RTCTF Chair will advise TAC leadership of any RTCRR Comments that propose to modify the scope of the KPs beyond that which was approved by the Board, and
    Request time for the MP to present to TAC for consideration, as well as another MP to present the counterpoints (if any) as to why the existing KP should continue to be maintained and aligned with RTCRRs.
    TAC may take a straw poll to endorse the proposed NPRR comments; the vote would not be binding and therefore non-appealable, but would classify the modified/added concept as valid.
  If TAC endorses the alternative, the RTCTF Chair would update the Board of the straw poll decision.
  The RTCRR comments would subsequently be considered at PRS, TAC, and ultimately the ERCOT Board as consistent with Protocols Section 21 process.

## Slide 10: Next Steps
Review reminders:
  MPs encouraged to send Revision Request redlines for RTCTF consideration to DMaggio@ercot.com & MMereness@ercot.com to document and discuss at next meeting.
  You can also submit formal comments through the standard Market Rules RevisionRequest process.
  As RTCTF achieves consensus on groups of issues, ERCOT will periodically submit formal comments reflecting the latest consensus/working versions of the NPRRs.
Next RTCTF is June 10th
June TAC meeting may include an item for discussion and potential vote
Any comments or questions?

## Slide 11: Appendix
Overall RTC Delivery Schedule

## Slide 12: Overall RTC Delivery Schedule
Draft Timeline
There are several items/policies, beyond RTCRRs, that must be addressed prior to the implementation of RTC—e.g.:
  Proxy Offer Curves;
  RUC AS Demand Curves;
  Transitional language for RTC go-live (if any);
  ORDC/RTC results comparison; and
  Target dates for MP detailed requirements (e.g., SCADA changes, XML changes, Market Trials plans).