## Sheet1
TX SET Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2020-05-20
Agenda Item: | Decision / Resolution | Action Items :
April Meeting Notes
| No updates were made. | The Texas SET Vice Chair will have the notes posted on the ERCOT Texas SET meeting page key documents.
Flight Update
ERCOT Staff presented the 0620 Flight update.
ERCOT Staff conducted the Change Control Call at 10 AM | Change Controls on the ERCOT Website. http://www.ercot.com/mktrules/issues/txsetcc
Change Control 2020-810: Clarifies how the TDSP utilize the BGN08 and REF~5H segments within the 650_04 when terminating or suspending service at a premise. | Consensus was reached to request that the Retail Market Subcommittee (RMS) approve the change control as a non-emergency for version 4.0A
Change Control 2020-819: Clarify REF~4P and REF~IX are not provided when NM109 is NONE or UNMETERED in the 814_20. | Consensus was reached to request that RMS approve the change control as a non-emergency for a future release.
Change Control 2020-820: Recipients of the Select Language Characters (Special Characters) found in the Extended Character Set of the Application Control Structure can be rejected with a 997 Reject. | Consensus was reached to request that RMS approve the change control as a non-emergency for version 4.0A..
Change Control 2020-821: Add necessary data elements to transactions to allow the submission of County to be communicated. | Consensus was reached to request that RMS approve the change control as a non-emergency for a future release.
Change Control 2020-822: Update the 814_20 Guide for the REF~4P to clarify the use when NM101=MX. | Consensus was reached to request that RMS approve the change control as a non-emergency for version 4.0A
Change Control 2020-823 Administrative change to the 824 to clarify only one OTI loop per transaction | Consensus was reached to request that the RMS approve the change control as a non-emergency for version 4.0A
ERCOT Discussion Items
PR288-01 EDI Map and Translator Replacement Texas SET EDI Questions—Living Document Discussion | 1. ERCOT will begin using the updated version of the translator in the Retail Market Test Environment (RMTE) in July. 2. ERCOT will ask that all of their trading partners exchange a large and small file to test in the RMTE and that information updates will begin to be exchanged in mid-July. 3. ERCOT will provide another update on the EDI Project at the June Texas SET meeting. 4. CNP requested clarification of what version of NAESB will be used for the test in RMTE--ERCOT stated all versions currently supported will be allowed for the test.
PR288-02 NAESB Application Tech Refresh Business driver is security—Possible testing specs collaboration with TDTMS | Nothing new was provided, except that ERCOT stated a specific shutoff date for older TLS versions will occur sometime early next year.
The Texas SET Chair provided the Retail Market Subcommittee (RMS) Update on the following topics.
All Change Controls submitted were approved in a subsequent email vote after the meeting.
ERCOT Staff provided the Mass Transition Test Recap--This drill was considered a success.
RMS Assignments this month
COVID ERP Process Discussion | The Texas SET Chair conducted a discussion on how the MarkeTrak process is going. 1. ERP_A and ERP_D There were no issues noted on the Submit portion. CRs would like to have consistent comments in the responses of the MarkeTrak Issues. CRs would like to have a comment that states if all are accepted or if there are any rejects contained within the spreadsheet. One TDSP requested that the CRs put a comment stating whether the ERP_D was a mistake on addition or if the customer was removed from the Solix list. 2. ERP_R CR's would like for the MarkeTraks to be held open for a period of time (maybe 3 hours or until the end of the day) to allow the CRs time to attach the spreadsheet. One TDSP stated that they are keeping them open for one hour unless a CR asks for more time. CRs stated that they would like to know if they need to ask for more time as long as they have the spreadsheet attached by 5 PM. CRs cover sheet has a count of ESI IDs. TDSPs are expecting only the number of distinct ESI IDs and not necessarily the total number of rows. One TDSP stated that the TDSPs are going to review and provide feedback. That TDSP stated that the group is considering changing the cover sheet to have the count stated as the number of distinct invoices. 3. ERP_P It was noted that there are instances where a customer may switch away a second time creating a leap frog condition and the request from the CR may be rejected because they are not the immediate previous CR. More discussion may occur in the future. 4. One CR would like to have a weekly list of customers that switched to them that were already on the suppression list so they insure that they do not disconnect those customers. Two TDSPs are sending a list, but two are requesting the CRs use the rate codes from the 814_05 of the switch as a determination. CRs would like consistency, but will work with the differences. | The TDSPS will conduct further discussions where needed and provide subsequent feedback at a later date.
Issues-- | Issues on the ERCOT Website http://www.ercot.com/mktrules/issues/txset
Issue 020-I150 Need to review the use of the A13 Reject Code | 1. CNP suggested that an evaluation be completed to determine if new codes are needed based on a large percentage of A13 use. 2. It was suggested that TXUE scrub the data to determine which rejects are from ERCOT and which are from TDPSs; then resend the spreadsheets. 3. The TDSPs agreed to review together; then provide feedback at the next meeting.
Discussion Items
Texas SET Enhancement Matrix 1. Feedback on how to populate the date field for Continuous Service Agreement (CSA) start times in transactions and ERCOT CSA database. 2. Feedback on Texas SET Leadership review of Market guides (Solution to Stacking, REP Rule 13, Retail Market Guide, Protocols) to determine if the short term existing language in REP Rule 13 is sufficient or if additional language is needed to allow ERCOT to validate for the inappropriate use the REF~2W Ignore CSA code in the 814_24 Move Out Request. | 1. This item will be discussed in conjunction with other items still open on the matrix at the next Texas SET meeting. 2. This item will be discussed in conjunction with other items still open on the matrix at the next Texas SET meeting. 3. It was also noted that the next release may be pushed to 2022 due to ERCOT projects and the effects of the COVID19 virus. | 3. The RMS Vice Chair will get with ERCOT staff to attempt to determine a ballpark figure for the project and receive a possible timeline when the next version Release can be implemented.
Other Business
IDR vs AMS -- Proposed changes from PWG | At the PWG meeting, ERCOT suggested using new Load Profiles for those >700 KW / kva ESI IDs applicable to the 4CP billing that have AMS meters that are not designated with a BUSIDRRQ Load Profile. 1. CNP provided an alternative solution that allows a modification to the AMS Indicator to add a NCP or 4CP designation as opposed to the new Load Profiles. 2. This was noted as a secondary option and will be discussed at the June 2nd IDR vs AMS workshop; then can be further discussed at the next Texas SET meeting if needed.
Parking Lot
MISP Workshop Action Items • Add a MISP definition in RMG (RMGRR) | Still on Hold
Next Meeting--ERCOT MET Center 102 or WebEx Only | 2020-06-17
Attendees F-T-F
Attendees Webex
Kyle Patrick NRG | Jordan Troublefield ERCOT | Sai Mullady
Diana Rehfeldt TNMP | Kathryn Thurman ERCOT | Sam Pak ONCOR
Andrea Couch TNMP: | Kathy Scott Centerpoint Energy | Stephen Wilson TXUE
Brad Neilson | Keanan Ryan ERCOT | Tracie Gaetano Accent Energy
Carolyn Reed Centerpoint Energy | Kim Wall Hansen Technologies | Mark Ruane ERCOT
Cindy | Lauren Damin | Keenan Ryan ERCOT
Deb Belin MarketWise | Linda | Heather Falls ONCOR
Eric Blakey Just | Lore Lee | Dave Michelsen ERCOT
Frank Nunes EcInfoSystems | Mary Do Znalytics | Vrushal Bonde TNMP
Janie Escalante Summer Energy | Michael Glass NEC | Sheri Wiegand TXUE
Jennifer | Paul Williams ePSolutions | Chris Rowley ONCOR
Jim Lee AEP | Paul Yockey ERCOT | Esther Kent Centerpoint Energy
Tyler Krueger Big Data Energy