## Slide 1
Resource Integration Workshop
Resource Integration Topics
ERCOT
Jay Teixeira
June 23, 2020

## Slide 2: Quarterly Stability Assessment (QSA)
Planning Guide 5.9
Next Deadline for QSA
If a GINR is not included in QSA, its Initial Synchronization date will be automatically delayed to the next quarter
All-Inclusive Generation Resource Initial Synchronization Date | Last Day for an IE to meet prerequisites as listed in paragraph (4) below | Completion of Quarterly Stability Assessment
Upcoming January, February, March | Prior August 1 | End of October
Upcoming April, May, June | Prior November 1 | End of January
Upcoming July, August, September | Prior February 1 | End of April
Upcoming October, November, December | Prior May 1 | End of July

## Slide 3: Quarterly Stability Assessment (QSA)
Planning Guide 5.9, Quarterly Stability Assessment
Issue’s seen in previous QSA’s
  10 day comment period for FIS
    Needs to be complete before QSA deadline
    TSPs need to plan for it
  Dynamic Model Review
    Dependent on FIS Stability study
    Need to meet PG 6.9 15 to 30 days prior to QSA deadline

## Slide 4: GINR Time Line (Fastest)

## Slide 5: Posting Screening Studies
Recent MP Inquires as to why Screening Studies are not posted
PG section 7.1(2), contains
PG section 7.1, created by PGRR036, was not created to contain posting requirements, only “the transfer of data and information to the Market Information System (MIS)” from the Planning and Operations Information (POI) website

## Slide 6: Posting Screening Studies
PGRR044 – added Screening Studies to section 7.1(2) but did not add posting language to PG section 5 so no posting requirements were made
ERCOT will initiate PGRR to clean up section 7.1(2) and remove items no longer created such as Generation Data Forms and Generation Interconnection Supporting Documents as well as clarify its purpose
The posting of screening studies after an FIS request will have an impact on ERCOT as some screening studies include references to other GINR’s that may not be public
ERCOT would be open to post specific screening studies upon a valid request from a registered MP

## Slide 7: RARF Submission Process During Full Registration
Two approved ways for RARF submittal:
  MIS e-service or service request tool (Primary)
  E-mailing to ERCOT legal (Alternate)
The second option should only be used if MIS submission can not be used due to technical issues, the MP should:
  create a Helpdesk ticket for the MIS issue and copy your Account Manager;
  submit the RARF along with the Alternate Signature Form via email to MPRegistration@ercot.com and resourcereg@ercot.com, and copy your Account Manager.

## Slide 8: RARF Submission Process During Full Registration
Proofpoint is not supposed to be used for RARF submission or any confidential information
Please submit on MIS at least 4-5 business days ahead of the deadline. Don’t wait till the last minute.
  If using the alternate method of submission, allow an additional 3-5 days (7 to 10 business days total)
If you are new to MIS, please contact the assigned Account Manager to give you an introduction to the MIS and the process to submit service requests including RARFs.

## Slide 9: Active PGRR’s
NPRR973, NOGRR196, PGRR074, RRGRR022 – Add Definitions for Generator Step-Up and Main Power Transformer - TAC June 24
PGRR076 – Improvements to Generation Resource Interconnection or Change Request (GINR) Process – ROS for Impact Analysis, July 9, ERCOT IA on KCE Comments 052820 to be reviewed

## Slide 10: Other contact information
ResourceIntegrationDepartment@ercot.com is distribution list for Resource Integration department

## Slide 11: Questions?
Thank you!