## NPRR 1014 BESTF Schedule_062620
New concepts/sections for single model ESR
Sections Overlaps with RTC NPRR
New Sections added with ERCOT 06-19-2020 Commments and before 6-30-20
Protocol Section | Section Header | Status | 2020-04-16 | 2020-05-01 | 2020-05-21 | 2020-06-12 | 2020-06-30 | 2020-07-23 | 2020-08-14 | 2020-09-11 | 2020-09-29 | 2020-10-22 | 2020-11-13
2.1 | Definitions | Completed | bar: 2020-05-01 to 2020-05-21
3.1.4.3 | Reporting for Planned Outages, Maintenance Outages, and Rescheduled Outages of Resource and Transmission Facilities | bar: 2020-06-12 to 2020-07-23
3.2.1 | Calculation of Aggregate Resource Capacity | bar: 2020-06-12 to 2020-07-23
3.2.5 | Publication of Resource and Load Information | bar: 2020-06-12 to 2020-07-23
3.3.2.1 | Information to Be Provided to ERCOT | bar: 2020-06-12 to 2020-07-23
3.9.1 | Current Operating Plan (COP) Criteria | Completed | bar: 2020-05-01 to 2020-05-21
4.3 | QSE Activities and Responsibilities in the Day-Ahead | Completed | bar: 2020-05-01 to 2020-05-21
4.4.7.2 | Ancillary Service Offers | Completed | bar: 2020-05-01 to 2020-06-12
4.4.7.2.1 | Ancillary Service Offer Criteria | Completed | bar: 2020-05-01 to 2020-05-21
4.4.7.3.1 | Ancillary Service Trade Criteria | Completed | bar: 2020-05-01 to 2020-05-21
4.4.9.2 | Startup Offer and Minimum-Energy Offer | Completed | bar: 2020-05-01 to 2020-05-21
4.4.9.3 | Energy Offer Curve | bar: 2020-06-30 to 2020-08-14
4.4.9.4.1 | Mitigated Offer Cap | Completed | bar: 2020-05-01 to 2020-05-21
4.4.9.4.2 | Mitigated Offer Floor | Completed | bar: 2020-05-01 to 2020-05-21
4.4.9.7 | Energy Bid/Offer Curve (new) | Completed | bar: 2020-05-01 to 2020-05-21
4.4.9.7.1 | Energy Bid/Offer Curve Criteria (new) | Completed | bar: 2020-05-01 to 2020-05-21
4.4.9.7.2 | Energy Bid/Offer Curve Validation (new) | Completed | bar: 2020-05-01 to 2020-05-21
4.4.10 | Credit Requirements for DAM Bids and Offers | Completed | bar: 2020-05-01 to 2020-05-21
4.5.1 | DAM Clearing Process | Completed | bar: 2020-05-21 to 2020-06-30
4.5.3 | Communicating DAM Results | Completed | bar: 2020-05-21 to 2020-06-30
4.6.2.1 | Day-Ahead Energy Payment | bar: 2020-06-30 to 2020-08-14
4.6.2.2 | Day-Ahead Energy Charge | bar: 2020-06-30 to 2020-08-14
4.6.2.3 | Day-Ahead Make-Whole Settlements | Completed | bar: 2020-05-21 to 2020-06-30
4.6.2.3.2 | Day-Ahead Make-Whole Charge | bar: 2020-06-30 to 2020-08-14
5.3 | ERCOT Security Sequence Responsibilities | Completed | bar: 2020-05-21 to 2020-06-30
5.4 | QSE Security Sequence Responsibilities | Completed | bar: 2020-05-21 to 2020-06-30
5.7.1 | RUC Make-Whole Payment | bar: 2020-06-12 to 2020-07-23
5.7.2 | RUC Clawback Charge | bar: 2020-06-12 to 2020-07-23
5.7.3 | Payment When ERCOT Decommits a QSE-Committed Resource | bar: 2020-06-12 to 2020-07-23
5.7.4.1.1 | Capacity Shortfall Ratio Share | bar: 2020-06-30 to 2020-08-14
6.3 | Adjustment Period and Real-Time Operations Timeline | Completed | bar: 2020-05-21 to 2020-06-30
6.3.1 | Activities for the Adjustment Period | Completed | bar: 2020-05-21 to 2020-06-30
6.4.2 | Output Schedules | Completed | bar: 2020-05-21 to 2020-06-30
6.4.2.1 | Output Schedules for Resources Other than Dynamically Scheduled Resources | Completed | bar: 2020-05-21 to 2020-06-30
6.4.2.3 | Output Schedule Criteria | Completed | bar: 2020-05-21 to 2020-06-30
6.4.4 | Energy Offer Curve | Completed | bar: 2020-05-21 to 2020-06-30
6.5.1.2 | Centralized Dispatch | Completed | bar: 2020-05-21 to 2020-06-30
6.5.5.2 | Operational Data Requirements | Completed | bar: 2020-05-21 to 2020-06-30
6.5.7.1.10 | Network Security Analysis Processor and Security Violation Alarm | Completed | bar: 2020-05-21 to 2020-06-30
6.5.7.1.12 | Resource Limits | Completed | bar: 2020-05-21 to 2020-06-30
6.5.7.2 | Resource Limit Calculator | Completed | bar: 2020-05-21 to 2020-06-30
6.5.7.3 | Security Constrained Economic Dispatch | Completed | bar: 2020-05-01 to 2020-05-21
6.5.7.3.1 | Determination of Real-Time On-Line Reliability Deployment Price Adder | Completed | bar: 2020-05-01 to 2020-05-21
6.5.7.5 | Ancillary Services Capacity Monitor | bar: 2020-06-30 to 2020-08-14
6.6.3.1 | Real-Time Energy Imbalance Payment or Charge at a Resource Node | bar: 2020-06-30 to 2020-08-14
6.6.5.1 | Resource Base Point Deviation Charge | bar: 2020-06-30 to 2020-08-14
6.6.5.1.1.3 | Controllable Load Resource Base Point Deviation Charge for Over Consumption | bar: 2020-06-30 to 2020-08-14
6.6.5.1.1.4 | Controllable Load Resource Base Point Deviation Charge for Under Consumption | bar: 2020-06-30 to 2020-08-14
6.6.5.5 | Energy Storage Resource Base Point Deviation Charge for Over Performance | bar: 2020-06-30 to 2020-08-14
6.6.5.5.1 | Energy Storage Resource Base Point Deviation Charge for Under Performance | bar: 2020-06-30 to 2020-08-14
6.6.5.3 | Resources Exempt from Deviation Charges | bar: 2020-06-30 to 2020-08-14
6.6.7.1 | Voltage Support Service Payments | bar: 2020-06-30 to 2020-08-14
7.9.1.3 | Minimum and Maximum Resource Prices | bar: 2020-06-30 to 2020-08-14
8.1.1.2.1.1 | Regulation Service Qualification | bar: 2020-06-12 to 2020-07-23
8.1.1.2.1.2 | Responsive Reserve Service Qualification | bar: 2020-06-12 to 2020-07-23
8.1.1.4.1 | Regulation Service and Generation Resource/Controllable Load Resource Energy Deployment Performance | bar: 2020-06-12 to 2020-07-23
Note on E14: Sandip: may be best if discussed in the context of NPRR 1015.