## Slide 1
Impact of New Equipment Outages on DAM
Anson Lee
Market Analysis and Validation
CMWG
July 13th, 2020

## Slide 2: Overview
All the transmission outages relating to New Equipment Energization (NEE)
  Study Period: January 2017 and June 2020
  Represents 10% of all Transmission outages (Second largest category after “Other”)
There are 7,797 distinct NEE transmission outages or 48,137 NEE-related transmission outage records (i.e. status update, start/end time update and etc.) during the study period
Grouped Outage (3,090 or 39.63%)
  Grouped Outage could involve up to 58 equipment
Each outage could have several extensions
  Number of extensions ranged from 1 to 21
    65.23% (or 5,086) had no extension
    34.77% (or 2,711) had at least one extension
    18.6 % (or 1450) had at least two extensions
    10.25 % (or 799) had at least three extensions
Notes: Outages without actual start date or actual end date are excluded (5%)

## Slide 3: Methodology
Data
  New Equipment Energization Transmission Outages
  Outages which are either cancelled, withdrawn or rejected are not included
  Outages involving multiple equipment are treated as one if submitted together
  Outage extensions submitted on the same day are consolidated
    Use 10AM as date break instead of midnight.
Assumption
  Actual end date is the exact time when the equipment came into service
Three scenarios
  Outage extensions submitted after DAM
  Outages completed earlier than expected in DAM
  Outages completed later than expected in DAM
6/1/2020 10AM
6/2/2020 10AM
6/3/2020 10AM
1 hr
2 hr
3 hr
1 hr
3 hr
6 hr
4 hr
Extension
Early
Late

## Slide 4: Analysis – Outage Extension
Outage extension submitted after DAM
  If an outage extension is submitted after DAM deadline at 10AM, the topological change will not be modeled in DAM.
Example: New equipment Outage A was scheduled to be completed on 6/1/2020 17:00. An outage extension was submitted on 6/1/2020 13:00 to extend outage to 6/2/2020 20:00.
Percentage of New Equipment Outages with extension
  Extension submitted after DAM deadline at 10AM
    152 (2.46%) out of 6,247 outage extensions
    Extended duration ranged from 7 minute to 18.56 days
      Median is 2.88 hours
DAM
5/31/2020
10:00
Original Planned End Date
6/1/2020 17:00
New Planned End Date
6/2/2020 20:00
Update time
5/31/2020 13:00
6/2/2020 00:00
Outage Not modelled in DAM

## Slide 5: Comparison of Extended Outage Duration
Longer term extension tends to be submitted ahead of time, while
extension submitted after DAM deadline is mostly
for shorter term extension (less than 12 hours)
Notes: The difference is statistically significant.

## Slide 6: Analysis – Outage Early Completion
Outage completed earlier than expected in DAM
  If an outage is completed earlier than the planned end date seen in DAM, it will cause topological difference between DAM and Real-Time.
Example: New equipment Outage C was scheduled to be completed on 6/1/2020 18:00. However, the outage work completed early on 6/1/2020 00:00.
Percentage of New Equipment Outages with early completion
  Outage completed earlier than expected in DAM*
    860 (11 %) out of 7,797 outages
      385 (44.77 %) had prior extension(s)*
    Shortened duration ranged from 1 minute to 168 days**
    Median is 2.49 hours
  * With respect to the outage snapshot used for DAM for the operating day (i.e. 6/1/2020)
  ** Note: In this specific case, it was found that a new outage was submitted for the new equipment.
DAM
5/31/2020
10:00
Original Planned End Date
6/1/2020 18:00
Outage Completed
6/1/2020 00:00
Outage still modelled in DAM

## Slide 7: Analysis – Outage Late Completion
Outage completed later than expected in DAM
  If an outage is completed later than the planned end date seen in DAM, it will cause topological difference between DAM and Real-Time.
Example: New equipment Outage B was scheduled to be completed on 6/1/2020 18:00. However, the outage work was not completed until 6/1/2020 21:00.
Percentage of New Equipment Outages with early completion
  Outage completed later than expected in DAM*
    943 (12 %) out of 7,797 outages
      509 (53.98 %) had prior extension(s)*
    Delayed duration ranged from 1 minute to 11 hours**
    Median is 1.15 hours
  * With respect to the outage snapshot used for DAM for the operating day (i.e. 6/1/2020)
  ** Note: Real impact on DAM is between 0 to 24 hours
DAM
5/31/2020
10:00
Original Planned End Date
6/1/2020 18:00
Outage Completed
6/1/2020 21:00
Outage Not modelled in DAM

## Slide 8: Shortened vs Delayed Duration
Completed Early
Completed Later
On Time
Median: 2.49 hours
Median: 1.15 hours

## Slide 9: DAM/RT NEE Outage Model Consistency

## Slide 10: Questions?