## Sheet1
TX SET Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2020-06-17
Agenda Item: | Decision / Resolution | Action Items :
May Meeting Notes | The notes were approved with minor changes. | The Texas SET vice Chair will have the final version posted to the May meeting page key documents.
The Texas SET Chair provided the Retail Market Subcommittee (RMS) Update on the following topics.
All Change Controls submitted were approved Except 800 and 810. Texas SET to review at June Meeting. | See the results of the Change Control Call below.
ERCOT Discussion Items
Flight Update | ERCOT Staff presented this update.
Projects | • ERCOT will incorporate the project changes into the Retail Market Test Environment (RMTE) the weekend of July 25th. • ERCOT will request that the trading partners exchange one large (more for the TDSPs) and one small file to test the changes. • ERCOT will be sending a market notice next week about this change; then send follow up notices as a reminder to the Market.
PR288-02 NAESB Application Tech Refresh Business driver is security—Possible testing specs collaboration with TDTMS | It was noted that there were no changes since the last update.
PR288-01 EDI Map and Translator Replacement Texas SET EDI Questions—Living Document Discussion | Texas SET agreed to the changes as written. | ERCOT will submit the Change Control and conduct an emergency Texas SET Change Control Call on June 25; then to RMS in July as a Version 4.0A change.
Change Control Call at 10 AM | Change Controls on the ERCOT Website. http://www.ercot.com/mktrules/issues/txsetcc
Change Control 2013-800, Muni-Coop guidelines are different than the IOU guidelines for meter removal | Texas SET agreed to request that RMS approve to have this Change Control withdrawn since the changes were incorporated into Change Control 810.
Change Control 2020-810: Clarifies how the TDSP utilize the BGN08 and REF~5H segments within the 650_04 when terminating or suspending service at a premise. | Texas SET agreed to request that RMS approve this change control.
RMS Assignments this month
Change Controls 800 and 810 remanded back see RMS update and Change Control Call above | See the Change Control Call above for details
COVID ERP Process Discussion (10:30) | The RMS vice Chair reviewed the process that was discussed on a separate call that related to customers that were dropped off the ERP list in error by the state and how they will be re-instated. o The TDSPs requested that Competitive Retailers (CRs) send separate “Add” or “Previous” MarkeTrak Issues to re-instate those customers for the appropriate scenario; then put in comments that the MarkeTrak issue is for those customers that need to be re-instated.
Issues-- | Issues on the ERCOT Website http://www.ercot.com/mktrules/issues/txset
Issue 020-I150 Need to review the use of the A13 Reject Code | o TXU Energy provided an update on a previous conference call that discussed the codes. o ERCOT was asked to provide statistics on uses that will be provided at a future meeting. o Texas SET will review and determine if further work is needed.
Discussion Items
Texas SET Enhancement Matrix The Texas SET Chair conducted a discussion on the Texas SET Version 5.0 Release and reviewed those changes slated for Texas SET Version 4.0A Release. | o Timeline Review—The Texas SET Chair noted that the RMS Leadership requested guidance from ERCOT. • It was noted that Texas SET V5.0 changes will need to be finished by October or November of 2020. • ERCOT stated that it would best be slated for the end of 2021 or early 2022. o Workbook updates—Texas SET reviewed each change and made updates to the language as needed for the following topics. • Change Controls needed • Retail Market Guide Revision Requests (RMGRRs) needed • Nodal Protocols Revision Requests (NPRRs) needed
Other Business | No Other Business topics were discussed.
Parking Lot
MISP Workshop Action Items • Add a MISP definition in RMG (RMGRR) | Still on Hold
Next Meeting--WebEx Only | Emergency Change Control Call 6/25/2020
Regular meeting 7/22/2020
Attendees F-T-F
Attendees Webex
Kyles Patrick NRG | Pam Williams ePsolutions
Diana Rehfeldt TNMP | Frank Nunes ECInfoSystems
Jim Lee AEP | Abhinav Chada Epsolutions
Stephen Wilson TXU Energy | Mike Carson
Kathy Scott Centerpoint Energy | Paula Shadle Nueces Electric
Sam Pak ONCOR | Barbara White Ambit Energy
Deb Belin MarketWise | Nancy Nyan
Jordon Troublefield ERCOT | Sheri Wiegand
Kathryn Thurman ERCOT
Paul Yockey ERCOT
Dave Michelsen ERCOT
Kim Wall Hansen Technologies
Tracie Gaetano Accent Energy
Eric Blakey Just Energy
Debra Rabaeo