## Slide 1: ERCOT Model Requirement Impacts (PGR0075)
July 28, 2020

## Slide 2: Overview
PGRR0075 (effective May 1, 2020) adds a requirement for generators to provide model quality test results that demonstrate appropriate performance for submitted dynamic models.
    Dynamic model data should be provided using appropriate dynamic model templates
    Dynamic model data should be specific to each plant design
    Models are required to be submitted based on updated requirements for all new interconnection filings, or updates to existing interconnection filings
    Requirement partly driven by need to have reliable models, and to reduce load on TSPs/ERCOT to digest poor models that require repeat update requests.
  http://www.ercot.com/mktrules/issues/PGRR075

## Slide 3
Previous Typical Timeline (Before May 1st)
MONTH 0
M +2
M +4
M +6
M +8
M +10
M +12
M +14
M +16
M +18
M +20
M +22
M +24
M +26
M +28
M +30
M +32
M +34
1 M
5 Months
2 Months
3 Months
1 M
3 Months
3 Months
3.5 Months
1.5 M
1 M
In-Service Date
Initial Synchronization
(SGIA to ISD = 15-18 months depending on POI)
ERCOT QSA Review
Final Plant Design + Modeling
27 Months w/ 6-7 Months of Float
Full Production
Interconnection Application
Scoping Meeting, Study Agreement, and Steady State Study
SGIA Negotiation and Execution
Preliminary Collector System Modeling and Short Circuit Study
Facility Study
QSA Deadline
Reactive Study
Studies
Modeling
COD (Part 3 Approval)
~2.5 M Float
Final Short Circuit Study and Facility Study Check
Final Design Stability Study
1 M
~4 M Float

## Slide 4
New Typical Timeline (As of May 1st)
MONTH 0
M +2
M +4
M +6
M +8
M +10
M +12
M +14
M +16
M +18
M +20
M +22
M +24
M +26
M +28
M +30
M +32
M +34
3 Months
5 Months
2 Months
3 Months
1 M
1 M
In-Service Date
Initial Synchronization
(15 to 18 months depending on POI)
ERCOT QSA Review
Full Production
Interconnection Application and Preliminary Plant Modeling
Scoping Meeting, Study Agreement, and Steady State Study
SGIA Negotiation and Execution
Short Circuit Study
Facility Study
QSA Deadline
Studies
Modeling
COD (Part 3 Approval)
3 Months
3 Months
4 Months
1.5 M
Final Plant Design + Modeling + Testing
Reactive Study
Final Short Circuit Study and Facility Study Check
Final Design Stability Study
~0.5 M Float
29 Months w/ <1 Month of Float

## Slide 5: Full Interconnection Studies
Typical Study Timelines
  Steady State – 3-4 months; Prerequisite for all other studies
  Short Circuit – 2 months
  Stability – 2-3 months
  Facility – 2-3 months
  FIS timelines range from 3 to 8.5 months
  Study order and possibility of acceleration is TSP dependent, and generally unknown prior to an FIS scoping meeting
  Plant designs are typically not finalized until several months after an initial FIS filing
  Full plant dynamic models and tests are now required to schedule an FIS kickoff meeting, execute an FIS agreement, and begin a Steady State study – all processes that don’t need dynamic models
General Timelines

## Slide 6: Interconnection Agreements
PG 5.5.1(2): “Before an SGIA is signed, all studies included in the FIS scope must be completed, unless mutually agreed by the IE and the TSP. In the event the IE and the TSP agree to sign an SGIA prior to the completion of all studies included in the FIS scope, the TSP shall notify ERCOT”.
PG 5.5.1(3): “ERCOT does not participate in the IE’s and TSP’s negotiation of the SGIA”.
Most TSPs require at least a Facility Study, if not all studies to enter an SGIA
15-18 months is the typical time from SGIA execution to In-Service Date. The summer outage restriction window is a significant cause for delays and timeline risks.
General Timelines

## Slide 7: Challenges
Without the ability to submit plant-specific models in parallel to unrelated processes, projects can lose 2-3 months in terms of executing an SGIA and the POI in-service date. If summer outage restrictions overlap this delay, it can be 5-6 months and further puts a strain on commissioning plants in Q4 of a given year.
Assuming the same target QSA deadline, the amount of float in the interconnection timelines is reduced by months. This creates a significant risk of needing to synchronize in a later quarter, which further delays the COD by additional months and/or decreases float during commissioning
While selecting a final design early can relax timelines leading up to the QSA deadline, it further delays entering an SGIA and securing an ISD for the POI due to higher design overhead. It also forces projects to submit “final” designs before some aspects of development are sufficiently de-risked. These factors perpetuate a high probability of restudies and SGIA amendments that create more unnecessary work for all parties.

## Slide 8: Possible Solutions
  Full plant models and Model Quality Tests can be a prerequisite for performing any plant-specific studies (usually all except Steady State). With the transition away from embedding model files in the RARF, RIOO-IS in its current design can show what models and templates have been uploaded by an IE.
  During the initial screening of an FIS application, during an FIS kickoff, and/or in the FIS agreement it can be communicated that certain studies will not begin until plant-specific modeling requirements are met. Some TSPs don’t require an ASPEN model, let alone a tested dynamic model for the Steady State study.
  More flexibility from TSPs in entering SGIAs, E&P agreements, or ISAs earlier to give a path to a POI in-service date. Delays getting to a scoping meeting and FIS due to additional modeling requirements can be mitigated if some of the time is recovered by having more study overlap.
  TSPs having good templates for FIS agreements that allow for fast delivery of initial drafts following a scoping meeting.
  Leaner FIS scoping meetings that emphasize potential challenges posed by a project as-filed. Having more focused meetings can make it easier to find dates and times that work for all parties, and somewhat offset the delays in getting the filing marked as complete.