## Slide 1
Resource Integration Workshop
Resource Integration Topics
ERCOT
Jay Teixeira
July 28, 2020

## Slide 2: Quarterly Stability Assessment (QSA)
Planning Guide 5.9
Next Deadline for QSA
If a GINR is not included in QSA, its Initial Synchronization date will be automatically delayed to the next quarter
All-Inclusive Generation Resource Initial Synchronization Date | Last Day for an IE to meet prerequisites as listed in paragraph (4) below | Completion of Quarterly Stability Assessment
Upcoming January, February, March | Prior August 1 | End of October
Upcoming April, May, June | Prior November 1 | End of January
Upcoming July, August, September | Prior February 1 | End of April
Upcoming October, November, December | Prior May 1 | End of July

## Slide 3: Quarterly Stability Assessment (QSA)
Planning Guide 5.9, Quarterly Stability Assessment
Issue’s seen in previous QSA’s
  10 day comment period for FIS
    Needs to be complete before QSA deadline
    TSPs need to plan for it
  Dynamic Model Review
    Dependent on FIS Stability study
    Need to meet PG 6.9 15 to 30 days prior to QSA deadline
PSSE Model Quality Test Required
TSAT Model Required

## Slide 4: GINR Time Line (Fastest)

## Slide 5: Additional Discussion
For Solar Resources – what MW capacity(ies) should be submitted for study (SS & FIS) so that full installed inverter/panel capacity can be produced in off-peak hours when the lower temperatures allow higher output than on the maximum temperature day.
RE’s are reminded to submit Full Registration RARFs 30 days before deadline to provide time for corrections and feedback to minimize the risk of delays in loading the RARF data into the model to support energization. Full Registration RARFs require a registered Resource Entity to submit.

## Slide 6: Active PGRR’s
NPRR973, NOGRR196, PGRR074, RRGRR022 – Add Definitions for Generator Step-Up and Main Power Transformer - BOD Aug 11?
PGRR076 – Improvements to Generation Resource Interconnection or Change Request (GINR) Process – TAC Jul 29?

## Slide 7: Other contact information
ResourceIntegrationDepartment@ercot.com is distribution list for Resource Integration department

## Slide 8: Questions?
Thank you!