Outage Scheduler User Guide
for Qualified Scheduling Entities and 
Transmission Service Providers

Effective Date: September 30, 2017

Revision Date: August 6, 2020

Version 8.0

1.1 Purposes of the Outage Scheduler	8

1.2 Using this Guide	8

1.3 Technical Support and Contacts	9

1.4 System Requirements	9

2	Definitions	10

3	Business Rules	13

3.1 Common Rules	13

3.2 Two-Hour Rule for Revising Actual Start and Actual End	15

3.3 Planned Outage Rules	16

3.4 Maintenance Outage Rules	16

3.5 Forced Outage Rules	17

3.6 Remedial Switching Action Rules	17

3.7 Transmission Opportunity Outage Rules	17

3.8 Simple Outage Rules	17

3.9 Grouped Outage Rules	18

3.10 Recurring Outage Rules	18

3.11 Forced Extension Rules	18

3.12 Unavoidable Extension Rules	18

4	Warnings	18

4.1 Warning Conditions	18

4.3 System and Form Validation	20

5	Accessing the Outage Scheduler	20

5.1 Logging In	20

5.2 Logging Out	21

6	Outage Summary	22

6.1 Common Features and Controls	22

6.2 Show/Hide Preferences	26

6.3 Custom Filter	27

6.4 Show Actual Start and End	31

6.5 Error Handling	32

7	Common Functions Across all Outage Types	33

7.1 Using the Calendar to Enter/Update Dates	33

7.2 Selecting Resource Station, Equipment Type, and Equipment Name	34

7.2.1      Resource Outages	34

7.2.2     Select Multiple Resources	36

7.3 Derate Resources	36

7.4 Select Transmission Station, Equipment Type, and Equipment Names	37

7.5 Enter and View Notes	39

7.5.1	Requestor Notes	40

7.5.2	Remedial Action Plans, Automatic Mitigation Plans, and Remedial Action Schemes	40

7.5.3	Supporting Information	40

7.5.4	Reviewer Notes	41

7.6 Cancel an Outage	41

7.7 Withdraw an Outage	42

7.8 Reject an Outage Request	43

7.9 Copy an Outage	44

7.10 Create Grouped Outages	45

7.10.1   Adding to a Grouped Outage	45

7.10.2    Submit Actual Start and/or Actual End for the Entire Group from the Summary Screen	47

7.10.3     Submit Dates for the Entire Group from the Outage Detail Screen	48

7.10.4    From the Summary Screen, Remove one Outage from the Group by Updating the Actual Start/Actual End	48

7.10.5     From the Detail Screen, Remove one Outage from the Group by Updating Dates	49

7.10.6     Cancel the Entire Grouped Outage	49

7.10.7    Cancel an Individual Outage in the Group	51

7.11 Create a Recurring Outage	52

7.12 Submit a Forced Extension Outage	55

7.13 Submit an Unavoidable Extension	56

8	Planned Outages	57

8.1 Planned Outage Rules	58

8.2 Submit a Planned Outage Request	58

8.3 View and Update a Planned Outage	63

8.3.1     When Status is “Received at ERCOT”	63

8.3.2      When Status is “Study, Rejected or Withdrawn”	64

8.3.3     When Status is “Approved” and Outage is Not Active	64

8.3.4    When Status is “Approved” and Outage is Active	64

8.3.5      Revise a Planned Outage that has Ended	65

8.4 Rescheduled Outages	65

8.4.1	High Impact Outage and Rescheduled Outage Definitions:	65

8.4.2	High Impact Outage (HIO)/Rescheduled Outage (RO) Rules and Conventions	66

8.4.3	HIO Process Overview	67

9	Maintenance Outages	75

9.1 Maintenance Outage Rules	76

9.2 Submit Maintenance Outage Request	76

10	Forced Outages	78

10.1 Forced Outage Rules	78

10.2 Submit Forced Outage Request	78

11	Remedial Switching Action	80

11.1 Remedial Switching Action Rules	80

11.2 Submit Remedial Switching Action Outage Request	80

12	Simple Outages	83

12.1 Simple Outage Rules	83

12.2 Submit Simple Outage Request	83

13	Resource Opportunity Outage	86

13.1 Resource Opportunity Outage	86

13.2 View and Update a Resource Opportunity Outage	87

14	Transmission Opportunity Outages	90

14.1	Opportunity Outage Rules	90

14.2	Submit Transmission Opportunity Outage Request	91

14.3	View and Update an Opportunity Outage	94

14.3.1    When Status is “Received at ERCOT” pending a matching Resource Outage	94

14.3.2    When Status is “Received at ERCOT” with a matching Resource Outage	95

14.3.4    When Status is “Approved” and Outage is Not Active	97

14.3.5    When Status is “Approved” and Outage is Active	97

15	Retrieve Outage History	98

16	Printing Summary Information	99

17	Exporting Outage Data to a File	100

17.1 Export in XML format	100

17.2	Export as CSV format	102

# 1.0	Overview

## 1.1 Purposes of the Outage Scheduler

The ERCOT Outage Scheduler is a web-based database and scheduling application.  Its purposes are to:

- Allow ERCOT Market Participants to create, submit, view, and edit various types of Resource (Generation and Load) and Transmission Facility Outage requests.

- Allow ERCOT to study the impact of Outage requests and meet Outage coordination goals described in Section 3.1 of the ERCOT Nodal Protocols, Outage Coordination.

Refer to http://www.ercot.com/mktrules/nprotocols/current for the latest version of the Nodal Protocols.

## 1.2 Using this Guide

The guide provides instructions for creating, submitting, updating, and canceling submissions by providing a screenshot with instructions for performing the necessary user interactions.

The information and rules in this guide apply to all Outage types for both Transmission and Resource categories, unless otherwise noted.

- Fields in bold are required fields.

- Business rules are displayed like this:

Planned Outages must be submitted at least 3 days in advance.

Indicates Outage Scheduler screen entry and/or activity.

Indicates a keyboarding, navigation, or other tip/trick which may be used to more easily navigate the way through the Outage Scheduler.

Indicates a business rule, screen edit, or other information that applies to the Outage Scheduler.

- Data on screenshots is mock data. The fields displayed are accurate, but dates, Resources, and company names are not accurate.

This guide describes how to schedule Resource and Transmission Outages using the Outage Scheduler user interface for the following Outage types:

- Planned Outages

  - Rescheduled Outages

- Maintenance Outages (Levels 1, 2 & 3)

- Forced Outages

- Remedial Switching Actions

- Opportunity Outages

- Simple Outages

Additionally, users will learn how to:

- Copy Outages

- Create Recurring planned Outages

- Create and edit grouped Outages

- Extend Outages

- Cancel Outages

- Revise Outages in Received at ERCOT status

- Retrieve Outage data and history

## 1.3 Technical Support and Contacts

For all technical support issues, contact the ERCOT HelpDesk at (512) 248-6800.

## 1.4 System Requirements

The ERCOT Outage Scheduler has minimal hardware and operating system requirements.  Aside from a suitable browser and a security certificate that will be loaded by a system administrator, no additional software needs to be installed on a user’s computer.

| Specification | Required |
| --- | --- |
| Internet Browser | Internet Explorer 11.0 |
| Operating System | Windows 7+ |

# 2	Definitions

The information and rules in this section apply to all Outage types for both Transmission and Resource categories, unless otherwise noted.

Active Outages: Those Outages that have a Planned Start of today or earlier, no Actual End value, and a Planned End value that is future of the current date/time.

Entered Not Yet Submitted (ENYS):  Interim state awaiting input from Requestors.  ENYS applies to the following Outage types:

- Rescheduled Outages – Planned-Approved High Impact Outage being converted to a Rescheduled Outage.  Requestor must submit revised Planned Start and/or Planned End information for ERCOT evaluation and approval.

- Resource Opportunity Outage – Requestor must select either “Yes” to take the Opportunity Outage or “No” to reject it.

- Transmission Opportunity Outage – Requestor must submit Planned Start and Planned End information for ERCOT evaluation and approval.

Forced Outage:  An Outage initiated by protective relay or manually, in response to an observation by personnel that the condition of equipment could lead to an event, or potential event that poses a threat to people, equipment, or public safety.

For a Generation Resource, an Outage that requires immediate removal, either through controlled or uncontrolled actions, of all or a portion of the capacity of the Resource from service through automated or manual means. This type of Outage usually results from immediate mechanical/electrical/hydraulic control system trips and operator-initiated actions in response to a Resource’s condition.

Forced Extension:  A Forced Outage that cannot be returned to its normal status by the Planned End Date is a Forced Extension.

- Forced Extensions may be extended more than once but cannot exceed 1 year in duration from the original Outage start date.

- New Planned End may be submitted for up to 2 hours past the Planned End.

- New Planned End may be submitted multiple times – if within the 2-hour limit.

- After Planned End plus 2 hours – a New Forced Outage must be submitted.

Grouped Outages:  Multiple Outages that share the same start and end date/times. QSEs and TSPs may use grouped Outages for all Outage types except that Planned Outages cannot use the Group and Recurring features for the same Outage.

High Impact Outage (HIO):  A Planned Outage or Rescheduled Outage that interrupts flow on a High Impact Transmission Element (HITE).

Maintenance Outage:  An Outage initiated manually to remove equipment from service to perform work on components that could be postponed briefly but that is required to prevent a potential Forced Outage and that cannot be postponed until the next Planned Outage. Maintenance Outages are classified as follows:

- Maintenance Level 1: Equipment that must be removed from service within 24 hours to prevent a forced Outage.

Maintenance Level 2: Equipment that must be removed from service within 7 days to prevent a forced Outage.

Maintenance Level 3: Equipment that must be removed from service within 30 days to prevent a forced Outage.

Opportunity Outage: An Opportunity Outage is a special category of Planned Outage.

- A Resource Opportunity Outage (ROO) occurs when a specific Resource experiences a Forced Outage and the Resource has been previously Accepted or Approved for a Planned Outage during the next eight days.

- A Transmission Opportunity Outage (TOO) is a two-stage process:

  - The first stage involves submitting the initial request for a TOO with its duration, set of designated Resources and the desired transmission facilities.

  - The second stage involves the actual approval and implementation of a TOO if a Forced Outage occurs on the designated Resource.

Outage:  The condition of a Transmission Facility, or a portion of a Facility, or Generation Resource that is part of the ERCOT Transmission Grid and defined in the Network Operations Model that has been removed from its normal service, excluding the operations of Transmission Facilities associated with the start-up and shutdown of Generation Resources.

Planned Outage: An Outage that is planned and scheduled in advance with ERCOT, other than a Maintenance Outage or Opportunity Outage.

Recurring Outage: A Recurring Outage is a type of planned Transmission or Resource Outage, where the equipment will be taken out repeatedly, resulting in multiple Outages. The duration of a Recurring Outage must be less than 24 hours. The maximum number of recurrences is 50 and the number of days between recurrences cannot exceed 30.  No Groups in Recurring Outages.

Remedial Switching Action: A type of Forced Outage submitted for near Real-Time switching devices that will be opened to relieve or prevent an overload condition. The Outage must start within 3 days, have a maximum restoration time of 4 hours, and cannot exceed 72 hours in duration.

Rescheduled Outage: An Outage on a High Impact Transmission Element (HITE) that was originally submitted as a Planned Outage with more than 90-days’ notice and Approved, but is then rescheduled due to withdrawal of approval by ERCOT of the original Planned Outage or subsequent Rescheduled Outage(s).

Resource: The term is used to refer to both a Generation Resource and a Load Resource.

Within the category of Resource Outages, there are two types of Resources, or units:

- Non-contracted units – rules for these Resources fall under the heading “Resources.”

- Contracted units – rules for these Resources fall under the heading “Reliability Resources.” Reliability Resources include:

  - Reliability Must Run units

  - Black Start units

- Generation Resource

A generator capable of providing energy or Ancillary Service to the ERCOT System and is registered with ERCOT as a Generation Resource.

- Load Resource

A Load capable of providing Ancillary Service to the ERCOT System and/or energy in the form of Demand response and registered with ERCOT as a Load Resource.

- Black Start Resource

A Generation Resource under contract with ERCOT to provide Black Start Service.

- Intermittent Renewable Resource (IRR)

A Generation Resource that can only produce energy from variable, uncontrollable Resources, such as wind, solar, or run-of-the-river hydroelectricity.

- PhotoVoltaic Generation Resource (PVGR)
A Generation Resource that is powered by PhotoVoltaic (PV) equipment exposed to light.

- Quick Start Generation Resource (QSGR)
A Generation Resource that, in its cold-temperature state, can come On-Line within 10 minutes of receiving ERCOT notice.

- Switchable Generation Resource
A Generation Resource that can be connected to either the ERCOT Transmission Grid or a Non-ERCOT Control Area.

- Wind-powered Generation Resource (WGR)

A Generation Resource that is powered by wind.

Simple Outage: A Planned Outage or Maintenance Outage of any Transmission Element in the Network Operations Model such that when the Transmission Element is removed from its normal service, absent a Forced Outage of other Transmission Elements, the Outage does not cause a topology change in the LMP calculation and thus cannot cause any LMPs to change with or without the Transmission Element that is suffering the Outage.

Supporting Information:  Provides an explanation of how an Outage qualifies as a Forced Outage, Force Extended Outage, Unavoidable Extension Outage, or Remedial Switching Action

Transmission Element: A physical Transmission Facility that is either an Electrical Bus, line, transformer, generator, Load, breaker, switch, capacitor, reactor, phase shifter, or other similar device that is part of the ERCOT Transmission Grid and defined in the ERCOT Network Operations Model.

- High Impact Transmission Element (HITE)
A Transmission Element that may, in certain conditions, result in high congestion risk when taken out of service and that is identified as further described in Section 3.1.8, High Impact Transmission Element (HITE) Identification.

Transmission Facilities

- Power lines, substations, and associated facilities, operated at 60 kV or above, including radial lines operated at or above 60 kV

- Substation facilities on the high-voltage side of the transformer, in a substation where power is transformed from a voltage higher than 60 kV to a voltage lower than 60 kV or is transformed from a voltage lower than 60 kV to a voltage higher than 60 kV

- The direct current interconnections between ERCOT and the Southwest Power Pool or Commission Federal de Electricidad (CFE)

Unavoidable Extension: Unavoidable extensions may only be created for active Accepted or Approved, Planned, Maintenance, or Simple Outages.  An Unavoidable Extension occurs when a Planned, Maintenance, or Simple Outage is not completed within the original timeframe.

- Unavoidable Extensions may be extended more than once but cannot exceed 1 year in duration from the original Outage start date.

- New Planned End may be submitted for up to 2 hours past the Planned End.

- New Planned End may be submitted multiple times – if within the 2-hour limit.

- After Planned End plus 2 hours – a New Forced Outage must be submitted.

# 3	Business Rules

## 3.1 Common Rules

Transmission Service Providers (TSPs) may only request Outages on transmission facilities (breakers, switches, lines, transformers, and loads).

- TSPs can view all Transmission and Resource Outages.

- A TSP may create a Transmission Outage for any other TSP and on any facility or transmission element defined in the current Network Operations Model.

- A TSP cannot create a Resource Outage.

- A TSP cannot change the name of the Requesting Company. That is tied to the digital certificate.

- A TSP cannot edit an Outage submitted by another Requesting Company.

Qualified Scheduling Entities (QSEs) may only schedule and view Outages for the Resources and Transmission Facilities which they operate.

- Must log in separately for sub-QSEs.

- QSEs cannot view Transmission Outages in the Outage Scheduler application which have been submitted by TSPs.

- QSEs cannot submit Transmission and Resource Outages in a single request due to differing Protocol Requirements.

| Outage Type | Transmission | Resource |
| --- | --- | --- |
| Planned |  |  |
| Rescheduled |  |  |
| Maintenance |  |  |
| Forced |  |  |
| Opportunity |  |  |
| Remedial Switching Action |  |  |
| Simple |  |  |
| Forced Extension |  |  |
| Unavoidable Extension |  |  |

- Actual Start must be earlier than or equal to the current time, and can be no earlier than 2 hours prior to the Planned Start date/time.

- Actual End must be later than Actual Start and earlier than or equal to the current time.  It can be no later than 2 hours after the Planned End date/time.

- Actual End cannot be entered until after the Actual Start is submitted successfully.

- Earliest Start must be less than or equal to Planned Start.

- Planned End must be greater than Planned Start.

- Latest End must be greater than or equal to Planned End.

- New Transmission Outages cannot overlap with existing Transmission Outages ( any that are not Canceled, Rejected, or Withdrawn) where the date/time and equipment overlap.  Derated Resource Outages can overlap.

- Emergency Restoration cannot be longer than the Outage duration.

- Outage is not considered active once an Actual End time has been entered or the Planned End time has passed with no Actual End time entered, whichever comes first.

- See also Two-hour Rule for Revising Actual Start and Actual End.

## 3.2 Two-Hour Rule for Revising Actual Start and Actual End

These rules apply to all Outage types for both transmission and Resources, except for Forced Outages. Rules for Forced Outages are in that section.

#### 3.2.1	Actual Start

- The Actual Start field will not appear until after the Outage is Approved/Accepted.

- The Actual Start Date/Time may be changed for up to 2 hours after it is submitted.

- The new Actual Start must be earlier than the old Actual Start.

- Requestors may ask ERCOT to delete the Actual Start and Actual End Date/Times. If the Actual Start or Actual End Date/Time is deleted, it can be entered again.  The 2-hour editing period also begins again.

Tip: When the 2-hour window expires, the Actual Start field appears editable.  If Requestors try to update it, the system displays an error message.

Once Requestors enter an Actual End Date/Time, the Actual Start field changes to read-only. This happens even if the 2-hour editing window for Actual Start is still open.

Tip: On Forced Extensions and Unavoidable Extensions, entering a New Planned End date makes the Actual Start field appear editable.  If Requestors try to update it, the system displays an error message.

#### 3.2.2	Actual End

- The Actual End field will not appear until after the Actual Start has been submitted.

- An Actual End Date/Time may be changed for 2 hours from the time it was first submitted.

- The new Actual End must be earlier than the old Actual End.

- If Requestors ask ERCOT to remove the Actual End, they may begin again.

- Tip: When the 2-hour window expires, the Actual End field appears editable. If Requestors try to update it, the system displays an error message.

The Actual End field never displays as read-only.

#### 3.2.3  2-Hour Rule for Submitting a New Planned End

- New Planned End may be submitted for up to 2 hours past the Planned End

- New Planned End may be submitted multiple times – if within the 2-hour limit

- After Planned End plus 2 hours – a New Forced Outage must be submitted

- Applies to Unavoidable Extensions and Forced Extensions

## 3.3 Planned Outage Rules

- Planned Start and Earliest Start must be at least 3 days from current date

- All Common Rules apply

## 3.4 Maintenance Outage Rules

- The Maintenance Outage Level cannot be changed once an Outage is submitted/created.  If the Maintenance Outage Level needs to be revised, the Outage must be canceled and re-submitted.

- If the Planned Start for a Maintenance Outage is changed when the Outage status is “Approved” but the Outage is not active, the rules for enforcing Maintenance Outage Levels still apply.

- When a Maintenance Outage is copied, the Outage Type is populated with the Maintenance Level of the original Outage, and the new Maintenance Level must be designated by the user. Validation is the same as entering a new Outage if it is different.

- For M1 Outages, Planned Start date and time must be equal to or greater than current date and time and less than current date/time plus 24 hours.

- For M2 Outages, Planned Start date must be equal to or greater than current date and time and less than current date plus 7 days.

- For M3 Outages, Planned Start date must be equal to or greater than current date and time and less than current date plus 30 days.

- All Common Rules apply.

## 3.5 Forced Outage Rules

- Actual Start may be earlier than the current time.

- Actual Start must be the time the Forced Outage occurred.

- Supporting information is required.

- All Common Rules apply.

## 3.6 Remedial Switching Action Rules

- Planned Start must be greater than or equal to the current time and must be within 3 days of current date.

- Planned End cannot cause the Outage duration to exceed 72 hours.

- Emergency Restoration cannot exceed 4 hours.

- Supporting information is required.

- All Common Rules apply.

## 3.7 Transmission Opportunity Outage Rules

- The Opportunity Window End date is automatically set for 90 days after the Request Date.

- The Opportunity Outage will automatically be removed from the Outage Summary on the Opportunity Window End Date.

- All Common Rules apply.

## 3.8 Simple Outage Rules

- Should be submitted at least 1 day in advance.

- Maximum restoration time of 1 hour.

- Cannot exceed 12 hours in duration.

- All Common Rules apply.

## 3.9 Grouped Outage Rules

- Transmission and Resources Outages may both use grouped Outages for all Outage types except that Planned Outages cannot use the Group and Recurring features for the same Outage.

## 3.10 Recurring Outage Rules

- The duration of a Recurring Outage must be less than 24 hours.

- The maximum number of recurrences is 50.

- The maximum number of days between recurrences is 30.

- No Group Outages – single pieces of equipment only.

## 3.11 Forced Extension Rules

- Supporting information is required.

- Forced Extensions may not be created as new Outages. They must be created from an existing Forced Outage.

- Forced Extensions may be extended more than one time but cannot exceed 1 year in duration from the original Outage start date.

- Forced Extensions may be extended multiple times after the Planned End.  See Two-Hour Rule for New Planned End.

## 3.12 Unavoidable Extension Rules

- Supporting information is required.

- Unavoidable Extensions may not be created as new Outages. They must be created from an existing Planned, Maintenance, Rescheduled, or Simple Outage.

- Unavoidable Extensions may be extended more than one time but cannot exceed 1 year in duration from the original Outage start date.

- Unavoidable Extensions may be extended multiple times after the Planned End.  See Two-Hour Rule for New Planned End.

# 4	Warnings

## 4.1 Warning Conditions

When a new warning is generated, it displays on the Warnings screen. The warnings tab turns red and displays the total number of warnings. The warning also displays on the Outage Detail screen. The warnings display until Requestors enter the appropriate information to remedy the warning.

Outage Scheduler generates warnings for the following conditions:

- Current time is 30 minutes after Planned Start and no Actual Start has been entered.

- Current time is 30 minutes before Planned End and no Actual End has been entered.

- Current time is 30 minutes after Planned End and no Actual End has been entered.

- Actual End has been entered for Forced Outage, Forced Extension, Remedial Switching Action, or Unavoidable Extension and no Supporting Information has been entered.

- A Forced Outage has been submitted. (Outage details are provided.)

- A Maintenance Level 1 Outage has been submitted. (Outage details are provided.)

- Outage is late with Actual Start.

- Outage is late with Actual End.

| 4.2 Warning Corrections Warning Message | Action Required |
| --- | --- |
| Outage AEN00027691AEN00037691 is late with Actual Start. | Enter the Actual Start Date/Time. |
| Current time is 30 minutes before Planned End. | Enter the Actual End Date/Time. |
| Outage AEN00037691 is late with Actual End. | Enter Actual End Date/Time. |
| Supporting information is required for (Forced Outages, Forced Extensions, Remedial Switching Actions, and Unavoidable Extensions; whichever is appropriate). Enter supporting information on the Outage Detail screen. | Enter supporting information on the Outage Detail screen. |

## 4.3 System and Form Validation

Before saving  a Transmission Outage, the system looks for an existing Transmission Outage (one that is not Canceled, Rejected, or Withdrawn) whose date/time and equipment overlaps with the potential new Outage. If it locates one, it displays a warning message with information about that Outage. Requestors may change the information on the Create Outage Request screen and re-submit or cancel that request.

# 5	Accessing the Outage Scheduler

Each Market Participant (MP) must apply for and receive a digital certificate.  The MP administrator will in turn create digital certificates for all individuals authorized to create and edit Outage data according to their roles.

Tip: Requestors may have one certificate or many. If they have more than one ERCOT-issued certificate, they must select the appropriate certificate each time they log in.

## 5.1 Logging In

Open a web browser.

Click or enter the ERCOT MIS link.

From ERCOT.com, click on Market Information System.

From the MIS Home page, select the Applications tab.

Click on Outage Scheduler.

If Requestors have multiple certificates, they are presented with a digital certificate selection dialog box.

Click an identity Name to select it.

- Click OK.

Tip: Requestors may have one certificate or many.  If they have more than one ERCOT-issued certificate, they must select the appropriate certificate each time they log in.  The Outages that display are specific to the requesting entity’s identity as specified in the digital certificate.

After approximately 12 hours of inactivity in the Outage Scheduler, the connection times out.  If this happens, close the browser and repeat the above steps.  Please note that any unsubmitted Outage requests will be lost.

## 5.2 Logging Out

To log out, close the browser window by clicking the close icon (x) in the upper right.

# 6	Outage Summary

## 6.1 Common Features and Controls

After Requestors log in, the Outage Summary page appears.  By default, all columns and rows are displayed as saved by the Requestor during a previous session.

The width of the Summary screen will automatically adjust to fit Tablets, Laptops, or Monitors. If a scroll bar is visible on the right side of the browser window, it may be used to navigate up and down on the current page of the Outage list.

The Request Date for an Outage never changes, even if the Outage is edited.

The following options are available on the Outage Summary screen:

Outage Summary 
 Displays a summary view of Outages. This is the default view.

- Create New Outage

- Clicking this tab brings up the Create Outage Request menu.

- TSPs menu allows the submittal of Transmission Outages only.

- QSEs menu allows the submittal of both Resource and Transmission Outages for the equipment that they operate.

- Warnings 
Selecting this tab refreshes the screen to display warning messages. See Warnings.

- Expand/Collapse Grouped Outages Column

- Clicking on the +/- sign at the top of the column Expands/Collapses all Grouped Outages.

- Clicking on the +/- in front of a Grouped Outage Expands/Collapses the selected Group only.

- When using the Custom Filter, the Expand/Collapse Group feature works for the following conditions:Effective From/Effective To date plus Requesting Company and Operating Company

- Request From/Request To date plus Requesting Company and Operating Company

- If using Effective From/Effective To and Request From/Request To at the same time, the date ranges should be equal to each other

- Expand/Collapse feature is not available when searching by Outage ID, Group Name, Station, Outage Type, or Nature of Work

- Select and view detailed Outages

- Single-clicking on any row highlights the row

- Double-clicking on any row opens the Outage Detail screen

- Show Actual Start & End 
Checking this box refreshes the screen to display entry fields that allow a Requestor to submit Actual Start or Actual End dates/times on the Summary screen.  See Show Actual Start & End.

- View

- Allows Requestor to view 25, 50, 100, or 200 rows of Outage data

- Outages: Show Resource and/or Transmission

- Checking these boxes and then clicking on the GO box will set the default to always show Resource Outages and/or Transmission Outages.

Outages displayed in the summary are based on the qualifications set in the requestor’s digital certificate.

- Hide: Actual Ends and Canceled

- Checking the Actual Ends box will remove from the Summary view all Completed Outages with an Actual End time.

- Checking the Canceled box will remove all Canceled Outages from the Summary view.

- Selecting GO will retain the desired default settings between logins.

- Completed and Canceled Outages are removed from the Summary database at 0001 hours the day following the Outages Planned End date/time.

- Show/Hide Preferences 
Clicking this link allows Requestors to change the way columns and rows are displayed in the Outage summary view. See Show/Hide Columns

- Print Summary Information 
Allows Requestors to print the number of Total Records in the current Summary.

- Tip: Check the number of Total Records prior to printing.

- Export CSV file 
Allows Requestors to export, view. and filter in CSV format the number of Total Records in the current Summary.

- Export XML file
Allows Requestor to export and view in .xml format the Total Number of Records in the current summary.

- Pagination navigation 
Allows Requestor to navigate to additional pages of the Outage summary.

- Refresh button   
Allows Requestor to manually refresh the screen.

- Clicking on the Refresh button periodically will refresh the Outage Summary data and reset the 12-hour automatic timeout feature.

- Show Search/Hide Search 
Clicking this link refreshes the screen to display or not display the custom filter table. The custom filter allows Requestors to filter the Outage summary information.  See Show/Hide Search.

- When the Custom Filter is applied, a link displays next to the Custom Filter button to return to the default settings.

- Sort 
Columns may be sorted in ascending and descending order by clicking on the column heading.  All other columns will resort based on the column selected.

- To sort the results by a specific column in descending order, click the column heading. Clicking the arrow in the column heading reverses the sort order. The default sort order is by Request Date, from oldest to newest.

Tip: For multiple levels of sorting, export the Outage list data using the Export.csv feature and work with it in a spreadsheet.

High Impact Outage (HIO) columns
A “Y” in the High Impact Outage columns on the right edge of the Summary screen indicates the following:

- HIO column – The Outage has elements which are on the High Impact Transmission Element list.

- HIO>90 column – The Outage was submitter greater than 90 days prior to the Planned Start.

For High Impact Outages, if the Outage does not have elements on the High Impact Transmission Element (HITE) list and/or was not submitted greater than 90 days in advance, “N” will not be displayed.  Outages qualifying for Rescheduling will have a “Y” in both columns, with the following exception:

- For collapsed Group Outages, a “Y” will not be displayed in the HIO column if the first element in the Group is not on the HITE list.

## 6.2 Show/Hide Preferences

The Show/Hide Preference window displays when Requestors click the Show/Hide Preferences link.

Select the columns or rows of information to show or hide on the Outage Summary:

- Check All Outages to select or de-select all column headings in the first column

- Check All Transmission-Specific to select or de-select all column headings in the second column.

- Check All Resource-Specific to select or de-select the HSL and/or LSL columns.

- Check Resource and/or Transmission to display one or both of these Outage categories.

Selecting or de-selecting Resource or Transmission will show or hide rows of data.

- Hide:

  - Check Completed to hide Outages for which an Actual End has been submitted.

  - Check Canceled to hide Canceled Outages.

Completed and Cancelled Outages are removed from the Summary at 0001 Hours on the day following the Outages Planned End date.

- Check individual fields in the lists to select or de-select desired columns or rows.

Click Save & Apply. The screen closes to display the selected columns.

Click Close to exit the screen without Saving.

- Saved Settings are maintained between sessions.

## 6.3 Custom Filter

The custom filter feature allows a Requestor to filter the Outage Summary information.

To display the custom filter:

Select Show Search from the Outage Summary.  The custom filter will appear on the left-hand side of the Summary screen.  The Summary screen width will also resize to not hide any column data.

Tip: The Custom Filter feature can be displayed or hidden by selecting Hide Search or Show Search.

The following options are available on the Custom Filter selection screens:

- TSPs have the ability to select up to five Operating Companies and/or Requesting Companies to include in the search parameters.  If no Operating Companies or Requesting Companies are selected, the search will return records for all Operating Companies and Requesting Companies based on other search criteria selected (i.e., effective dates, etc.).

- TSPs may view Outages submitted by all Resource and Transmission companies.

Requests for large amounts of data could take several minutes and may return as many as 7,000 records.

- For QSEs, the records will default to the Operating Company and Requesting Company specified in the digital certificate.

- QSEs may only view the transmission facilities and Resources associated with the digital certificate being used.

Note:  Single or multiple search criteria may be used based on the search criteria as follows.

Effective Date From is a date/calendar field that returns Outages with a Planned End Date greater than the value shown. The default time is 00:00 on the current day.

Effective DateTo is a date/calendar field that returns Outages with a Planned Start Date less than the value shown. The default time is 00:00 of the following day.

Outage ID is a text field that returns the Outage that matches the value shown.

Requires the full Outage ID alpha-numeric (i.e., ABCD0001234) and is case-sensitive.

Group Name is a text field that returns Outages that match the value shown.

Requires the full Group Name and is case-sensitive.

Category allows for the selection of Transmission or Resource or Both.  Category defaults to Both.

- Outage Status allows for the selection of multiple values from the drop-down.

- Hold down the Ctrl button while clicking to select multiple Outages Status types.  No selection returns all Outage Status types.

Requesting Company allows for the selection of multiple values from the drop-down.  Requestors may select up to 5 entities by checking  the desired Companies.

Operating Company allows for the selection of multiple values from the drop-down. Requestors may select up to 5 entities by checking  the desired Companies.

Station allows for the selection of multiple values from the drop-down. Use the Control key to select up to 15 Stations.

Equipment Type allows for the selection of multiple values from the drop-down.  Use the Control key to select up to 15 types of Equipment.

- The Equipment Types vary based on Outage Category (Transmission or Resource).

Equipment Name allows for the selection of multiple values from the drop-down.  Requestors may select up to 15 values by holding down the Ctrl button while clicking.

- The check buttons   are used to populate the Station List, Equipment Type list, and Equipment Name list based on the entries previously selected.

Request Date From is a date/calendar field that returns Outages with a Request Date greater than the value shown. The default time is 00:00.

Request Date To is a date/calendar field that returns Outages with a Request Date less than the value shown. The default time is 00:00.

- Outage Type allows for the selection of multiple values from the drop-down.  Selecting no Outage type will return all categories.

- Nature of Work allows for the selection of multiple Nature of Work categories from the drop-down.  Selecting no Nature of Work will return all categories.

- Click Search to apply the selected filters and re-display the Outage Summary with the filter changes applied.

- The Restore Default Setting and Reset button both restore the default settings, and continue to display the Custom Filter window.

- Tip: Typing data into a search field will narrow searches by showing matching selections.

- Tip: The Custom Filter, when applied, is maintained for the current session only.

Tip: Where lists are populated based on other selections that have been made, any change to an earlier selection causes the lists to clear. For example, if the Requestor selects an Operating Company, Station, and Equipment Type and then goes back and changes to a different Operating Company, all selection fields below Operating Company will clear.

#### 6.3.1 	TSP Outage Scheduler Filtering Rules

- TSPs can view all Transmission and Resource Outages for all Operating and Requesting Companies.

#### 6.3.2 	QSE Outage Scheduler Filtering Options

- QSEs may only filter and view Resource and Transmission Outages for the equipment in the Network Operations Model associated with the digital certificate they have signed in to.

- The Summary page is the only place where QSEs can view Outages submitted for the Resources and the Transmission facilities that they operate in one database (per digital certificate).

## 6.4 Show Actual Start and End

When the Show Actual Start & End box is checked, the Outage Summary screen refreshes to include a new row under the Outage summary row for the submittal of Actual Start and End dates/times.

- Actual Start and Actual End may only be submitted by the Requesting entity.

- Settings are maintained for the current session only.

Enter Actual Start, which is a date/calendar field. See Two-Hour Rule.

Enter Actual End, which is a date/calendar field. See Two-Hour Rule.

Check Apply to entire group/Apply to this Outage only, which are radio buttons that apply to grouped Outages. This will allow for the submittal of the Actual Start and/or Actual End and apply it to the entire group or to the break-out of a single Outage from the group, applying the Actual Start and/or Actual End to the single Outage only.

Tip: When a change is applied to a single Outage that is part of a grouped Outage, that Outage is removed from the group and no longer part of the grouped Outage.  It must be managed separately from now on.

## 6.5 Error Handling

There are two types of error messages that can display on the Summary screen:

- General exception error

- No results found as the result of a query

A General exception error displays when the system experiences a general problem, such as a communication error. The user cannot use the system until the problem is fixed.

A The query returned no results error displays when a query is performed and no results match the query. This error will also display if the default settings are in place and there are no results.

# 7	Common Functions Across all Outage Types

## 7.1 Using the Calendar to Enter/Update Dates

In the Outage Scheduler, dates can be entered directly into a field by typing, or the date can be selected using the calendar function.  To access the calendar:

Click  beside the date field.

The calendar opens.

Click any day to select it.

Click  to scroll back through the calendar 1 month at a time.

Click  to scroll forward through the calendar 1 month at a time.

Click  to scroll back through the calendar 1 year at a time.

Click  to scroll forward through the calendar 1 year at a time.

Tip: Hold the mouse button on any of the above buttons for faster selection.

Click on any of the Time parts to increase it.

Shift-Click on any of the Time parts to decrease it.

For midnight, select 00:00.

Tip: Click and drag for faster selection.

Click  to display the calendar Help.

Click  to close the calendar.

## 7.2 Selecting Resource Station, Equipment Type, and Equipment Name

All Resource Outage types require the selection of the appropriate station, Resource type, and Resource equipment name. All Outage types allow the selection of multiple pieces of equipment, creating a grouped Outage. This section explains how the system enables equipment selection.

### 7.2.1      Resource Outages

For Resource Outages:

Use the drop-downs to select a station, Resource type, and Resource.

The screen refreshes to display the selected equipment in a table.

- When the Selected Equipment table displays, the pick lists continue to display the selections.

- Resource Equipment types are:

- UN for Generating Units

- LR  for Loads acting as a Resource

The screen refreshes to display the selected Resource in a table.

- When the Selected Resource table displays, the pick lists continue to display the selections.

Resources display two required fields for HSL and LSL values.

  - Enter 0 (zero) in the HSL and LSL fields to designate that the Resource will be off-line.

  - Enter the revised HSL and LSL if the Resource is being Derated.

Depending on the Outage type and the Resource selected, derate information may be required. See the Derate Resources section.

### 7.2.2     Select Multiple Resources

Selecting multiple Resources creates a grouped Outage. Rules for grouped Outages are described in the Grouped Outages section.

To select multiple Resources, use the drop-downs to select the Station, Resource Type, and Resource name for each Resource.

- When more than one Resource has been selected, the Group Name field is required.

- Enter the Group Name associated with this grouped Outage.

## 7.3 Derate Resources

Some equipment Outages require the derating of a Resource.  Deratings may apply to Planned, Forced, and Maintenance Outages.

#### 7.3.1   Select a Resource to Derate

To select a Resource or Resources:

Use the drop-downs to select a Station, Resource Type and Resource.

The Selected Resource Table displays the Operating Company, Station, Resource Type, Resource, Seasonal HSL, HSL & LSL submittal fields, and Remove button.

Enter the appropriate numeric value for HSL During Outage for the Resource unit. It is a required field.

The HSL During Outage value is always in MW.  For example, if HSL During Outage is 600, this means the unit can generate up to 600MW during the Outage.

- HSL During Outage must not be greater than the Seasonal HSL.

Enter the LSL for the Resource. It is a required field. Enter the appropriate numeric value.

LSL cannot be greater than HSL.

Note:  All ERCOT applications will use the lowest HSL value and its associated LSL for all studies and Real-Time processes.

- QSEs are solely responsible for the submission and accuracy of all Derate Outages!

## 7.4 Select Transmission Station, Equipment Type, and Equipment Names

All Transmission Outage types require Requestors to select the appropriate station, equipment type, and equipment name. Most Outage types allow a Requestor to select multiple pieces of equipment, creating a grouped Outage. This section explains how the system enables equipment selection.

#### 7.4.1	Select a Single Piece of Equipment

To select a single piece of equipment:

Use the drop-downs to select a station, equipment type, and equipment.

The screen refreshes to display the selected equipment in a table.

- When the Selected Equipment table displays, the pick lists continue to display the selections.

Depending on the equipment selected, other information may be entered in the table:

CBs and DSCs display a drop-down list with the default value for the Outage state (open or closed). The Outage state for a CB or DSC is opposite of the normal state. A Requestor may change this setting.

XFs (transformers) and LNs (lines) display a View button that allows a Requestor to view associated equipment (See Selecting Multiple Pieces of Equipment).

- If a Requestor has made selections in this list and then changes the station or equipment type, all selections below it will clear. For example, if they have selected a station, equipment type, and equipment and then change the station, both equipment type and equipment lists will clear.

#### 7.4.2	Select Multiple Pieces of Equipment

Selecting multiple pieces of equipment creates a grouped Outage. Rules for grouped Outages are described in the Grouped Outages section.

There are two ways to select multiple pieces of equipment:

Single piece of equipment method:

- Use the drop-downs to select the operating company, station, equipment type, and equipment for each piece of equipment.

Associated equipment method:

- For transformers (XF) and lines (LN) equipment types, click the View button in the Selected Equipment table. This refreshes the screen and displays other associated equipment, if it exists.

- Check the Select box(es).

- Click Add.

When more than one piece of equipment has been selected, the Group Name field displays under the Equipment list.

- Enter the name associated with this grouped Outage. This is a required field. Group Name is not validated against and may be used multiple times.

## 7.5 Enter and View Notes

The Notes section contains enterable areas for Requestor Notes, Remedial Action Plans, Automatic Mitigation Plans, Remedial Action Schemes, and Supporting Information.

Click the arrow to expand or collapse the Notes section. The default setting is expanded.

All Note fields allow a maximum of 1,000 characters.

Once a Requestor enters a note and submits or updates the Outage, the screen refreshes to display the note with the requestor’s name and the date/time the note was entered in read-only view. An empty text field displays above the note allowing the entry of another note, if needed.

### 7.5.1	Requestor Notes

Enter the reason for the Outage in the Requestor Notes when selecting “Other” or “Unknown” as the Nature of Work. Requestors may also use the Requestor Notes area for other pertinent information about the Outage that they wish to convey.

### 7.5.2	Remedial Action Plans, Automatic Mitigation Plans, and Remedial Action Schemes

Enter information in Remedial Action Plans, Automatic Mitigation Plans and Remedial Action Schemes to notify the ERCOT reviewer if the Outage request will disable or impact Remedial Action Plans, Automatic Mitigation Plans, or Remedial Action Schemes.

Important Note: The following actions are required if Outages disable or impact a Remedial Action Plan, Automatic Mitigation Plan, or Remedial Action Scheme:

- Enter information in the Notes area shown below.

- Email notes to OPSOutageCoordination@ercot.com.

Call ERCOT Outage Coordination at 512-248-6841 if additional explanation is necessary.

### 7.5.3	Supporting Information

Supporting information is used to provide an explanation of how an Outage qualifies as a Forced Outage.

Supporting information is required for:

- Forced Outages

- Forced Extensions

- Unavoidable Extensions

- Remedial Switching Actions

- For these Outages, supporting information shows as an optional field, but this information must be entered before the Outage can be completed. If an actual end date is entered and no supporting information exists, the system sends a warning to the Requestor to notify them. See Warnings.

### 7.5.4	Reviewer Notes

ERCOT Reviewer Notes will be displayed below the Supporting Information area and are non-enterable by requestors.

- Reviewer Notes are entered by ERCOT only. If a reviewer enters a note, it will display as read-only.

## 7.6 Cancel an Outage

Requestors may cancel an Outage that meets these conditions:

- The Outage is inactive (Actual Start has not been entered).

- The status is “Received at ERCOT,” “Approved,” or “Accepted.”

Access the Outage Request screen for the Outage being canceled by double-clicking on the Outage row.

Select the appropriate cancel reason using the Outage Status drop-down.

- When canceling an Outage, select one of these eight reasons:

- Cancel – Coordinating with ERCOT

- Cancel – Reschedule date unknown

- Cancel – Reschedule within next season

- Cancel – Will not reschedule

- Cancel – Weather Conditions

- Cancel – Materials Unavailable

- Cancel – Labor/Crew Unavailable

- Cancel – Emergency Operations

Click Update.

The Update Outage Request screen is refreshed showing that the Outage is canceled.

- ERCOT can cancel a Forced Outage that was entered by mistake using Cancel-Error.

## 7.7 Withdraw an Outage

ERCOT may withdraw any Approved Outage that is active or inactive except for Forced or Forced Extension.

- When ERCOT withdraws an active Outage (Actual Start entered), the status changes to Withdrawn and all fields are read-only except for Actual End, which must be entered by the requestor.

- When ERCOT withdraws an inactive Outage (no Actual Start entered), the status changes to Withdrawn and all fields are read-only.

## 7.8 Reject an Outage Request

ERCOT can reject any Outage submitted for approval.  Outages must be “Received at ERCOT” or in “Study” status.

- ERCOT adds Reviewer Notes indicating the reason the Outage is Rejected.

## 7.9 Copy an Outage

All Outages may be copied, regardless of their type or status, for both Transmission and Resource.

Access the Outage Request screen for the Outage being copied by double-clicking on the Outage row on the Summary screen.

Click Copy Outage.

The Create Outage Request screen is refreshed and the fields are populated with data from the Outage being copied.

Update the Outage Type if it is different from the Outage being copied.

- When the Outage Type is updated, the screen refreshes and displays the fields required for the new Outage type.  The fields are pre-populated with the data from the copied Outage.

Update all other Outage information as appropriate.

Click Submit. The Outage information is validated and the screen re-displays with a confirmation message. From here, a Requestor may make another copy of the Outage.

There is no limit to the number of copied Outages.

## 7.10 Create Grouped Outages

Grouped Outages are multiple Outages that share the same start and end date/times. Transmission Outages may use the group feature for all Outage types except that Planned Outages cannot use the Group and Recurring features for the same Outage.

### 7.10.1   Adding to a Grouped Outage

Follow the instructions to Create a New Outage and the instructions below for adding multiple pieces of equipment to the Outage.

- Use the drop-downs to select:

- For Resources – Select Station, Resource Type, and Resource Name.

- For Transmission – Select Station, Equipment Type, and Equipment for each piece of equipment.

When more than one piece of equipment has been selected, the Group Name field displays under the Equipment list.

- Enter the Group Name associated with this grouped Outage.

- For transformers (XF) and lines (LN) equipment types, click View in the Selected Equipment table. This refreshes the screen and displays other associated equipment, if it exists.

- Check the Select box(es).

- Maximum pieces of equipment in a Group is 60.

- Click Add.

When all of the equipment for the group is added:

- Click Submit.

Tip: If a piece of equipment is entered in error, click the Remove icon on any row to remove the equipment on that row. The screen refreshes and the removed equipment no longer displays.

- A Group Outage can be created when initially submitted only.  An Individual Outage Request cannot be added to in order to create a Group.

### 7.10.2    Submit Actual Start and/or Actual End for the Entire Group from the Summary Screen

For grouped Outages, update the Actual Start and/or Actual End for all of the Outages in the group from the Summary screen.				Check Show Actual Start & End on the Outage Summary screen.

The Outage Summary screen refreshes to include a new row under the Outage Summary row for the entry of Actual Start and End dates/times.

Enter Actual Start for the Grouped Outage or

Enter Actual End for the Grouped Outage.

Check Apply to entire group.

Click Enter on the Outage line.

The Actual Start or Actual End date is applied to all Outages in the Group.

### 7.10.3     Submit Dates for the Entire Group from the Outage Detail Screen

Actual Start and Actual End dates/times for a Group Outage may be submitted on the Outage Detail screen.

Double-click on the Outage row from the Outage Summary to open the Outage Detail screen.

Update Date fields as required.

Click Update Group.

The new date(s) is applied to all Outages in the Group.

### 7.10.4    From the Summary Screen, Remove one Outage from the Group by Updating the Actual Start/Actual End

Check Show Actual Start & End on the Outage Summary screen.

The Outage Summary screen refreshes to include a new row under the Outage summary row for the entry of Actual Start and End dates/times.

Enter Actual Start for the Outage to be started or

Enter Actual End for the Outage to be ended.

Check Apply to this Outage only and remove from group.

The Actual Start or Actual End date is applied to the selected Outage only and the Outage is removed from the group.

Tip: When a change is applied to a single Outage that is part of a grouped Outage, that Outage is removed from the group and no longer part of the grouped Outage.  It must be managed separately from now on.  Once the Outage is broken apart from the group, it cannot be re-grouped.

### 7.10.5     From the Detail Screen, Remove one Outage from the Group by Updating Dates

Double-click on the Outage row of the individual Outage to be updated from the Outage Summary to open the Outage Detail screen.

Update Date fields, as required.

Click Update This Outage Only.

The date change(s) is applied to the selected Outage only and the Outage is removed from the group.

Tip: When a change is applied to a single Outage that is part of a grouped Outage, that Outage is removed from the group and no longer part of the grouped Outage. It must be managed separately from now on. Once the Outage is broken apart from the group, it cannot be re-grouped.

### 7.10.6     Cancel the Entire Grouped Outage

A Requestor may cancel a Grouped Outage that meets these conditions:

- The Outage is inactive. (Actual Start has not been entered.)

- The status is “Received at ERCOT,” “Approved” or “Accepted.”

Access the Outage Request screen for the Grouped Outage being canceled by double-clicking on the Outage row.

Select the appropriate cancel reason using the Outage Status drop-down.

- When canceling an Outage, select one of eight reasons:

- Cancel – Coordinating with ERCOT

- Cancel – Reschedule date unknown

- Cancel – Reschedule next season

- Cancel – Will not reschedule

- Cancel – Weather Conditions

- Cancel – Materials Unavailable

- Cancel – Labor/Crew Unavailable

- Cancel – Emergency Operations

Click Update Group.

The Update Outage Request screen is refreshed showing that the Grouped Outage is canceled. All Outages that are part of the group are canceled.

### 7.10.7    Cancel an Individual Outage in the Group

A Requestor may cancel an Individual Outage in a Grouped Outage that meets these conditions:

- The Outage is inactive. (Actual Start has not been entered).

- The status is “Received at ERCOT,” “Approved,” or “Accepted.”

From the Summary Screen, select the Outage Request to be Canceled that is Currently part of a Grouped Outage by double-clicking on the Outage ID number for that Request.

Select the appropriate cancel reason using the Outage Status drop-down.

- When canceling an Outage, select one of eight reasons:

- Cancel – Coordinating with ERCOT

- Cancel – Reschedule date unknown

- Cancel – Reschedule next season

- Cancel – Will not reschedule

- Cancel – Weather Conditions

- Cancel – Materials Unavailable

- Cancel – Labor/Crew Unavailable

- Cancel – Emergency Operations

Click Update This Outage Only.

Tip: When a change is applied to a single Outage that is part of a grouped Outage, that Outage is removed from the group and no longer part of the grouped Outage. It must be managed separately from now on.  Once the Outage is broken apart from the group, it cannot be re-grouped.

The Update Outage Request screen is refreshed showing that the selected Outage is canceled. The Outage has been removed from the group.

## 7.11 Create a Recurring Outage

Definition: A Recurring Outage is a type of Planned Transmission Outage or Planned Resource Outage where the equipment will be taken out repeatedly, resulting in multiple Outages. The duration of a Recurring Outage must be less than 24 hours. The maximum number of recurrences is 50.  There is no capability for Recurring Group Outages.

- Select Yes for Recurring Outage? to indicate that the Outage is recurring.

- Select Periodically or Weekly.

- Enter the Planned Start Date and Time in hours.

- The Planned Start Date and Time sets the date and time, which determine all of the resultant Recurring Outages based on the desired periodicity.

- For Periodic Outages - Enter Duration in hours, number of Times the Outage is to repeat, and number of Days between Outages.

- For Weekly Outages - Enter Duration in hours, the number of weeks the Outages will span, and the pattern of recurrence by selecting from the Repeats drop-down and entering the recurrence pattern.

- When defining Duration, the recurrence pattern, Number of Times, and Number of Days must be whole numbers.

- Click Generate Dates.

The Create Outage Request screen displays with the proposed dates for the Recurring Outages based on the information supplied.

To delete one or more of the proposed Outage dates:

- Click the Remove icon beside the appropriate Outage.

- To remove a recurrence entered in error, correct the inaccuracy in the designations previously selected and then click Generate Dates again to populate all recurrences.

Once the proposed Outage dates are shown correctly, continue with the Outage by entering the equipment information and continuing with Submit a Planned Outage Request.

When the Recurring Outages are successfully submitted, the system displays the Update Outage Request screen including the Recurring Outage information.

- When submiting a Recurring Outage series for Transmission equipment, the system looks for existing, Outages (not Canceled, Rejected, or Withdrawn) whose date/times and equipment match any of the potential overlapping Outages. Any potential new Outages that would conflict with an existing Outage will not be created. Even the first potential new Outage will not be created if it has a conflict, but this will not prevent the creation of any other Outages that do not have conflicts.

- The Outage ID in the General Information section shows the Outage ID for each instance of the Recurring Outage.

- Once submitted, each Outage in the recurrence becomes a separate, stand-alone Outage. Any revisions, cancellations, etc. must be applied to each Outage individually.

## 7.12 Submit a Forced Extension Outage

Definition: A Forced Extension occurs when a Forced Outage is not completed within the original timeframe and the Requestor submits the extension before the Planned End Date/Time.

- Outages may be extended more than once but cannot exceed 1 year in duration from the original Outage start date.

- New Planned End times may be submitted up to 2 hours past the initial Planned End.

- New Planned End may be submitted multiple times.

- After Planned End plus 2 hours, a new Forced Outage must be submitted.

Access the Outage Detail screen for the Outage being extended by double-clicking on the Outage row.

- Enter the New Planned End date; the Latest End date will also update.

Enter the Supporting Information.

- Supporting Information allows a maximum of 1,000 characters.

Click Update.

- Before updating the Transmission Forced Extension Outage, the system ensures that there is not an existing Outage (not Canceled, Rejected, or Withdrawn) whose date/time and equipment overlaps with the potential new Outage. If there is, a warning message with information about that Outage is displayed. A Requestor may change the information and re-submit or cancel the extension request.

When the Forced Extension Outage is successfully submitted, the system displays the Outage Detail screen and a message stating the Outage request was successfully submitted.  From this point, the Forced Extension Outage follows the same view/editing rules as its previous Outage type.

## 7.13 Submit an Unavoidable Extension

Definition:  An Unavoidable Extension occurs when a Planned, Maintenance, Simple, or Rescheduled Outage is not completed within the original timeframe and the Requestor submits the extension before the Planned End Date/Time.

Unavoidable extensions may only be created for active Accepted or Approved, Planned, Maintenance, Simple, or Rescheduled Outages.

- Outages may be extended more than once but cannot exceed 1 year in duration from the original Outage start date.

- New Planned End times may be submitted up to 2 hours past the initial Planned End.

- New Planned End may be submitted multiple times.

- After Planned End plus 2 hours, a new Forced Outage must be submitted.

Access the Outage Detail screen for the Outage being extended by double-clicking on the Outage row.

- Enter the New Planned End date.

Enter the Supporting Information.

- Supporting Information allows a maximum of 1,000 characters.

Click Update.

- Before updating the Transmission Outage, the system ensures that there is not an existing Outage (not Canceled, Rejected, or Withdrawn) whose date/time and equipment overlaps with the potential new Outage. If there is, a warning message with information about that Outage is displayed. A Requestor may change the information and re-submit or cancel the extension request.

When the Unavoidable Extension Outage is successfully submitted, the system displays the Outage Detail screen and a message stating the Outage request was successfully submitted.  From this point, the Unavoidable Extension follows the same rules as its previous Outage type.

# 8	Planned Outages

Definition: An Outage that is planned and scheduled in advance with ERCOT, other than a Maintenance Outage or Opportunity Outage.

## 8.1 Planned Outage Rules

See Planned Outage Rules in the Common Business Rules and Definitions section.

## 8.2 Submit a Planned Outage Request

From the Outage Summary screen, click Create New Outage.  The Create Outage Request screen displays in a new window.

The QSE Create New Outage menu allows the Requestor to select Resource or Transmission Outages.  The rules for submission and approval of Transmission Outages submitted by QSEs are exactly the same as the rules for Transmission Outages, which are submitted by TSPs as shown on the TSP Create New Outage menu.

The TSP Create New Outage Request menu allows the selection of Transmission Outages only.

Click Resource Planned or Transmission Planned.

The detailed Outage Request screen displays.

The General Information section displays Request Date (current date and time), Requestor, Requesting Company, Primary Phone, and Secondary Phone.  All are read-only.

Requestor, Requesting Company, Primary Phone, and Secondary Phone are all pulled from the Requestor’s digital certificate.

Update Requestor Phone and Requestor Name, if required.

Note: These are required fields and cannot be left blank.

The Requestor Phone Number and Name fields are retained from the previous login.

The Outage Data section displays Category and Request Type as read-only.

Update Recurring Outage? (defaults to No).

Using the calendar, submit the Planned Start, Earliest Start, Planned End, and Latest End dates.

Tip: When Planned Start is selected, all four date/time fields are populated.  Once that has occurred, selecting Planned Start populates Earliest Start field; selecting Planned End populates Latest End field.

Outage analysis uses the Planned Start and Planned End only.

Earliest Start and Latest End are used for alternate evaluation only.

Enter hours needed for Emergency Restoration.

- Emergency Restoration cannot be longer than the Outage duration.

Select Nature of Work.

Nature of Work is a required field.

Select the Resource or Transmission Nature of Work that most closely matches the work being performed.

If Other or Unknown is selected – use Requestor Notes area to define the work being performed.

Enter a Project Name, if desired.

Operating Company displays the company name from the digital certificate.

Select a Station from the drop-down list.

Select the Equipment or Resource Type from the drop-down list.

Transmission Outages - Outage State automatically defaults to the state opposite from the Normal State defined in the Network Operations Model.

Resource Outages – HSL and LSL are required fields.

  - An HSL and LSL of 0 (zero) designate that the Resource will be off-line.

  - Enter the appropriate HSL and LSL for Derated Resources.

Tip: A Requestor may add additional equipment and create a Grouped Outage.

Add Requestor Notes, Remedial Action Plans, Automatic Mitigation Plans, Remedial Action Schemes, and/or Supporting Information as needed. See Enter and View Notes.

Click Submit.

When the planned Outage is successfully submitted, the system displays the Update Outage Request screen with a message stating the Outage request was successfully submitted.

## 8.3 View and Update a Planned Outage

### 8.3.1     When Status is “Received at ERCOT”

When the status for a Planned Outage is Received at ERCOT, a Requestor may:

- Modify Common data

- Requestor Phone Number and Name

- Planned Start/Planned End

- Earliest Start/Earliest End

- Emergency Restoration

- Nature of Work

- HSL/LSL (Resource Outages only.)

- Notes

- Add to a Group Outage (If the outage was originally a Group.)

- Cancel Outage

### 8.3.2      When Status is “Study, Rejected or Withdrawn”

When the status for a planned Outage is Study, Rejected, or Withdrawn, Requestors are not able to make updates to the Outage. Copy the Outage, if desired.

### 8.3.3     When Status is “Approved” and Outage is Not Active

When status for a Planned Outage is “Approved” but the Outage is not active, the following changes may be made to a planned Outage:

Change the Requestor Phone number or name.

Enter the Actual Start.

Shorten Outage duration by revising Planned Start and/or Planned End.

Add notes.

Copy the Outage.

Cancel the Outage.

### 8.3.4    When Status is “Approved” and Outage is Active

When status for a planned Outage is “Approved” and the Outage is active, a Requestor may make the following changes to a planned Outage:

Change the Requestor Phone Number or Name.

Edit Actual Start.  May be changed for up to 2 hours after submittal.

Requestor may ask ERCOT to delete the Actual Start.

New Actual Start may also be edited for up to 2 hours.

Enter Actual End.

Shorten the Outage by revising the “Planned End” Date/Time.

Extend the Outage by revising New Planned End Date/Time.

Add notes.

Copy the Outage.

- New Planned End may be revised multiple times for up to 2 hours past the Planned End.

- After Planned End plus 2 hours, New Forced Outage must be submitted.

### 8.3.5      Revise a Planned Outage that has Ended

After a Planned Outage has ended, a requestor may:

- Revise the Actual End within 2 hours of entering the first Actual End.

- New Actual End must be earlier than original Actual End.

- ERCOT can delete the Actual End within 2 hours of being entered.  Once deleted, it can be submitted again, restarting the 2-hour editing window.

## 8.4 Rescheduled Outages

Rescheduled Outage (RO) – An Outage on a High Impact Transmission Element (HITE) that was originally submitted as a Planned Transmission Outage with more than 90-days’ notice and Approved, but is then rescheduled due to withdrawal of approval by ERCOT of the original Planned Outage or subsequent Rescheduled Outage(s).

### 8.4.1	High Impact Outage and Rescheduled Outage Definitions:

High Impact Outage (HIO) - A Planned Outage or Rescheduled Outage that interrupts flow on a High Impact Transmission Element (HITE).

High Impact Transmission Element (HITE) - A Transmission Element that may, in certain conditions, result in high congestion risk when taken out-of-service and that is identified as further described in Section 3.1.8, High Impact Transmission Element (HITE) Identification.

High Impact Transmission Element (HITE) List – Detailed list that is updated annually and posted on the MIS Secure at Grid>Transmission>Transmission Outages.

Major Transmission Elements (line, transformer, bus or breaker/switch combinations) may be added to or removed from the High Impact Transmission Element list based on:

- Actual Outages associated with significant congestion1 during the previous years, including:

  - Multiple Outages

  - Planned and Forced Outages

  - Outages identified by Outage Coordination studies that could have caused excessive generation re-dispatch under certain conditions.

    - Regardless of whether the Outage actually occurred or not

  - Additional elements as requested by Market Participants.

- The High Impact Transmission Elements list is comprised of:

- All of the equipment associated with each Major Transmission Element (line, transformer, bus, breaker/switch, etc.)

- Station From/To Names

- Equipment Types (CB, LN, DSC) and Name

- Normal and Outage State (Open or Closed)

- Voltage (kV)

- TEID (Transmission Element ID) and RDFID (Resource Description Framework ID)

- Congestion may occur when all of the elements under the Major Transmission Element heading are included in a Group Outage.

- Outages on individual elements that are part of a Major Transmission Element group will appear on the Summary screen and in the Equipment Selection screens with an HIO flag and will be included in the “90 Day or Less” report that is posted daily.

### 8.4.2	High Impact Outage (HIO)/Rescheduled Outage (RO) Rules and Conventions

- HIOs apply to Approved Planned Transmission Outages only.

- HIO flags on the Summary screen and Equipment Selection screens indicate:

  - HIO with a “Y” flag – Element is on the High Impact Transmission Element List.

  - HIO>90 with “Y” flag - High Impact Outage was requested greater than 90 days prior to the Planned Start.

- For High Impact Outages, “N” will not be displayed. Blank fields indicate that:

  - HIO fields – Element was not on the HITE list.

  - HIO>90 Day fields – request was 90 days or less in advance.

- For High Impact Group Outages:

  - Elements can never be added to a Group.

  - If all of the High Impact Transmission Elements are removed from a HIO Group, it no longer qualifies for Rescheduling.

- On the Outage Scheduler Summary screen – For collapsed Group Outages, a “Y” will not be displayed in the HIO column if the first transmission element chosen is not on the HITE list.

- HIO and HIO>90 Day data will be recorded in the following Outage Scheduler summaries and reports:

  - Outage Scheduler User Interface

    - Summary Page

    - Outage History

    - Print Summary

    - CSV Summary

    - XML Summary

- Market Information System (MIS)

  - Consolidated Transmission Outage report

  - High Impact Outages – Submitted “90 Days or Less” report

### 8.4.3	HIO Process Overview

#### 8.4.3.1  HIO requests submitted 90 days or less before the Planned Start:

- Outages submitted 90 days or less in advance are not eligible for Rescheduling.

- When ERCOT identifies that a HIO has been submitted with 90 days or less notice, ERCOT may coordinate with the requestor to make reasonable efforts to minimize any detected impact.

- High Impact Outages submitted with 90 days or less notice will be posted daily on the MIS Secure at Grid>Transmission>Transmission Outages.

#### 8.4.3.2   High Impact Outages submitted 90 days or less in advance MIS report

- A once-a-day Current Day Report (CDR) titled “High Impact Outages – Submitted 90 Days or Less” will be posted to the MIS Secure at Grid>Transmission>Transmission Outages shortly after midnight.

- Report will contain only the Accepted or Approved HIOs in the Outage Scheduler at 0000 hours that were submitted 90 days or less in advance of the Planned Start.

- For Group Outages, the Non-High Impact Transmission Elements will not be included in the report!

#### 8.4.3.3     HIO requests submitted greater than 90 days prior to Planned Start

    - May be eligible for rescheduling if ERCOT must consider for withdrawal.

    - ERCOT will discuss rescheduling with requestor.

    - If requestor cannot reschedule – ERCOT will withdraw.

    - If requestor can reschedule – ERCOT will convert to a Rescheduled Outage.

Requestor must submit revised Planned Start and Planned End dates and times.

    - 3-day minimum submittal period applies

After Rescheduled Dates are submitted, requestor may remove Elements and modify enterable fields.

    - ERCOT will re-evaluate and, if no security violations exist, issue approval.

    - After approval, Outage follows the same rules as a normal Planned Outage.

#### 8.4.3.4     When RO Status is “Entered Not Yet Submitted” (ENYS)

When the requestor confirms that they can reschedule the Approved Planned High Impact Transmission Outage:

- ERCOT will convert the Approved Planned High Impact Transmission Outage to a Rescheduled Outage.

- Warning Message “Outage ABCD12345678 has been rescheduled, new dates must be submitted” is issued.

- Outage status will show as Rescheduled Outage-Entered Not Yet Submitted.

- Original Request Date is retained.

Requestor must submit new Planned Start, Earliest Start, Planned End, and Latest End information. (Revised information in all four fields is required.)

    - 3-day minimum submittal period applies

    - Outage may start earlier or end later

    - New Outage duration cannot exceed the original duration

Requestor may edit the Name, Number, Emergency Restoration, and Notes fields.

Requestor may Cancel.

- Single Element Outage - Rescheduled Outage in “ENYS” status

- Group Outage - Rescheduled Outage in “ENYS” status

- When the RO status is “ENYS,” ERCOT has the capability to:

- Withdraw the Outage

- Revert the Rescheduled Outage – “ENYS” status back to a Planned Outage. “Approved” status after discussion with the requestor

- Outage cannot be reverted if edited Planned Start, Earliest Start, Planned End, or Latest End has been submitted.

- Outage can only be reverted back to Planned Outage with “Approved” status in the initial occurance of the Reschedule Outage process.

#### 8.4.3.5	Rescheduled Outage in “Received at ERCOT” (RatE) status

- While in “Received at ERCOT” status, requestors may:

- Revise the Planned Start, Earliest Start, Planned End, and Latest End information.

  - 3-day minimum submittal applies

  - Outage may start earlier or end later

  - New Outage duration cannot exceed the original duration

- Only remove elements from Group Outages.

- Edit the Name, Number, Emergency Restoration, Nature of Work, and Notes fields.

- Cancel the request.

- When the requestor has completed any revisions while in “Received at ERCOT” status, ERCOT shall evaluate the Rescheduled Outage and either:

  - Approve or

  - Reject the Request

- When the Transmission Rescheduled Outage becomes Approved, the normal rules and procedures for Approved Transmission Planned Outages apply.

- While in “Approved” status, ERCOT has the capability to:

- Withdraw the Outage

- Revert the Rescheduled Outage – Approved status back to a Rescheduled Outage. Entered Not Yet Submitted status, after discussion with the requestor.

- Outage cannot be reverted if edited Planned Start, Earliest Start, Planned End, or Latest End has been submitted.

#### 8.4.3.6    RO Status is reverted back to ENYS

When ERCOT reverts a Rescheduled Outage – Approved status back to a Rescheduled Outage – Entered Not Yet Submitted status:

- Warning Message “Outage ABCD12345678 has been rescheduled, new dates must be submitted” is issued.

- Outage status will show as Rescheduled Outage – Entered Not Yet Submitted.

- Original Request Date is retained.

Requestor must submit new Planned Start, Earliest Start, Planned End, and Latest End information, (Revised information in all four fields is required,)

    - 3-day minimum submittal period applies

    - Outage may start earlier or end later

    - New Outage duration cannot exceed the original duration

Requestor may edit the Name, Number, Emergency Restoration, and Notes fields.

Requestor may Cancel.

# 9	Maintenance Outages

Definition: An Outage initiated manually to remove equipment from service to perform work on components that could be postponed briefly but that is required to prevent a potential Forced Outage and that cannot be postponed until the next Planned Outage. Maintenance Outages are classified as follows:

- Maintenance Level 1: Equipment that must be removed from service within 24 hours to prevent forced Outage.

- Maintenance Level 2: Equipment that must be removed from service within 7 days to prevent forced Outage.

- Maintenance Level 3: Equipment that must be removed from service within 30 days to prevent forced Outage.

## 9.1 Maintenance Outage Rules

See Maintenance Outage Rules in the Common Business Rules and Definitions section.

## 9.2 Submit Maintenance Outage Request

Refer to procedures for submitting Planned Outages with the following exceptions:

Click Maintenance 1 to create an Outage that must be started within 24 hours to prevent a forced Outage.

- Planned Start date and time should be greater than current date and time and less than current date and time plus 24 hours.

OR

Click Maintenance 2 to create an Outage that must be started within 7 days to prevent a forced Outage.

Planned Start date should be greater than current date and time and less than current date plus 7 days.

OR

Click Maintenance 3 to create an Outage that must be started within 30 days to prevent a forced Outage.

- Planned Start date should be greater than current date and time and less than current date plus 30 days.

# 10	Forced Outages

Definition: An Outage initiated by protective relay or manually in response to an observation by personnel that the condition of equipment could lead to an event, or potential event that poses a threat to people, equipment, or public safety.

For a Generation Resource, an Outage that requires immediate removal, either through controlled or uncontrolled actions, of all or a portion of the capacity of the Resource from service through automated or manual means. This type of Outage usually results from immediate mechanical/electrical/hydraulic control system trips and operator-initiated actions in response to a Resource’s condition.

Forced Outages are submitted after the Outage has occurred.

## 10.1 Forced Outage Rules

See Forced Outage Rules in the Common Business Rules and Definitions section.

## 10.2 Submit Forced Outage Request

Refer to procedures for submitting Planned Outages with the following exceptions:

Click Forced.  The Create Outage Request screen displays.

- Submit the Actual Start, Planned End, and Latest End

Actual Start must be the time the Forced Outage actually occurred.

Add Requestor Notes, Remedial Action Plans, Automatic Mitigation Plans, Remedial Action Schemes, and/or Supporting Information as needed. See Enter and View Notes.

Supporting information is not required to create a Forced Outage request, but it is required before the Outage can be completed.

When the Forced Outage is successfully submitted, the system displays the Outage Detail screen with a message stating the Outage request was successfully submitted. The system automatically assigns it a status of “Accepted.”

# 11	Remedial Switching Action

Definition: A type of Forced Outage submitted for near Real-Time switching devices that will be opened to relieve or prevent an overload condition. The Outage must start within 3 days, have a maximum restoration time of 4 hours, and cannot exceed 72 hours in duration.

## 11.1 Remedial Switching Action Rules

See Remedial Switching Action in the Common Business Rules and Definitions section.

## 11.2 Submit Remedial Switching Action Outage Request

Refer to procedures for submitting Planned Outages with the following exceptions:

From the Outage Summary screen, click Create New Outage.  The Select Outage Type screen displays in a new window.

Click Remedial Switching Action.  The Create Outage Request screen displays.

Using the calendar, select the Planned Start, Earliest Start, Planned End, and Latest End dates.

Planned Start should be later than the current date/time and not more than 3 days from today.

Outage duration cannot exceed 72 hours.

Enter hours needed for Emergency Restoration.

Emergency Restoration cannot exceed 4 hours.

Add Requestor Notes, Remedial Action Plans, Automatic Mitigation Plans, Remedial Action Schemes, and/or Supporting Information as needed.  See Enter and View Notes.

Supporting information is not required to create a Remedial Switching Action request, but it is required before the Outage can be completed.

Click Submit.

When the Remedial Switching Action is successfully submitted, the system displays the Outage Detail screen with a message stating the Outage request was successfully submitted.

# 12	Simple Outages

Definition: A Planned Outage or Maintenance Outage of any Transmission Element in the Network Operations Model such that when the Transmission Element is removed from its normal service, absent a Forced Outage of other Transmission Elements, the Outage does not cause a topology change in the LMP calculation and thus cannot cause any LMPs to change with or without the Transmission Element that is suffering the Outage.

## 12.1 Simple Outage Rules

Simple Outages must meet the following criteria:

- Must be submitted at least 1 day in advance

- Maximum Emergency Restoration of 1 hour

- Outage duration cannot exceed 12 hours

## 12.2 Submit Simple Outage Request

Refer to procedures for submitting Planned Outages with the following exceptions:

From the Transmission Create Outage request menu, click Simple.

Using the calendar, select the Planned Start, Earliest Start, Planned End, and Latest End dates.

Planned Start must be later than or equal to the current date/time and not more than 1 day from today.

Outage duration cannot exceed 12 hours.

Enter hours needed for Emergency Restoration.

- Emergency Restoration cannot be longer than 1 hour in duration.

When the Simple Outage is successfully submitted, the system displays the Outage Detail screen with a message stating the Outage request was successfully submitted.

# 13	Resource Opportunity Outage

Definition: Resource Opportunity Outages are a specific type of Planned Outage. Resource Opportunity Outages allow a Requestor to join a forced Outage with an existing planned Outage. The planned Outage must already exist and have a status of “Approved” when the forced Outage is submitted to qualify. The planned Outage must have a start date within the next 8 days. HSL must be “0” for both Outages.

## 13.1 Resource Opportunity Outage

###### A Resource Opportunity Outage request may be granted by ERCOT when:

- A specific Resource experiences a Forced Outage and

- The Resource had been previously Approved or Accepted for a Planned Outage with a Planned Start during the next 8 days.

The QSE Sequence of Events for a Resource Opportunity Outage is:

- QSE has a previously Accepted or Approved Planned Outage on a Resource with a Start date of 8 calendar days or less.

- QSE enters a Forced Outage on the same Resource.

  - Outage Scheduler application will issue a warning message to the QSE and ERCOT.

- QSE may access the original Planned Outage request and select:

  - Yes to take a Resource Opportunity Outage.

    - The Resource will stay off-line.

    - Opportunity Outage covers the time period between the start of Forced Outage and the start of the Planned Outage.

  - No to not take the Opportunity Outage.

    - Resource becomes available after the Planned End Date of the Forced Outage until the Planned Start Date of the Planned Outage.

    - Original Planned Outage does not change.

## 13.2 View and Update a Resource Opportunity Outage

This warning will display on the Outage Detail screen the Forced Outage in the match.

#### 13.2.1	     When Status is “Entered Not Yet Submitted” (ENYS)

When a Forced Outage is submitted on an Approved Planned Outage meeting the Opportunity Outage criteria, the Planned Outages status changes to “Entered Not Yet Submitted” pending the Requestors Yes or No decision.

MPQSE

GenCity

UN

GenCity11

When the status for an Opportunity Outage is “Entered Not Yet Submitted,” a requestor may make the following changes:

Modify Requestor Phone and Name.

Add Notes.

Copy the Outage.

Select Take Opportunity Yes or No.

- Selecting Yes confirms that the Resource will stay off-line and the Opportunity Outage will cover the period between the start of the Opportunity Outage and the start of the original Planned Outage.

- Selecting No confirms that the Resource will become available after the Planned End Date of the Forced Outage and the Original Planned Outage does not change.

#### 13.2.2	   When in “Received at ERCOT” status.

A requestor may make the following changes:

- Cancel the Outage

- Shorten the Planned Start and Planned End

- Modify the Nature of Work

- Submit Notes

- Copy Outage

Once Approved by ERCOT, the Opportunity Outage follows the same procedure as a Planned Outage.

#### 13.2.3    When in Study, Rejected, or Withdrawn Status

When the status for an Opportunity Outage is Study, Rejected, or Withdrawn, a requestor may not make updates to the Outage. The Outage may be copied, if desired.

# 14	Transmission Opportunity Outages

Definition: An Opportunity Outage is a special category of Planned Outage. A Transmission Opportunity Outage (TOO) is a two-stage process. The first stage involves submitting the initial request for a TOO with its duration, set of designated Resources and the desired Transmission elements. The second stage involves the actual approval and implementation of a TOO when conditions have been met for the TOO.

## Opportunity Outage Rules

See Opportunity Outage Rules in the Common Business Rules and Definitions section.

The sequence of Events for a Transmission Opportunity outage is:

  - TSP and QSE/Resource Entity attempt to schedule maintenance during a Resource Planned Outage.

  - If no Resource Outage is planned or scheduled, TSP may submit an Opportunity Outage request.

  - If  QSE submits a Planned, Forced, or Maintenance Outage request on the designated Resource:

    - Outage Scheduler issues a Warning Message to ERCOT & the TSP.

    - TSP must:

      - Confirm that work can be completed during the Resource Outage.

      - Enter Planned Start and End dates into the Opportunity Outage request.

    - ERCOT will evaluate the request and if no security violations occur, issue approval.

## Submit Transmission Opportunity Outage Request

From the Outage Summary screen, click Create New Outage. The Create Outage Request screen displays in a new window.

Click Opportunity. The Create Outage Request screen displays.

The General Information section displays Request Date (current date and time), Requestor, Requesting Company, Primary Phone, and Secondary Phone. All are read-only.

Update Requestor Phone and Requestor Name, if required. 

Note: These are required fields and cannot be left blank.

Outage Data Section Requirements

The Outage Data section displays Category (Transmission) and Request Type (Opportunity) as read-only.

Select desired Resource Operating Company from the drop-down list.

Select a Resource Station from the drop-down list.

Select the Resource Equipment Type from the drop-down list.

Select the Resource Equipment from the drop-down list.

Enter HSL of “0” to designate that the Resource must be off-line for the Opportunity Outage window.

Tip: Up to 5 Resources may be designated in an Opportunity Outage.

The Opportunity Window End date defaults to 90 days from the request date.

On the Opportunity End Date, the TOO is automatically removed from “Received at ERCOT” status and is removed from the Summary.

Tip: The Opportunity window can only be a total of 90 days from today’s date. A requestor can shorten the window to less than 90 days by moving the default date inward.

Select the Outage Duration Days (dd) and Hours (HH) from the drop-down lists.

Enter hours needed for Emergency Restoration.

Emergency Restoration cannot exceed duration of the Outage.

Select Nature of Work.

Enter a Project Name, if required.

Select Operating Company. This defaults to the company name in the digital certificate.

Select a Station from the drop-down list.

Select the Equipment Type from the drop-down list.

Select the Equipment from the drop-down list.

When selecting a breaker or switch, verify the Outage State for the equipment.

Add Requestor Notes, Remedial Action Plans, Automatic Mitigation Plans, Remedial Action Schemes, and/or Supporting Information as needed. See Enter and View Notes.

Tip: A requestor may add additional equipment to an existing Grouped Outage, as long as the Outage Status is Received at ERCOT.

Click Submit.

Tip: This completes Stage One of the Opportunity Outage. The Opportunity Outage will now be waiting for a matching Resource Outage within the date window.

## View and Update an Opportunity Outage

### 14.3.1    When Status is “Received at ERCOT” pending a matching Resource Outage

When the status for an Opportunity Outage is “Received at ERCOT,” a requestor may make the following changes:

Change the Requestor Phone number or name.

Cancel the Outage.

### 14.3.2    When Status is “Received at ERCOT” with a matching Resource Outage

When the status for an Opportunity Outage is “Received at ERCOT,” a requestor may make the following changes:

A Warning displays at the top of the page to confirm the match between the Opportunity Outage and the Resource Outage.

Change the Requestor Phone Number or Name.

Cancel the Outage.

Using the calendar, select the Planned Start, Earliest Start, Planned End, and Latest End dates.

Planned Start and Planned End must fall between the Designated Resource Planned Start and the Designated Resource Planned End, as displayed in the Resource section of the page.

The Planned Start must be current date/time or greater than the current date/time.

The Planned End can be greater than the end date of the Opportunity Window End as long as the Planned End is not greater than the Planned End of the Resource Outage.

Add notes.

Copy the Outage.

Click Submit.

Tip: The Opportunity Outage waits at this stage for, first, the approval of the Resource Outage and then, the Opportunity Outage. Once both Outages have approvals, the Opportunity Outage updates to the status of “Approved.”

#### 14.3.3    When Status is “Received at ERCOT” with a matching Resource Outage

When the status for an Opportunity Outage is Received at ERCOT, a requestor may make the following changes:

Add notes.

Copy the Outage.

Change the Requestor Phone Number or Name.

Cancel the Outage.

Change Planned Start, Planned End, Earliest Start, and Latest End.

#### 14.3.4    When Status is “Approved” and Outage is Not Active

When status for an Opportunity Outage is “Approved” but the Outage is not Active, a Requestor may make the following changes:

Enter the Actual Start.

Shorten Outage duration by revising Planned Start and/or Planned End.

Add notes.

Copy the Outage.

Change the Requestor Phone Number or Name.

Cancel the Outage.

### 14.3.5    When Status is “Approved” and Outage is Active

When status for an Opportunity Outage is “Approved” and the Outage is active, a Requestor may make the following changes to a planned Outage:

Enter Actual End.

Enter New Planned End

Shorten Outage duration by revising Planned End.

Add notes.

Copy the Outage.

Change the Requestor Phone Number or Name.

# 15	Retrieve Outage History

An Outage History is available for all submitted Outages and completed Outages. The Outage history will provide the date and time and requestor name of every action related to when an Outage is:

- Created

- Submitted

- Received at ERCOT/Study

- Approved/Accepted or Rejected

- Modified

- Extended

- Cancelled or Withdrawn

- Completed (Actual End Submitted)

All Requestor Notes and related-ERCOT Reviewer Notes will be included.

To retrieve an Outage’s history record:

- Access is available only through the Outage Scheduler User interface.

TSPs may access all Transmission and Resource Outage history records.

QSEs may only access the Transmission and Resource Outage history records for the facilities which they operate.

- Requestors must use the Custom Filter to find the desired Detailed Outage request.

If the selected Outage is part of a Grouped Outage, all of the Outages in the group will be included in the History. If an Outage has been removed from a group, its history after having been removed must be retrieved separately.

- Select History at the bottom of the Detailed Outage Request screen.

- Open the dialog box to Open or Save the file in XLXS format.

# 16	Printing Summary Information

Every standard browser has a print function that will produce hardcopy output of the on-screen display. In addition, Outage Scheduler allows the current Outage Summary list to be printed in a more detailed report format.

Use the Custom Filter feature to control the content and number of Total Records before Printing!

Click Print Summary Information.

The Print View opens in a new window.  The print view displays the same columns as the default columns in the Summary screen, except it does not have the Warnings column.

- The print view always uses the default columns.

- Show/Hide Columns or Rows does not affect print view.

- The print view displays the first set of Requestor Notes only.

- The print view displays the results that are displayed on the Summary screen when the user clicks the Print Summary Information link. If the result set is more than one page, the print view prints all rows.

- Use the File/Print command to print as normal.

# 17	Exporting Outage Data to a File

Outage Scheduler allows the current Outage Summary list to be exported to either XML or CSV formats.

Use the Custom Filter feature to control the content and the number of Total Records before exporting!

## 17.1 Export in XML format

Click Export .xml

The File Download dialogue box displays.

Click Open to open the XML file.

The XML file (EXtensible Markup Language) opens in the default text editor. The XML view displays the same columns as the default columns in the Summary screen.

The XML file will only contain the Outages in the Summary at the time of the download.

Tip: A Requestor may select Save to save the file for later use.

## 17.2	Export as CSV format

Click Export .csv

The File Download dialogue box displays.

Click Open to open the CSV file.

The CSV file will only contain the Outages in the Summary at the time of the download.

All Requestor and ERCOT Reviewer Notes may not be included in the CSV format.  Use Outage History to retrieve all data related to an Outage.

Tip: A Requestor may select Save to save the file for later use.

The CSV file opens in the default spreadsheet software. The CSV view displays the same columns as the default columns in the Summary screen.

----------------------- End of User Guide -----------------------