## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
August 13, 2020

## Slide 2
Project Portfolio Update
  Recent / Upcoming Project Implementations
  2020 Release Targets
  NPRR885 Must-Run Alternative (MRA) Update
  2020/2021 Project Spending Forecast
  ERCOT Project Spending Highlights
  Priority/Rank Options for Revision Requests with Impacts
  Planned Project Starts / Prioritization Discussion
    Initial Discussion at July PRS / Follow-Up at August PRS
    Revision Request Inventory
      In-Flight Revision Requests
      Candidates for Summer 2021
      Candidates for Implementation Prior to 2024 RTC Go-Live
      Remaining Items
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Implementations
2020 August Release – Off-Cycle – 8/1/2020 Complete
  NPRR933 – Reporting of Demand Response by Retail Electric Providers and Non-Opt-In Entities
  RRGRR021 – Dynamic Model Requirement for TSAT
2020 August Release – R4 – 8/4/2020 – 8/6/2020 Complete
  NPRR935(a) – Post All Wind and Solar Forecasts
    Section 4.2.2 (1)(6) and Section 4.2.5
  NPRR951 – Active and Inactive SCED Constraint Reporting
  NPRR977 – Create MIS Posting for RUC Cancellations
2020 September Release – Off-Cycle – 9/3/2020 In Flight
  RIOO – RARF Replacement – View/Update – Initial Release
2020 November Release – Off-Cycle In Flight
  SCR804 – ERCOT GridGeo Access for Transmission Operators – 11/12/2020
  RIOO – RARF Replacement – View/Update – Follow-Up Release – 11/12/2020
  Enterprise Content Management System (ECMS) Phase 2 – 11/16/2020
2020 November/December Release – Off-Cycle In Flight
  MMS/OS Tech Refresh
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2020 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/4 – 2/6 | April 3/31 – 4/2 | May 5/26 – 5/29 | August 8/4 – 8/6 | October 10/13 – 10/15 | December 12/8 – 12/10
NPRR873 SCR797 NPRR877 Ph2 NPRR968 NPRR943 EMIL Web Interface NPRR863 FFR NPRR960 NOGRR187 OBDRR011 | SCR802 NPRR928 NPRR929 NPRR978(a) NPRR988 NPRR953 | NPRR856 NPRR884 OBDRR006 SCR803 NPRR887 NPRR907 NPRR985 RMGRR163 NPRR837 NPRR930(a) NPRR933 RRGRR021 | NPRR935(a) NPRR951 NPRR977 SCR804 SCR781(a) RRGRR016 RRGRR019 | NPRR902 MIS Go-Live SCR804 RIOO R2 MMS/OS Refresh NPRR863 ECRS | NPRR978 SCR806 NPRR857 NPRR904 NPRR905 NPRR917 NPRR936 NPRR941 NPRR963 NPRR971 NPRR978 NPRR986 NPRR998 OBDRR009 PGRR070(b) SCR781(b) SCR799
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
P
E
P
E
R1
R2
R3
R4
R5
R6
3/1
NPRR930(a) – O&M portion
NPRR935(a) – Sections 4.2.2 (1) (6), 4.2.5
NPRR935(b) – Sections 2.1, 2.2, 4.2.3
NPRR978(a) – Initial report decommissions
PGRR070(b) – Remaining PGRR language
SCR781(a) – View / Edit capability
MMS/OS Upgrade “Chill”
MMS/OS Upgrade “Freeze”
ü
ü
ü
November / December
Off-Cycle
1/1
2021 Go-Lives
I
NS
NS
P
NS
NS
NS
NS
P
I
P
NS
E
E
NS
September
Off-Cycle
1/19
E
ü
ü
TBD Items | 2017 | 2018 | 2019 / 2020
 | NPRR702, NPRR829 | NPRR825(b), NPRR867, NPRR841 | NPRRs: 826, 879, 885, 918, 930, 935(b), 939, 962, 965, 974, PGRR066, SCR800, SCR805
ü
CMM Release 2a
1/30
8/1
November
RIOO – 9/3
RARF Go-Live - View/Update
ü
ü
ü
ü
ü
ü
ü
ü
ü
5/1
ü
7/1
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
2024 Go-Lives
ü
ü
ü
On Hold

## Slide 5: NPRR885 Must-Run Alternative (MRA) – Update
At the July PRS, ERCOT noted exploring NPRR885 implementation alternatives
  Project is now “On Hold”
During Planning, ERCOT found the project was extremely complex and created resource conflicts with other priority efforts such as MMS/OS Tech Refresh and Real-Time Co-Optimization
ERCOT will explore whether any non-system components, such as the MRA Agreement, can be implemented on an interim basis
If an MRA is needed before system implementation, ERCOT will utilize manual work-arounds to remain compliant

## Slide 6: 2020 Project Spending
2020 PPL Budget = $29.0M
“Potential Demand” represents internal ERCOT projects that have not been fully approved

## Slide 7: ERCOT Project Spending Highlights
Improve data and information exchange to ERCOT stakeholders
  RARF Replacement (RIOO-RS)
  Enterprise Content Management System (ECMS) Phase 2
Enhance operating capabilities to maintain the reliability of an increasingly complex system
  Macomber Map Replacement for Control Room/OTS Integration (part of GridGeo)
  MMS/OS Tech Refresh
  EMS Upgrade
  Registration System Upgrade
  Enterprise Database Software Upgrade
  EDI Map and Translator Replacement
  REC Rewrite
  Wide Area Network (WAN) Refresh
Optimize use of ERCOT Inc.’s resources by providing staff with effective tools
  MS Office Update
  Project & Portfolio Management Tool Implementation
  Delivery Tool Chain Modernization
  Help Desk Software Replacement

## Slide 8: Revision Request (RR) Funding Placeholder Status
ERCOT reports RR spending each month to help PRS gauge the amount of resource demand being approved in the stakeholder process
ERCOT leadership understands that the years leading up to Real-Time Co-Optimization (RTC) go-live will be unique due to the inclusion of RRs relating to Battery Energy Storage (BES) and Distributed Generation Resources (DGR)
Market priority and ERCOT staff availability will be the driving factors behind the selection of projects to be undertaken
For this reason, ERCOT will temporarily suspend the reporting of RR spending against the annual funding placeholder

## Slide 9: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
 | None |  |  | 
Options for…
PPL Rank Information
Next available 2020 Rank in Business Strategy = 3060
Next available Rank in Regulatory = 260
Note
Items in the Regulatory section of the PPL are not tracked against the market Revision Request funding allocation

## Slide 10: Project Prioritization Discussion
Following the discussion of this topic at the July 2020 PRS meeting, a list of “Not Started” Revision Requests was compiled and sent to the PRS distribution list
ERCOT applied an initial recommendation by adding “Prioritization Category” and “High / Medium / Low” for use in segmenting the list into manageable groups
Prioritization Category
  1 – Regulatory
  2 – High Priority (“needed for summer 2021”, “needed for shoulder months”, etc.)
  3 – Needed for RTC (Passport)
  4 – Consider When Resources are Available
  5 – Consider When Efficiencies Exist With Another Effort
  6 – Dependent on Another Project
  8 – Candidate to Defer
  9 – No Action Needed
Categories 4 and 5 seem similar but the intent is to use Category 4 for items we clearly want to get done if resources are available. Category 5 are candidates for deferral but if the opportunity presents itself to pair them with related items for efficiency, we should consider doing so.

## Slide 11: Project Prioritization Discussion
Key Discussion Points
  Are projects properly categorized?
  Are “High / Medium / Low” values fairly applied?
Remember:
  The absolute rank isn’t the only factor in whether a project can get done
  Specific required resources (as defined by impacted systems) can also allow a project to be worked into the plan
What’s Next:
  ERCOT will prepare to start “High Priority” and “Needed for RTC” projects as appropriate in upcoming months
  ERCOT will evaluate remaining items on the list to determine what can be started based on resource availability

## Slide 12: Appendix
Prioritization slides from July 2020 PRS meeting

## Slide 13: Project Prioritization Discussion
A number of Revision Requests were approved in late 2019 and early 2020
  Revision Request project demand is high relative to historical norms
  Project resources are at a very high utilization level
  A review of priorities is needed to ensure funding is available for the most critical Revision Requests
ERCOT has identified candidates for delivery by summer 2021
ERCOT has also identified candidates to be started in the next 6 months so they can be delivered prior to the software development phase of Real-Time Co-Optimization (RTC)
Market input is requested on:
  Summer 2021 / Pre-RTC (summarized on slide 7)
  Remaining Revision Requests (summarized on slide 8)
The next project starts are targeted for September/October so this discussion can conclude at the August PRS meeting

## Slide 14: Revision Requests – In-Flight Spending Forecasts
Revision Request | Phase | 2020 Spend | 2021 Spend | Comment
NPRR863 Phase 2 – ECRS (ERCOT Contingency Reserve Service) | Planning | $700k | $1.40M | 2022 Go-Live Target
SCR781 – RARF Replacement (RIOO) | Execution | $400k | $300k | View/Change in progress
CMM Phase 2 – NPRRs 484, 867, 887, 907, 985 | Execution | $400k | $200k | 2020 R3 Go-Live (partial)
NPRR856 / NPRR884 / OBDRR006 | Execution | $350k | – | 2020 R3 Go-Live
SCR804 – ERCOT GridGeo Access for Transmission Operators | Planning | $350k | – | 2020 Sept. Go-Live Target
NPRR863 Phase 1 – FFR (Fast Frequency Response) | Execution | $250k | – | 3/1/2020 Go-Live
NPRR986 / NPRR971 – BESTF-2 / RT AIEC | Planning | $200k | $50k | 2021 Go-Live Target
NPRR929 – PTP Obligations w/Links to Option DAM Award Eligibility | Closing | $150k |  | 2020 R2 Go-Live
NPRR902 – ERCOT Critical Energy Infrastructure Information | Planning | $100k | – | 2020 R5 Go-Live Target
SCR803 – Wind Integration Rpt / Solar Integration Rpt/Dashboard | Execution | $50k | – | 2020 R3 Go-Live
NPRR935 – Post All Wind and Solar Forecasts | Execution | $50k | – | 2020 R4 Go-Live Target
NPRR951 – Active and Inactive SCED Constraint Reporting | Execution | $50k | – | 2020 R4 Go-Live Target
NPRR905 – CRR Balancing Account Resettlement | Planning | $50k | $25k | 2021 Go-Live Target
NPRR873, NPRR911, NPRR920, NPRR952, NPRR998, SCR797, SCR802 (all <$25k spend in 2020) | Various | $100k | – | 
Total |  | $3.20M | $1.98M | 

## Slide 15: Revision Requests – 2020 / 2021 Spending Scenario
Revision Request | 2020 Spend | 2021 Spend | Comments
In-Flight (from previous slide) | $3.20M | $1.98M | 
Potential Candidates for Summer 2021 |  |  | 
NPRR930 – Pricing /Cost Recovery for Delayed Res. Outages | $50k | $100k | Shoulder month issue – Early 2021 target
NPRR939 – Mod. to Load Resources Providing RRS… | $10k | $50k | 
NPRR904 / OBDRR009 – ORDC Revisions | $50k | $200k | Address market concerns and events that are more likely to occur in the summer months
NPRR1019 – Pricing & Settlement Changes for SWGRs... | $10k | $100k | 
NPRR974 – Capacity Insufficiency OCN Transparency | $10k | $50k | 
Potential Candidates to Implement Prior to RTC |  |  | 
NPRR1029 – BESTF-6 DC Coupled Resources | – | $500k | ERCOT evaluating this group of RRs to assess if: Needed before RTC go-live in 2024 … or … Lays the foundation for work that’s expected to be delivered with RTC in 2024
NPRR1016 – DGRs and DESRs | $25k | $400k | 
NPRR917 – Nodal Pricing for SODGs and SOTGs | $10k | $300k | 
NPRR1026 – BESTF-7 Self-Limiting Facilities/Resources | – | $150k | 
NPRR963 – Base Point Deviation - Combo Model | $10k | $150k | 
NPRR987 – BESTF-3 ESR PRC & RT Capacity Calcs | $25k | $150k | 
NPRR1002 – BESTF-5 ESR Single Model Registration & Charging Restrictions | $25k | $100k | 
PGRR082 – Establish Small Generation Interconnection | $25k | $50k | 
Total | $3.45M | $4.28M | 
Important: These items have not been assessed for resource availability.
That review will be done once agreement is reached on overall priorities.

## Slide 16: Approved Revision Requests “Not Started” – Market Input Requested
Revision Request | Priority | Cost Est. | Comments
NPRR826 – Mitigated Offer Caps for RMR Resources | 2020 | $100k-$200k | Market input needed
NPRR829 – Incorporate RT Non-Modeled Telemetered Net Generation… | 2019 | $200k-$300k | ERCOT recommends separating from CMM Phase 2 for delivery by summer 2021
NPRR841 – RT Adj. to Day-Ahead Make Whole Pmts due to A/S Infeasibility | 2019 | $60k-$80k | Does RTC change the need for this?
NPRR879 – SCED Base Point, Base Point Deviation, & Performance Eval… | 2020 | $200k-$250k | Market input needed
NPRR918 – Validation for PTP Obligations with Links to an Option | 2020 | $30k-$50k | Market input needed
NPRR936 – CRR Account Holder Limits | 2020 | $150k-$250k | Market input needed
NPRR941 – Create a Lower Rio Grande Valley Hub | 2020 | $250k-$350k | Market input needed
NPRR962 – Publish Approved DC Tie Schedules | 2020 | $15k-$30k | Market input needed
NPRR965 – GREDP Shutdown Exemption | 2020 | $10k-$20k | Market input needed
NPRR975 – Load Forecast Model Transparency | 2020 | $75k-$100k | Market input needed
NPRR1006 – Update RT On-Line Reliability Deployment Price Adder Inputs... | 2020 | $140k-$180k | Market input needed
PGRR066 – Interconnection Req. Cancellation & Creation of Inactive Status | 2019 | $100k-$150k | Next phase of RIOO
SCR799 – ERCOT Outage Study Cases in the SOTE | 2019 | $150k-$250k | Market input needed
SCR800 – Addition of DC Tie Ramp to GTBD Calculation | 2020 | $30k-$50k | Market input needed
SCR805 – Early Access to Certain 60-Day Reports to TSPs | 2020 | $40k-$60k | Market input needed
SCR807 – Increase CRR Transaction Capability | 2020 | $50k-$100k | Potential efficiencies with related CMM work
SCR809 – Changes to Ext. Telemetry Validations in Resource Limit Calc. | 2020 | $40k-$60k | Market input needed
SCR810 – EMS Change to Count DC Ties towards 2% Constraint Criterion | 2020 | $15k-$25k | Market input needed (August Board)

## Slide 17: Approved Revision Requests “Not Started” – Others
Revision Request | Priority | Start Date | Cost Est. | Comment / Recommended Action
NPRR702 – Flexible Accounts, Payment of Invoices, and Disposition of Interest on Cash Collateral | 2016 | N/A | $150k-$200k | NPRR1027 proposes to strike remaining gray-box language
NPRR825 – Require ERCOT to Issue a DC Tie Curtailment Notice Prior to Curtailing DC Tie Load | 2018 | TBD | $200k-$300k | Pending internal ERCOT project that will provide required data
NPRR857 – Creation of Direct Current Tie Operator Market Participant Role | 2019 | TBD | $500k-$700k | Southern Cross – no budgetary impact
Revision Request | Next Approval | Target Start Date | Cost Est. | Comment / Recommended Action
NPRR1004 – Load Distribution Factor Process Update | Board | TBD | $45k-$65k | Market input needed
NPRR1030 – Modify Allocator for CRR Auction Revenue Distribution | Board | TBD | $175k-$225k Revised | Urgency requested at July PRS Market input needed
NOGRR195 – Generator Voltage Control Tolerance Band | Board | TBD | $30k-$50k | Market input needed
PGRR076 – Improvements to GINR Process | Board | TBD | $50k-$75k | Market input needed
Revision Requests – In Stakeholder Process