## Sheet1
REVISION REQUEST PRIORITIZATION - "NOT STARTED" RRs
PPL Category | Priority | Rank | Revised Rank | Prioritization Category | High / Medium / Low | Source Doc | Approval Status | Board Approval Date | Project Name | Release | Project Status | IA Budget Range | IA Duration Range | Major Impacted System | Major Impacted System % | % Vendor Required | Impacted Systems (Listed on IA) | ERCOT Comments | PRS Comments
Regulatory | 2020 | 300 |  | 1 - Regulatory | 1 - High | NOGRR195 | PPL | 2020-08-01 | Generator Voltage Control Tolerance Band | TBD | Not Started | $30k-$50k | 4-6 months | EMS | 67% | 0% | EMS, BI & Data Analytics | Addresses ERCOT audit recommendations from TRE
Business Strategy | 2019 | 2720 |  | 2 - High Priority | 1 - High | OBDRR009 | PPL | 2019-08-01 | ORDC OBD Revisions for ERCOT-Directed Actions Related to DC Ties | 2021-R3 | Not Started | $30k-$50k | 4-6 months | MMS | 40% | 0% | MMS, DAIP, BI & Data Analytics | Summer 2021 candidate Pairs with NPRR904
Business Strategy | 2019 | 2720 |  | 2 - High Priority | 1 - High | NPRR904 | PPL | 2019-08-01 | Revisions to Real-Time On-Line Reliability Deployment Price Adder for ERCOT-Directed Actions Related to DC Ties and to Correct Design Flaws | 2021-R3 | Not Started | $200k-$300k | 6-9 months | MMS | 85% | 41% | MMS, EMS, BI & Data Analytics, DAIP | Summer 2021 candidate Pairs with OBDRR009
Business Strategy | 2019 | 2770 |  | 2 - High Priority | 1 - High | NPRR939 | PPL | 2019-10-01 | Modification to Load Resources Providing RRS to Maintain Minimum PRC on Generators During Scarcity Conditions | 2021-R3 | Not Started | $70k-$100k | 5-7 months | MMS | 70% | 0% | MMS, DAIP, Integration | Shoulder month issue - early 2021 target
Business Strategy | 2020 | 2815 |  | 2 - High Priority | 1 - High | NPRR963 | PPL | 2020-02-01 | Base Point Deviation Settlement and Deployment Performance Metrics for Energy Storage Resources (Combo Model) | 2021-R3 | Not Started | $150k-$200k | 8-12 months | DAIP | 31% | 0% | DAIP, S&B, EMS, BI & Data Analytics, Integration | Needed to support combo-model ESR
Business Strategy | 2020 | 2890 |  | 2 - High Priority | 1 - High | NPRR930 | PPL | 2019-10-01 | Process Pricing and Cost Recovery for Delayed Resource Outages | 2021-R2 | Not Started | $100k-$200k | 5-7 months | MMS | 74% | 39% | MMS, OS, DAIP, Data Access & Transparency, External Public | Shoulder month issue - early 2021 target
Business Strategy | 2020 | 2980 |  | 2 - High Priority | 1 - High | NPRR974 | PPL | 2020-02-01 | Capacity Insufficiency Operating Condition Notice (OCN) Transparency | 2021-R2 | Not Started | $50k-$80k | 5-7 months | DAIP | 62% | 0% | DAIP, MMS, External Public | Summer 2021 candidate
Business Strategy | 2020 | 3010 |  | 2 - High Priority | 1 - High | NPRR987 | PPL | 2020-06-01 | BESTF-3 Energy Storage Resource Contribution to Physical Responsive Capability and Real-Time On-Line Reserve Capacity Calculations | TBD | Not Started | $150k-$200k | 6-9 months | MMS | 34% | 9% | MMS, S&B, EMS, Integration, BI & Data Analytics, DAIP | Needed to support combo-model ESR
Business Strategy | 2020 | 3030 |  | 2 - High Priority | 1 - High | NPRR1019 | PPL | 2020-06-01 | Pricing and Settlement Changes for Switchable Generation Resources (SWGRs) Instructed to Switch to ERCOT | 2021-R3 | Not Started | $100k-$140k | 5-7 months | MMS | 98% | 44% | MMS, BI & Data Analytics | Summer 2021 candidate
Business Strategy | 2020 | 3060 |  | 3 - Needed for RTC | 1 - High | NPRR1002 | PPL | 2020-08-01 | BESTF-5 Energy Storage Resource Single Model Registration and Charging Restrictions in Emergency Conditions | TBD | Not Started | $100k-$200k | 7-10 months | Resource Integration | 83% | 0% | Resource Integration, Integration, DAIP | Supports integration of ESRs into the ERCOT markets - both combo model and single model
Business Strategy | 2020 | 3070 |  | 3 - Needed for RTC | 1 - High | NPRR1016 | PPL | 2020-08-01 | Clarify Requirements for Distribution Generation Resources (DGRs) and Distribution Energy Storage Resources (DESRs) | TBD | Not Started | $400k-$550k | 12-18 months | OS | 41% | 16% | OS, EMS, BI & Data Analytics, DAIP, MMS, REG, NMMS, Integration
- | - | - |  | 3 - Needed for RTC | 1 - High | NPRR989 | - | 2020-06-01 | BESTF-1 Energy Storage Resource Technical Requirements | TBD | Not Started | <$10k | - | NDCRC | - | - | NDCRC, DAIP | O&M - not prioritized on PPL Will be included with other BESTF RRs
Business Strategy | 2017 | 1820 |  | 4 - Consider When Resources are Available | 1 - High | SCR789 | PPL | 2016-08-01 | Update NMMS Topology Processor to PSSE 34 Capability | TBD | On Hold | $300k-$450k | 9-12 months | NMMS | 100% | 76% | NMMS
Business Strategy | 2019 | 2510 |  | 4 - Consider When Resources are Available | 1 - High | NPRR829 | PPL | 2017-10-01 | Incorporate Real-Time Non-Modeled Telemetered Net Generation by Load Zone into the Estimate of RTL | TBD | Not Started | $200k-$300k | 5-10 months | CMM | 26% | 0% | CMM, NMMS, EMS, REG, Integration, DAIP, Data Access & Transparency | Originally planned for CMM Phase 2 Being considered as a stand-alone effort
Business Strategy | 2020 | 2515 |  | 4 - Consider When Resources are Available | 1 - High | NPRR1030 | PPL | 2020-08-01 | Modify Allocator for CRR Auction Revenue Distribution | TBD | Not Started | $175k-$225k | 8-12 months | S&B | 74% | 0% | S&B, DAIP, CMM, Integration
Business Strategy | 2019 | 2700 |  | 4 - Consider When Resources are Available | 1 - High | NPRR917 | PPL | 2019-08-01 | Nodal Pricing for Settlement Only Distribution Generators (SODGs) and Settlement Only Transmission Generators (SOTGs) | 2021-TBD | Not Started | $300k-$400k | 9-12 months | S&B | 30% | 0% | S&B, Integration, MMS, DAIP, NMMS, CMM, REG, Data Access & Transparency, External Public, BI & Data Analytics | Possible bundle with NPRR995 (still in stakeholder process)
Business Strategy | 2019 | 2710 |  | 4 - Consider When Resources are Available | 1 - High | SCR799 | PPL | 2019-06-01 | ERCOT Outage Study Cases in the System Operations Test Environment (SOTE) | 2021-R2 | Not Started | $150k-$250k | 5-7 months | SOTE | 100% | 0% | SOTE | Improves the ability of TSPs to evaluate Outages prior to submittal to ERCOT
Business Strategy | 2020 | 2855 |  | 4 - Consider When Resources are Available | 1 - High | SCR807 | PPL | 2020-06-01 | Increase CRR Transaction Capability | 2020-TBD | Not Started | $50k-$100k | 5-7 months | CRR | 95% | 60% | CRR, Integration | ERCOT will watch auction trends closely and recommend the start of this NPRR when it is needed
Business Strategy | 2020 | 3020 |  | 4 - Consider When Resources are Available | 1 - High | NPRR1006 | PPL | 2020-06-01 | Update Real-Time On-Line Reliability Deployment Price Adder Inputs to Match Actual Data | TBD | Not Started | $140k-$180k | 6-9 months | MMS | 62% | 29% | MMS, DAIP, EMS, S&B, BI & Data Analytics
Business Strategy | 2020 | 2920 |  | 4 - Consider When Resources are Available | 2 - Medium | SCR805 | PPL | 2019-12-01 | Provide Early Access to Certain 60-Day Reports to TSPs Upon Request | 2021-R3 | Not Started | $40k-$60k | 4-6 months | DAIP | 97% | 0% | DAIP, Data Access & Transparency
Business Strategy | 2020 | 2970 |  | 4 - Consider When Resources are Available | 2 - Medium | NPRR826 | PPL | 2020-02-01 | Mitigated Offer Caps for RMR Resources | 2021-R3 | Not Started | $100k-$200k | 6-8 months | MMS | 70% | 68% | MMS, DAIP, External Public, Data Access & Transparency
Business Strategy | 2020 | 3050 |  | 4 - Consider When Resources are Available | 2 - Medium | SCR810 | PPL | 2020-08-01 | EMS System Change to Count DC Ties towards the 2% Constraint Activation Criterion | TBD | Not Started | $15k-$25k | 3-5 months | EMS | 100% | 0% | EMS
Business Strategy | 2021 | 3220 |  | 4 - Consider When Resources are Available | 2 - Medium | NPRR1020 | PPL | 2020-08-01 | Allow Some Integrated Energy Storage Designs to Calculate Internal Loads | TBD | Not Started | $175k-$225k | 8-12 months | EPS Meter | 86% | 0% | EPS Meter, S&B | Dependent on SMOGRR to be filed
Business Strategy | 2020 | 2910 |  | 5 - Consider When Efficiencies Exist With Another Effort | 1 - High | SCR800 | PPL | 2019-12-01 | Addition of DC Tie Ramp to GTBD Calculation | 2020-R5 | Not Started | $30k-$50k | 3-5 months | EMS | 38% | 0% | EMS, Data Management, MMS, BI & Data Analytics
Business Strategy | 2020 | 2800 |  | 5 - Consider When Efficiencies Exist With Another Effort | 2 - Medium | NPRR879 | PPL | 2018-12-01 | SCED Base Point, Base Point Deviation, and Performance Evaluation Changes for IRRs that Carry Ancillary Services | 2021-R5 | Not Started | $200k-$250k | 6-9 months | DAIP | 46% | 0% | DAIP, S&B, BI & Data Analytics, EMS, NMMS, Integration
Business Strategy | 2020 | 2840 |  | 5 - Consider When Efficiencies Exist With Another Effort | 2 - Medium | NPRR918 | PPL | 2019-10-01 | Validation for PTP Obligations with Links to an Option | 2021-R2 | Not Started | $30k-$50k | 4-6 months | MMS | 57% | 0% | MMS, DAIP, Integration
Business Strategy | 2020 | 2850 |  | 5 - Consider When Efficiencies Exist With Another Effort | 2 - Medium | NPRR936 | PPL | 2019-10-01 | CRR Account Holder Limits | 2021-R2 | Not Started | $150k-$250k | 8-10 months | CRR | 90% | 51% | CRR, DAIP
Business Strategy | 2020 | 2870 |  | 5 - Consider When Efficiencies Exist With Another Effort | 2 - Medium | NPRR962 | PPL | 2019-10-01 | Publish Approved DC Tie Schedules | 2020-R6 | Not Started | $15k-$30k | 3-4 months | DAIP | 86% | 0% | DAIP, BI & Data Analytics
Business Strategy | 2020 | 2900 |  | 5 - Consider When Efficiencies Exist With Another Effort | 2 - Medium | NPRR965 | PPL | 2019-12-01 | GREDP Shutdown Exemption | 2021-R3 | Not Started | $10k-$20k | 3-5 months | BI & Data Analytics | 100% | 0% | BI & Data Analytics
Business Strategy | 2020 | 3000 |  | 5 - Consider When Efficiencies Exist With Another Effort | 2 - Medium | NPRR975 | PPL | 2020-06-01 | Load Forecast Model Transparency | 2021-TBD | Not Started | $75k-$100k | 6-9 months | EMS | 58% | 0% | EMS, DAIP, BI & Data Analytics
Business Strategy | 2020 | 3040 |  | 5 - Consider When Efficiencies Exist With Another Effort | 2 - Medium | SCR809 | PPL | 2020-06-01 | Changes to External Telemetry Validations in Resource Limit Calculator | TBD | Not Started | $40k-$60k | 4-6 months | EMS | 83% | 0% | EMS, BI & Data Analytics
Business Strategy | 2021 | 3200 |  | 5 - Consider When Efficiencies Exist With Another Effort | 2 - Medium | PGRR076 | PPL | 2020-08-01 | Improvements to Generation Resource Interconnection or Change Request (GINR) Process | TBD | Not Started | $50k-$75k | 6-9 months | Resource Integration | 57% | 0% | Resource Integration, Integration, Data Access & Transparency | Potential to include in RIOO in 2021 2 FTE impact
Business Strategy | 2021 | 3210 |  | 5 - Consider When Efficiencies Exist With Another Effort | 2 - Medium | NPRR1004 | PPL | 2020-08-01 | Load Distribution Factor Process Update | TBD | Not Started | $45k-$65k | 5-7 months | MMS | 41% | 0% | MMS, Integration, DAIP, External Public
Business Strategy | 2019 | 2520 |  | 5 - Consider When Efficiencies Exist With Another Effort | 3 - Low | NPRR841 | PPL | 2018-02-01 | Real-Time Adjustments to Day-Ahead Make Whole Payments due to Ancillary Services Infeasibility Charges | TBD | Not Started | $60k-$80k | 4-6 months | S&B | 88% | 0% | S&B, Integration, Data Access & Transparency, CRM & Registration System | RTC implementation may make this NPRR a candidate for deferral
Business Strategy | 2019 | 2580 |  | 5 - Consider When Efficiencies Exist With Another Effort | 3 - Low | PGRR066 | PPL | 2018-12-01 | Interconnection Request Cancellation and Creation of Inactive Status | 2021-R4 | Not Started | $100k-$150k | 4-6 months | Resource Integration | 100% | 0% | Resource Integration | ERCOT can keep the existing manual workaround until resources are available
Business Strategy | 2020 | 2860 |  | 5 - Consider When Efficiencies Exist With Another Effort | 3 - Low | NPRR941 | PPL | 2019-12-01 | Create a Lower Rio Grande Valley Hub | 2021-R5 | Not Started | $250k-$350k | 6-8 months | MMS | 91% | 75% | MMS, DAIP, EMS, External Public
Business Strategy | 2018 | 2090 |  | 6 - Dependent on Other Project | 2 - Medium | NPRR825 | PPL | 2017-12-01 | Require ERCOT to Issue a DC Tie Curtailment Notice Prior to Curtailing any DC Tie Load | TBD | Not Started | $200k-$300k | 8-12 months | MMS | 82% | 0% | MMS, Data Access & Transparency, DAIP, Integration | Dependent on internal ERCOT project Partial delivery in Oct. 2018
Business Strategy | 2019 | 2530 |  | 6 - Dependent on Other Project | 2 - Medium | NPRR857 | PPL | 2018-10-01 | Creation of Direct Current Tie Operator Market Participant Role | TBD | Not Started | $500k-$700k | 12-18 months | OS | 53% | 25% | OS, EMS, OTS, WAN, NMMS, External Public, Integration, BI & Data Analytics, REG, Data Access & Transparency, DAIP
Business Strategy | 2016 | 1550 |  | 9 - No Action Needed | 3 - Low | NPRR702 | PPL | 2015-12-01 | Flexible Accounts, Payment of Invoices, and Disposition of Interest on Cash Collateral | N/A | Not Started | $150k-$200k | 6-9 months | FT | 83% | 0% | FT, CMM, DAIP, External Public | NPRR1027 strikes this NPRR