## Slide 1
Real-Time Co-optimization Task Force (RTCTF) Update
Bryan Sams
RTCTF Vice Chair
TAC
August 26, 2020

## Slide 2: Outline of RTCTF Update
RTC Revision Requests (RTCRRs)
RTCRR Review Schedule & Progress to Date
Next Steps
Appendix
  RTCRR Review Process
  Previously Discussed Consensus Items
  Overall RTC Delivery Schedule

## Slide 3: RTC Revision Requests
Reminder that based on the Board-approved RTC Key Principles (KPs), ERCOT developed and released the following NPRRs, NOGRR, and OBDRR with a single Impact Analysis (IA).
RTCRRs released March 25, 2020 | Pages 549 total
NPRR1007- RTC NP3- Management Activities for the ERCOT System | 62
NPRR1008- RTC NP4- Day-Ahead Operations | 65
NPRR1009- RTC NP5- Transmission Security Analysis and Reliability Unit Commitment | 39
NPRR1010- RTC NP6- Adjustment Period and Real-Time Operations | 248
NPRR1011- RTC NP8- Performance Monitoring | 49
NPRR1012- RTC NP9- Settlement and Billing | 15
NPRR1013- RTC NP 1, 2, 16, 25- Overview, Definitions/Acronyms, Registration and Qualification of MPs, and Market Suspension and Restart | 24
NOGRR211- RTC Nodal Operating Guides 2 and 9- System Operations and Control Requirements and Monitoring Programs | 21
OBDRR020- RTC - Methodology for Setting Maximum Shadow Prices for Network and Power Balance Constraints | 26

## Slide 4: RTCRR Review Schedule & Progress to Date
Schedule of 2020 meetings for RTCRRs:
Mar. 11 – RTCTF (Plan and logistics for RR review)
Apr. 8 – RTCTF (Review detailed plan, and begin review process)
Apr. 30 – RTCTF
May 11 – Special RTCTF for Potential Design Flaw- AS Price Cap discussion
May 20 – RTCTF
Jun. 10 – RTCTF
Jun. 22 – Special RTCTF for Ancillary Service Deployments
Jun. 29 – RTCTF
Jul. 15 – Special RTCTF for AS Deployment Expectations & Durations
Jul. 22 – RTCTF
Aug. 12 – RTCTF
Sep. 9 – RTCTF
Sep. 28 – RTCTF
Oct. 21 – RTCTF
Nov. 5 – ROS
Nov. 11 – PRS
Nov. 12 – RTCTF (if needed)
Nov. 17 – CWG
Nov. 18 – TAC
Dec. 8 – ERCOT Board

## Slide 5: RTCRR Review Schedule & Progress to Date
Detailed schedule for reviewing the RTCRR language with RTCTF (posted on the RTCTF page, and excerpt below).
The overall status of 84% complete (consensus on 163 of 193 binding document sections under review)

## Slide 6: RTCRR Review Schedule & Progress to Date
8/12/2020 RTCTF Consensus (27 items):
  RTM - AS Deployment and AS Qualification
    NOGRR211 (2.3, 2.3.1.2, 2.3.2.1, 2.3.3.1)
    NPRR1011 (8.1.1.2.1, 8.1.1.2.1.1, 8.1.1.2.1.2, 8.1.1.2.1.3, 8.1.1.2.1.6)
  Additional Comments to 6.5.5.2 - Regarding Non-Spin from On-line Generator using Power Augmentation
    NPRR1010 (6.5.5.2) - Initial consensus on 5/20/20
  Additional Comments to 6.5.7.4.1 Regarding FFR Deployment in UDSP
    NPRR1010 (6.5.7.4.1) - Initial consensus on 7/22/20
  RTM Settlement
    NPRR1010 (6.7.5, 6.7.5.1, 6.7.5.2, 6.7.5.3, 6.7.5.4, 6.7.5.5, 6.7.5.6, 6.7.5.7, 6.7.5.8, 6.7.6, 6.7.7)
  Emergency Settlement – Non-SCED Failure scenarios
    NPRR1010 (6.6.9)
  Legal/Market Rules Clarifications
    NPRR1010 (6.4.9.1.2, 6.5.7.3, 6.5.7.6.1, 6.7.4)

## Slide 7: Next Steps
Review reminders:
  As always, MPs encouraged to send Revision Request redlines for RTCTF consideration to DMaggio@ercot.com & MMereness@ercot.com to document and discuss at next meeting.
  You can also submit formal comments through the standard Market Rules RevisionRequest process.
  On August 18, 2020 ERCOT posted formal comments for some NPRRs to capture cumulative consensus changes as a single set of redlines under the author of “ERCOT 081820”,
    Included portions of NPRR1007, 1010, 1011, 1012, and NOGRR211
Next RTCTF is September 9th
Any comments or questions?

## Slide 8: Appendix
RTCRR Review Process
Previously Discussed Consensus Items
Overall RTC Delivery Schedule

## Slide 9: RTCRR Review Process
7-days prior #1
ERCOT posts agenda and RTCRRs to be reviewed
7-days prior #2
MP comments and redlines due and posted to address concerns or alternatives
During meeting, MPs discuss any concerns or alternatives
7-days prior #3
MPs must document concerns and alternative language prior to meeting, and be prepared to discuss.
7-days prior #3
Non-consensus materials posted for options on language to be considered.
Meeting #1 Meeting #2 Meeting #3
TAC will be updated monthly. If irresolvable issues occur at RTCTF, the RTCTF Chair can request TAC endorsement to resolve.
2-days prior #2
ERCOT responds to MP comments with redlines
Consensus Items Tracked in Spreadsheet as Complete
Resolved Items Tracked in Spreadsheet as Complete
ERCOT will file cumulative RTCRR comments reflecting when consensus on sections achieved. (Also tracked in summary spreadsheet)

## Slide 10: RTC Review Process (continued)
At the May 2020 TAC meeting there was no opposition to the following process (if needed) to potentially modify RTCRRs beyond the scope of the RTC KPs if a market design flaw or error was discovered following Board approval of the RTC KPs:
  The modification complies with PUC directives;
  The modification will not incur additional RTC project costs or schedule delays; and
  The modification will not delay timely implementation of RTCRRs (i.e., will not prevent the Board from considering the NPRR at the December 8, 2020 Board meeting).
Next slide describes the review and escalation process from RTCTF to TAC

## Slide 11: RTC Review Process (continued)
Proposed process for modifying RTCRRs beyond scope of Board-approved KPs:
  A Market Participant has the right to express concerns with a RTCRR.
    A Market Participant may file comments to modify a RTCRR beyond the scope of the Board-approved KPs.
    In comments to modify an RTCRR, the submitting party shall explain how the revisions meet the criteria proposed on the previous slide.
  RTCTF will provide:
    The technical forum (e.g., an extra off-cycle meeting) for discussion of the proposed RTCRR changes with the understanding that RTCTF consensus is not practical and will not occur.
  At TAC:
    RTCTF Chair will advise TAC leadership of any RTCRR Comments that propose to modify the scope of the KPs beyond that which was approved by the Board, and
    Request time for the MP to present to TAC for consideration, as well as another MP to present the counterpoints (if any) as to why the existing KP should continue to be maintained and aligned with RTCRRs.
    TAC may take a straw poll to endorse the proposed NPRR comments; the vote would not be binding and therefore non-appealable, but would classify the modified/added concept as valid.
  If TAC endorses the alternative, the RTCTF Chair would update the Board of the straw poll decision.
  The RTCRR comments would subsequently be considered at PRS, TAC, and ultimately the ERCOT Board as consistent with Protocols Section 21 process.

## Slide 12: Previously Discussed Consensus Items
4/30/2020 RTCTF Consensus:
  SWCAP/VOLL - OBDRR020 (Sections 2 and 4)
  AS Proxy Offers and General SCED – NPRR1010 (6.4.9.1.1)
  Reliability Deployment Pricing Run - NPRR1010 (6.5.7.3.1)
  COP Changes - NPRR1007 (3.9, 3.9.1, and 3.9.2)
  RUC General Update - NPRR1009 (5.1, 5.2.2.1, 5.2.2.2, 5.3, 5.4, 5.4.1, and 5.5.2)
5/20/2020 RTCTF Consensus:
  SWCAP/VOLL- NPRR1008 (4.4.11 and 4.4.11.1)
  ASDC Creation- NPRR1008 (4.4.12)
  AS Proxy Offers and General SCED- NPRR1010 (6.5.7.3)
  Market Restart- NPRR1013 (25.3)
  SASM Removal- NPRR1008 (4.5.2) & NPRR1010 (6.4.9, 6.4.9.1.3, 6.4.9.2, 6.4.9.2.1, 6.4.9.2.2, and 6.4.9.2.3)
  DAM General Update- OBDRR020 (Appendix 1)

## Slide 13: Previously Discussed Consensus Items (continued)
6/10/2020 RTCTF Consensus (37 items):
  DAM – AS Only Offer Material (Round 3)
    NPRR1008 (4.3, 4.4.7.2, 4.4.7.2.1, 4.4.7.2.2, 4.4.7.2.3, 4.4.7.2.4, and 4.5.3)
  RTM - Telemetry and RLC (Round 3)
    NPRR1010 (6.4.6, 6.5.5.2, 6.5.7.1.12, 6.5.7.1.13, and 6.5.7.2)
  DAM General Update (Round 3)
    NPRR1008 (4.1, 4.2.1.2, 4.4.7.1, 4.4.7.1.1, 4.4.7.3, 4.4.8, 4.4.9.3.1, 4.4.9.3.3, 4.4.9.4.1, 4.4.9.5.1, and 4.5.1)
  Credit (Round 2)
    NPRR1013 (16.11.4.1, 16.11.4.3.2)
  DAM Credit/Settlement (Round 2)
    NPRR1008 (4.4.10, 4.6.2.3.1, 4.6.4.1.1, 4.6.4.1.2, 4.6.4.1.3, 4.6.4.1.4, 4.6.4.1.5, 4.6.4.2.1, 4.6.4.2.2, 4.6.4.2.3, 4.6.4.2.4, 4.6.4.2.5)

## Slide 14: RTCRR Review Schedule & Progress to Date
6/29/2020 RTCTF Consensus (34 items):
  DAM General Update (Round 3)
    NPRR1008 (4.4.7.3)
  RUC Settlement (Round 3)
    NPRR1009 (5.6.2, 5.7.1.3, 5.7.1.4, 5.7.4.1.1)
  RTM - AS Deployment (Round 2)
    NPRR1007 (3.16, 3.17.1, 3.18)
  RTM - General Update (Round 2)
    NOGRR211 (2.1, 2.2.4, 2.2.4.2)
    NPRR1013 (1.3.1.4, 1.3.3)
    NPRR1007 (3.6.1, 3.8.1, 3.8.2, 3.8.3, 3.14.4.1)
    NPRR1008 (4.4.4, 4.4.7.4)
    NPRR1010 (6.1, 6.3, 6.3.1, 6.3.2, 6.4.7.1, 6.5.1.1, 6.5.1.2, 6.5.7, 6.5.9.2, 6.5.9.3.3, 6.5.9.3.4, 6.5.9.4)
    NPRR1011 (8.1.1.1, 8.1.1.2)

## Slide 15: RTCRR Review Schedule & Progress to Date
7/22/2020 RTCTF Consensus (46 items):
  RTM - AS Deployment (Round 3)
    NPRR1010 (6.5.7.4.1, 6.5.7.6.1, 6.5.7.6.2, 6.5.7.6.2.1, 6.5.7.6.2.2, 6.5.7.6.2.3, 6.5.7.6.2.4, 6.5.9.4.2)
  RTM – General Update (Round 3)
    NPRR1010 (6.4.9.1.2)
  RTM Settlement (Round 2)
    NPRR1007 (3.5.2.1, 3.5.2.2, 3.5.2.3, 3.5.2.4, 3.5.2.5, 3.5.2.6, 3.5.2.7)
    NPRR1010 (6.6.1, 6.6.1.1, 6.6.1.2, 6.6.1.6, 6.6.1.7, 6.6.3.1, 6.6.3.7, 6.6.3.9, 6.6.5.1, 6.6.5.1.1.3, 6.6.5.1.1.4, 6.6.5.2, 6.6.5.2.1, 6.6.5.3, 6.6.5.3.1, 6.6.5.4, 6.6.5.5, 6.6.5.5.1, 6.6.5.6, 6.6.12.1, 6.7.1, 6.7.2, 6.7.2.1, 6.7.2.2, 6.7.3, 6.7.4)
    NPRR1012 (9.5.3, 9.19.1)
  Additional Comments for Renaming of Base Point Deviation (Round 1)
    NPRR1007 (3.8.3) - Initial consensus on 6/29/20
    NPRR1011 (8.1.1.1) - Initial consensus on 6/29/20

## Slide 16: Overall RTC Delivery Schedule
Draft Timeline
There are several items/policies, beyond RTCRRs, that must be addressed prior to the implementation of RTC—e.g.:
  Proxy Offer Curves;
  RUC AS Demand Curves;
  Transitional language for RTC go-live (if any);
  ORDC/RTC results comparison; and
  Target dates for MP detailed requirements (e.g., SCADA changes, XML changes, Market Trials plans).