## Slide 1
Resource Integration Topics
Jay Teixeira
ERCOT
Resource Integration Workshop
August 25, 2020

## Slide 2: Quarterly Stability Assessment (QSA)
Planning Guide 5.9
Next Deadline for QSA
If a GINR is not included in QSA, its Initial Synchronization date will be automatically delayed to the next quarter
All-Inclusive Generation Resource Initial Synchronization Date | Last Day for an IE to meet prerequisites as listed in paragraph (4) below | Completion of Quarterly Stability Assessment
Upcoming January, February, March | Prior August 1 | End of October
Upcoming April, May, June | Prior November 1 | End of January
Upcoming July, August, September | Prior February 1 | End of April
Upcoming October, November, December | Prior May 1 | End of July

## Slide 3: Quarterly Stability Assessment (QSA)
Planning Guide 5.9, Quarterly Stability Assessment
Issue’s seen in previous QSA’s
  10 day comment period for FIS
    Needs to be complete before QSA deadline
    TSPs need to plan for it
  Dynamic Model Review
    Dependent on FIS Stability study
    Need to meet PG 6.9 15 to 30 days prior to QSA deadline
PSSE Model Quality Test Required
TSAT Model Required

## Slide 4: GINR Time Line (Fastest)

## Slide 5: Meaning and uses of HRL
High Reasonability Limit - RARF Glossary – description:
  A theoretical value of net generation above which, the generator is not expected to operate under most conceivable conditions. This value is used by ERCOT market systems to validate COP submissions of HSL, telemetered HSL, and certain offers which may have been entered in error by the QSE. The HRL is also used in settlements to deconstruct prices at a CCT logical resource node.”
HRL is used as a limit for telemetered unit net MW output as well as HSL – telemetry alerts if telemetered values exceed HRL
Registering a unit’s HRL in the RARF has been limited to the SGIA MW and FIS studied MW.
If the SGIA MW and FIS MW don’t represent the capability of the unit for operating temperatures that are less than maximum temperatures, then the HRL based on SGIA and FIS may limit output below the actual ability to produce MW.

## Slide 6: Meaning and uses of HRL
ERCOT Business Practice – Current Operating Plan Practices By Qualified Scheduling Entities:
  Section 3.1 Intermittent Renewable Resources
    Page 11
      “QSEs that submit COPs for WGRs and/or PVGRs for hours which do not have a forecast from ERCOT, it is recommended that the resource’s High Reasonability Limit (HRL) be used as its COP HSL value for these hours. Once these hours fall within the 168-hour rolling window for forecasting, ERCOT’s systems will automatically start updating the COP HSL value with the most recent forecast for the resource.”

## Slide 7: Active PGRR’s
NPRR973, NOGRR196, PGRR074, RRGRR022 – Add Definitions for Generator Step-Up and Main Power Transformer - Approved by BOD Aug 11
PGRR076 – Improvements to Generation Resource Interconnection or Change Request (GINR) Process – Approved by BOD Aug 11 except paragraph (3) of Section 5.2.1 and paragraph (4)(b)(vi) of Section 5.7.1 which are upon system implementation

## Slide 8: Other contact information
ResourceIntegrationDepartment@ercot.com is distribution list for Resource Integration department

## Slide 9: Questions?
Thank you!