## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
September 10, 2020

## Slide 2
Project Portfolio Update
  Recent / Upcoming Project Implementations
  2020 Release Targets
  2020 Project Spending Forecast
  Project Prioritization Next Steps
  Priority/Rank Options for Revision Requests with Impacts
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Implementations
2020 August Release – Off-Cycle – 8/1/2020 Complete
  NPRR933 – Reporting of Demand Response by Retail Electric Providers and Non-Opt-In Entities
  RRGRR021 – Dynamic Model Requirement for TSAT
2020 August Release – R4 – 8/4/2020 – 8/6/2020 Complete
  NPRR935(a) – Post All Wind and Solar Forecasts
    Section 4.2.2 (1)(6) and Section 4.2.5
  NPRR951 – Active and Inactive SCED Constraint Reporting
  NPRR977 – Create MIS Posting for RUC Cancellations
2020 September Release – Off-Cycle – 9/3/2020 Complete
  RIOO – RARF Replacement – View/Update – Initial Release
2020 November Release – Off-Cycle In Flight
  SCR804 – ERCOT GridGeo Access for Transmission Operators – 11/12/2020
  RIOO – RARF Replacement – View/Update – Follow-Up Release – 11/12/2020
  Enterprise Content Management System (ECMS) Phase 2 – 11/16/2020
2020 November/December Release – Off-Cycle In Flight
  MMS/OS Tech Refresh
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2020 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/4 – 2/6 | April 3/31 – 4/2 | May 5/26 – 5/29 | August 8/4 – 8/6 | October 10/13 – 10/15 | December 12/8 – 12/10
NPRR873 SCR797 NPRR877 Ph2 NPRR968 NPRR943 EMIL Web Interface NPRR863 FFR NPRR960 NOGRR187 OBDRR011 | SCR802 NPRR928 NPRR929 NPRR978(a) NPRR988 NPRR953 | NPRR856 NPRR884 OBDRR006 SCR803 NPRR887 NPRR907 NPRR985 RMGRR163 NPRR837 NPRR930(a) NPRR933 RRGRR021 | NPRR935(a) NPRR951 NPRR977 SCR781(a) RRGRR016 RRGRR019 | NPRR902 MIS Go-Live SCR804 RIOO R2 MMS/OS Refresh NPRR863 ECRS | SCR806 NPRR857 NPRR902 NPRR904 NPRR905 NPRR917 NPRR936 NPRR941 NPRR963 NPRR971 NPRR978 NPRR986 NPRR998 OBDRR009 PGRR070(b) SCR781(b) SCR799
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
E
E
E
R1
R2
R3
R4
R5
R6
3/1
NPRR930(a) – O&M portion
NPRR935(a) – Sections 4.2.2 (1) (6), 4.2.5
NPRR935(b) – Sections 2.1, 2.2, 4.2.3
NPRR978(a) – Initial report decommissions
PGRR070(b) – Remaining PGRR language
SCR781(a) – View / Edit capability
MMS/OS Upgrade “Chill”
MMS/OS Upgrade “Freeze”
ü
ü
ü
November / December
Off-Cycle
1/1
2021 Go-Lives
P
NS
P
NS
E
NS
NS
NS
NS
E
P
E
NS
E
E
NS
1/19
E
ü
ü
TBD Items | 2017 | 2018 | 2019 / 2020
 | NPRR702, NPRR829 | NPRR825(b), NPRR867, NPRR841 | NPRRs: 826, 879, 885, 918, 930, 935(b), 939, 962, 965, 974, PGRR066, SCR800, SCR805
ü
CMM Release 2a
1/30
8/1
November
RIOO – 9/3
RARF Go-Live - View/Update
ü
ü
ü
ü
ü
ü
ü
ü
ü
5/1
ü
7/1
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
2024 Go-Lives
ü
ü
ü
On Hold
ü
ü
ü
ü
ü

## Slide 5: 2020 Project Spending
2020 PPL Budget = $29.0M
“Potential Demand” represents internal ERCOT projects that have not been fully approved

## Slide 6: Project Prioritization Next Steps
Thank you to PRS members for your input in August
ERCOT suggests we continue to maintain the PPL as we have in the past; no restructuring required
PRS prioritization input helped inform ERCOT of priority items as we build 2021 project plans
ERCOT will refer to the posted list as we seek to fit additional items into the 2021 plan
  Important: Limit impact to Passport and summer 2021 initiatives
  Seek to leverage efficiencies by bundling related items
Key Point: Unless something is very high priority, we should target new items for 2021, 2022 or even later project starts due to all the high priority activity already in the project queue

## Slide 7: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR999 | DC Tie Ramp Limitations | N/A | N/A | <$5k O&M – no project required
NPRR1025 | Remove Real-Time On-Line Reliability Deployment Price from Ancillary Service Imbalance Calculation | 2020 | 3015 | $15k-$25k – S&B impacts Candidate to combine w/NPRR987
NPRR1031 | Notices for Curtailment of Load | TBD | TBD | Additional time requested to complete IA
NPRR1035 | DC Tie Schedules Protected Information Expiry and Posting | 2021 | 3230 | $20k-$40k – Reporting impacts
SCR811 | Addition of Intra-Hour PhotoVoltaic Power Forecast to GTBD Calculation | TBD | TBD | $60k-$90k – MMS & EMS impacts Pending urgency vote
Options for…
PPL Rank Information
Next available 2021 Rank in Business Strategy = 3230
Next available Rank in Regulatory = 320
Note
Items in the Regulatory section of the PPL are not tracked against the market Revision Request funding allocation