## Slide 1
Resource Integration Topics
Jay Teixeira
ERCOT
Resource Integration Workshop
September 25, 2020

## Slide 2: Quarterly Stability Assessment (QSA)
Planning Guide 5.9
Next Deadline for QSA
If a GINR is not included in QSA, its Initial Synchronization date will be automatically delayed to the next quarter
All-Inclusive Generation Resource Initial Synchronization Date | Last Day for an IE to meet prerequisites as listed in paragraph (4) below | Completion of Quarterly Stability Assessment
Upcoming January, February, March | Prior August 1 | End of October
Upcoming April, May, June | Prior November 1 | End of January
Upcoming July, August, September | Prior February 1 | End of April
Upcoming October, November, December | Prior May 1 | End of July

## Slide 3: Quarterly Stability Assessment (QSA)
Planning Guide 5.9, Quarterly Stability Assessment
Issue’s seen in previous QSA’s
  10 day comment period for FIS
    Needs to be complete before QSA deadline
    TSPs need to plan for it
  Dynamic Model Review
    Dependent on FIS Stability study
    Need to meet PG 6.9 15 to 30 days prior to QSA deadline
PSSE Model Quality Test Required
TSAT Model Required – If PSSE model is UDM, then TSAT model should be UDM.

## Slide 4: GINR Time Line (Fastest)

## Slide 5: Conventional MW Ratings to Use When Generator and Turbine Ratings Different
The capacity rating of a conventional generation resource is typically expressed in MW, not in MVA. This is because for conventional synchronous gas/steam turbine generators, the prime mover/turbine generates only active power. In contrast, the electrical generator can generate both active and reactive power. Therefore, turbine is always rated in MW and generator has both a MVA rating and a MW rating.
For the Max rating of the project In RIOO, it should be the MW rating of the generation resource as a whole (the smaller of turbine and generator MW ratings) because that’s the power coming out of the generator (at the generator terminal) and being delivered to the grid.

## Slide 6: Conventional MW Ratings to Use When Generator and Turbine Ratings Different
For power flow, the machine Pmax is the MW rating, corresponding to the smaller of turbine and generator MW rating. Pmax is used to dispatch the generator. The machine also has a MVA base/rating, which the generator dynamic model parameters are based.
The turbine is mostly expressed in the governor model, in which a turbine MW rating can be specified. The turbine impacts the H value in the generator model because it shares the shaft with the generator rotor, but its contribution in H is based on generator MVA base.
Bottom-line, if the MVA rating of the generator is different than the turbine rating, the lower of the two should be entered as MW rating of the project in RIOO. The MW rating in RIOO is the maximum active power at the generator terminals.

## Slide 7
UNIT INFO – AGR Tab for ESR/BESS
This tab has been filled out for BESS/ESR in order to reflect inverter information
This tab is only meant for reciprocating engines to aggregate as an AGR and is used for settlements purposes
For all others, ONLY column A needs to be filled out in the future

## Slide 8: Active PGRR’s
PGRR086 and RRGRR027, submitted by Enel Green Power North America on September 18, 2020, Clarify Models Required to Proceed with an FIS. Next up at ROS where the next meeting is October 8, 2020.

## Slide 9: Other contact information
ResourceIntegrationDepartment@ercot.com is distribution list for Resource Integration department

## Slide 10: Questions?
Thank you!