## Slide 1
NPRR902 Implementation Update
Jonathan Levine
ERCOT Senior Corporate Counsel
Technical Advisory Committee Meeting
September 23, 2020

## Slide 2: NPRR902 Implementation Update
Implementation Delay
NPRR902, ERCOT Critical Energy Infrastructure Information, was approved by the ERCOT Board in December 2019 (Priority 2020; Rank 2930)
At the June 24, 2020 TAC meeting, we reported that implementation was scheduled for 2020 R5 (10/13-10/15)
Presentation from that meeting includes a summary of NPRR902, the requirement for ECEII-eligible Digital Certificates, and categories of MIS Secure Area and Certified Area items preliminarily designated as ECEII
Project has encountered delays during planning; implementation now expected 2021 R1 (anticipated to be early to mid-February 2021)
Workforce constraints within ERCOT (i.e., individuals/teams focused on higher priority projects)
Technical solution for MIS Certified Area is more complicated than expected

## Slide 3: NPRR902 Implementation Update
Upcoming Steps
ERCOT Internal Implementation Work (ECEII designation confirmation, system changes, training preparation, etc.)
Market Participant Training: November-December 2020
Expected NPRR902 Implementation: February 2021 (R1)
  ERCOT will issue courtesy Market Notice 30 days prior to implementation and required Market Notice 10 days prior to implementation
Follow-up Revision Requests to reclassify non-ECEII items from MIS Secure Area to MIS Public Area (“ERCOT website” after NPRR1039)

## Slide 4: NPRR902 Implementation Update
Market Participant Training
Format for training still under consideration. Anticipate there will be at least one workshop.
Training topics:
User Security Administrator (USA) assignment of Digital Certificates that are ECEII eligible and non-eligible
Review of new/clarified Market Participant and ERCOT responsibilities pursuant to language added by NPRR902
Review of MIS Secure Area and Certified Area information designated as ECEII
Other suggestions for topics?

## Slide 5: NPRR902 Implementation Update
Questions?
Please feel free to email Jonathan.Levine@ercot.com with questions or other feedback