| PGRR Number | 083 | PGRR Title | Add RPG Project Number and TPIT Revisions |
| --- | --- | --- | --- |
| Date of Decision |  | September 3, 2020 |  |
| Action |  | Recommended Approval |  |
| Timeline |  | Normal |  |
| Proposed Effective Date |  | To be determined |  |
| Priority and Rank Assigned |  | To be determined |  |
| Planning Guide Sections Requiring Revision |  | 3.1.5, Regional Planning Group Comment Process 6.4.3, TSP Responsibilities |  |
| Related Documents Requiring Revision/Related Revision Requests |  | ERCOT Steady State Working Group (SSWG) Procedure Manual |  |
| Revision Description |  | This Planning Guide Revision Request (PGRR) adds a requirement for ERCOT to assign a Regional Planning Group (RPG) project number for projects submitted for RPG review. It also removes the specification of some Transmission Service Provider (TSP) provided Transmission Project Information Tracking (TPIT) information from the Planning Guide. The ROS-approved SSWG Procedure Manual will be updated to contain the complete specification for TSP-provided TPIT information. |  |
| Reason for Revision |  | Addresses current operational issues. Meets Strategic goals (tied to the ERCOT Strategic Plan or directed by the ERCOT Board). Market efficiencies or enhancements Administrative Regulatory requirements Other: Allows for better tracking of RPG projects over time. (please select all that apply) |  |
| Business Case |  | The creation of an RPG project number will allow ERCOT to better track RPG project information after RPG review of the project has been completed. Moving the specification of TPIT information to the SSWG Procedure Manual will allow for that information to be specified in one central location that is controlled by a stakeholder body (ROS). |  |
| ROS Decision |  | On 8/6/20, ROS voted unanimously via roll call to table PGRR083 and refer the issue to the Planning Work Group (PLWG). All Market Segments were present for the vote. On 9/3/20, ROS voted unanimously via roll call to recommend approval of PGRR083 as submitted. All Market Segments were present for the vote. |  |
| Summary of ROS Discussion |  | On 8/6/20, participants expressed concern for the relocation of TPIT information to the SSWG Procedure Manual and requested additional discussion at PLWG. On 9/3/20, participants discussed multiple proposed concepts in regards to transmission project updates. |  |

| Sponsor |  |
| --- | --- |
| Name | Jeff Billo |
| E-mail Address | Jbillo@ercot.com |
| Company | ERCOT |
| Phone Number | 512-248-6334 |
| Cell Number |  |
| Market Segment | Not applicable |

| Market Rules Staff Contact |  |
| --- | --- |
| Name | Jordan Troublefield |
| E-Mail Address | Jordan.Troublefield@ercot.com |
| Phone Number | 512-248-6521 |

| Comments Received |  |
| --- | --- |
| Comment Author | Comment Summary |
| None |  |

Market Rules Notes

None

Proposed Guide Language Revision

- 3.1.5	Regional Planning Group Comment Process

(1)	Any stakeholder may initiate an RPG project review in accordance with Protocol Section 3.11.4.1, Project Submission.  All project submissions should be sent electronically to rpg_submittal@ercot.com.  The RPG project review consists of the following steps:

(a)	ERCOT will provide electronic copies of RPG project review submittals by email to the RPG within five Business Days of receipt and solicit comments or questions from the RPG;

(b)	ERCOT will assign a unique project identification number (RPG project number) to the RPG project review submittals according to the following convention:

yrRPGxxx

where:	       yr is the calendar year the RPG project is submitted

RPG indicates RPG project

xxx is a sequence number beginning with 001 (reset for each year)

(c)	All concerns/questions or objections about the submitted project by any stakeholder or ERCOT should be submitted by email to the RPG within 15 Business Days after ERCOT’s transmittal to the RPG;

(d)	Each Entity providing comments should provide a “single” complete comment about each project by the end of the 15-Business Day comment period rather than sending multiple comments at various times or from various individuals;

(e)	Any questions related to data deficiency should be submitted to ERCOT and the submitting party immediately;

(f)	If concerns or objections about a project are received during the 15-Business Day comment period, the project will be put into “study mode.”  During study mode, the submitting party shall respond to any concerns or objections and provide additional information, if necessary, by email to the RPG until all concerns are resolved or until ERCOT assesses that a reasonable effort has been made to resolve all concerns or objections.  A submitting party may make modifications to a Tier 3 project to address concerns or objections without having to resubmit the project so long as the modifications do not result in the project being classified as a Tier 1 or 2 project.  Study mode shall end no later than 20 Business Days following the end of the comment period, unless ERCOT finds good cause to extend study mode;

(g)	The submitting party should answer all questions and respond to all concerns in a timely manner;

(h)	Comments should be based on Good Utility Practice and sound engineering judgment. Suggestions should be able to be implemented by the TSP constructing and operating the project; and

(i)	ERCOT will post all project submissions, the comments received, and other information and databases associated with submitted transmission projects on the MIS Secure Area.

(j)	Comments received after the 15 Business Day comment period may be considered by ERCOT or the submitting party, but a response is not required.

6.4.3	TSP Responsibilities

(1)	The TSP responsible for submitting model data used in the SSWG case build or SSWG case update shall provide information for its transmission projects to ERCOT.

(2)	The TSP shall provide transmission project data for inclusion in the TPIT report as specified in the ERCOT Steady State Working Group Procedure Manual

.