## Slide 1
Real-Time Co-optimization Task Force Update to ROS
Matt Mereness
RTCTF Chair
October 8, 2020

## Slide 2: RTC Revision Requests (RTCRRs) Summary
Based on Board-approved RTC Key Principles (KPs), ERCOT developed and released the following NPRRs, NOGRR, and OBDRR with a single Impact Analysis (IA).
RTCRRs released March 25, 2020 | Pages 549 total
NPRR1007- RTC NP3- Management Activities for the ERCOT System | 62
NPRR1008- RTC NP4- Day-Ahead Operations | 65
NPRR1009- RTC NP5- Transmission Security Analysis and Reliability Unit Commitment | 39
NPRR1010- RTC NP6- Adjustment Period and Real-Time Operations | 248
NPRR1011- RTC NP8- Performance Monitoring | 49
NPRR1012- RTC NP9- Settlement and Billing | 15
NPRR1013- RTC NP 1, 2, 16, 25- Overview, Definitions/Acronyms, Registration and Qualification of MPs, and Market Suspension and Restart | 24
NOGRR211- RTC Nodal Operating Guides 2 and 9- System Operations and Control Requirements and Monitoring Programs | 21
OBDRR020- RTC - Methodology for Setting Maximum Shadow Prices for Network and Power Balance Constraints | 26

## Slide 3: RTCRR Review Schedule & Progress to Date
Detailed RTCTF schedule for reviewing the RTCRR language is posted on the RTCTF page, and excerpt below.
Of the 197 total Protocol/OBD sections under review, RTCTF has reached consensus on 183 sections to date (92% complete).

## Slide 4: RTCRR Review Schedule & Progress to Date
Schedule of 2020 meetings for RTCRRs:
Mar. 11 – RTCTF (Plan and logistics for RR review)
Apr. 8 – RTCTF (Review detailed plan, and begin review process)
Apr. 30 – RTCTF
May 11 – Special RTCTF for Potential Design Flaw- AS Price Cap discussion
May 20 – RTCTF
Jun. 10 – RTCTF
Jun. 22 – Special RTCTF for Ancillary Service Deployments
Jun. 29 – RTCTF
Jul. 15 – Special RTCTF for AS Deployment Expectations & Durations
Jul. 22 – RTCTF
Aug. 12 – RTCTF
Sep. 9 – RTCTF
Sep. 28 – RTCTF
Oct. 21 – RTCTF
Nov. 5 – ROS
Nov. 11 – PRS
Nov. 12 – RTCTF (if needed)
Nov. 17 – CWG
Nov. 18 – TAC
Dec. 8 – ERCOT Board
Requesting Urgency and ROS Vote for NOGRR211 at November 5, 2020 meeting

## Slide 5: Next Steps
RTCTF is still completing NOGRR211 discussions 10/21
  TAC direction for MPs to participate at RTCTF.
  MPs can send Revision Request redlines for RTCTF consideration to DMaggio@ercot.com & MMereness@ercot.com to document and discuss at subsequent RTCTF meetings.
Any RTCTF changes will be filed as cumulative ERCOT Comments to NOGRR211, including request for Urgency.
NOGRR211 will be ready for ROS approval at the November 5 ROS meeting.
Any questions?
  Can also email MMereness@ercot.com

## Slide 6: Appendix
RTCRR Review Process
Updates to Telemetry From/To QSE in RTC
TAC Direction on RR changes different from Key Principles
Harmonizing RTC and Battery Energy Storage
Overall RTC Delivery Schedule

## Slide 7: RTCRR Review Schedule and Process
7-days prior #1
ERCOT posts agenda and RTCRRs sections to be reviewed
7-days prior #2
MP redlines due and posted to address concerns or alternatives
During meeting, MPs discuss any concerns or alternatives
7-days prior #3
MPs must document concerns and alternative language prior to meeting, and be prepared to discuss.
7-days prior #3
Non-consensus materials posted for options on language to be considered.
Meeting #1 Meeting #2 Meeting #3
TAC will be updated monthly. If irresolvable issues occur at RTCTF, the RTCTF Chair can request TAC endorsement to resolve.
2-days prior #2
ERCOT responds to MP questions and redlines
Consensus Items Tracked in Spreadsheet as Complete
Resolved Items Tracked in Spreadsheet as Complete
ERCOT will file cumulative RTCRR comments reflecting when consensus on sections achieved. (Also tracked in summary spreadsheet)

## Slide 8: Updates to Telemetry From/To QSE in RTC (Updated 5/7/2020)
Resource Specific To QSE |  | 
Unit Related |  | A/S Related
Base Point (BP) |  | Non-Spin Deployed (NDPL)
Locational Marginal Price (LMP) |  | RRS Deployed (RDPL) [NCLR]
Curtailment (SBBH) |  | Regulation Up Award, Regulation Down Award
SCCT Status (SCCT) |  | Responsive Reserve Award
Updated Desired BP (UDBP) |  | ECRS Award, Non-Spin Award
 |  | Regulation Up Deployment, Regulation Down Deployment
 |  | Updated Desired SP (UDSP)
Resource Specific From QSE |  |  | 
Unit Related |  |  | A/S Related
High/Low Sustained Limits (HSL, LSL) | AVR Status (AVR) |  | FRRS Up/Down Participation Factor (FUPF, FDPF)
High/Low Emergency Limit (HEL, LEL) | Dynamically Scheduled Resource Schedule (DSRS)[Gen] |  | FRRS Up/Down Responsibility (FURS, FDRS)
Energy (Normal) Up/Down Ramp Rate (NURR, NDRR) | Lower/Raise Block Status (LBST, RBST) [Gen] |  | Regulation Up/Down Participation Factor (RUPF, RDPF)
Emergency Up/Down Ramp Rates (EURR, EDRR) | PSS Status (PSS) |  | Regulation Up/Down Responsibility (RURS, RDRS)
Net MW/MVAR (MW (aka NPF for CCP), MVAR) | POI kV Measurement/Target (KVM, KVT) |  | Responsive Reserve Responsibility/Schedule (RRRS, RRSC)
Gross MW/MVAR (GMW, GMV) | Scheduled Power Consumption (SPC, SPC2) [CLR] |  | High Set Under Frequency Relay (HSUF) [NCLR]
Resource Status (RST) | Storage Resource Charge/Discharge Data (MXCP, MXDP, MXOD, SOC) |  | Non-Spin Responsibility/Schedule (NSRS, NSSC)
CCP Config No (CCC) | IRR MET Data (DEG, IRAD, MPH, PRES, PTMP, TEMP) |  | Regulation Up/Down Ramp Rate (based on 5-min blended)
Non Frequency Responsive Capacity (NFRC) | IRR Turbine/Panel Availability (NTOF, NTON, NTUN) |  | RRS PFR/FFR/UFR Capability
Load Resource Breaker Status (LRCB) [NCLR] | CCP Frequency Responsive Capacity High/Low Limit, Frequency Responsive MW |  | Non-Spin Ramp Rate (based on 30-min blended)
Max/Low Power Consumption (MPC, LPC) [CLR, NCLR] |  |  | ECRS Ramp Rate (based on 10-min blended)
 |  |  | RRS/ECRS Self Provision (based on DAM Award and AS trades) [NCLR]
 |  |  | ECRS Responsibility, Schedule
QSE Specific To QSE
A/S Related
Regulation Up/Down MW (REGU, REDG)
FRRS Up/Down MW (FURQ, FDRQ)
Responsive Reserve Gen/ONRR/FFR Deployment (RR, ONRR, FFR)
ECRS Deployment (Gen, ONRR)
*Base telemetry list in this table has been created using ERCOT Nodal ICCP Communications Handbook (note also included are some potential changes related to NPRR 863 Ph2 (reflected in green color).
**RTC related changes that are identified in this list (reflected in red color) are based on KP1.3, 1.4, 1.5.

## Slide 9: TAC Direction on RR changes different from Key Principles (TAC Discussion May 27, 2020)
Below are the following criteria to modify RTCRRs beyond the scope of the RTC KPs if a market design flaw or error was discovered following Board approval of the RTC KPs:
  The modification complies with PUC directives;
  The modification will not incur additional RTC project costs or schedule delays; and
  The modification will not delay timely implementation of RTCRRs (i.e., will not prevent the Board from considering the NPRR at the December 8, 2020 Board meeting).
(Step-by-step process described on next slide)

## Slide 10: TAC Direction on RR changes different from Key Principles (TAC Discussion May 27, 2020)
A Market Participant has the right to express concerns with a RTCRR.
  Any MP may file comments to modify a RTCRR beyond the scope of the Board-approved KPs.
  In comments to modify an RTCRR, the submitting party shall explain how the revisions meet the criteria proposed on the previous slide.
RTCTF will provide:
  The technical forum (e.g., an extra off-cycle meeting) for discussion of the proposed RTCRR changes with the understanding that RTCTF consensus is not practical and will not occur.
At TAC:
  RTCTF Chair will advise TAC leadership of any RTCRR Comments that propose to modify the scope of the KPs beyond that which was approved by the Board, and
  Request time for the MP to present to TAC for consideration, as well as another MP to present the counterpoints (if any) as to why the existing KP should continue to be maintained and aligned with RTCRRs.
  TAC may take a straw poll to endorse the proposed NPRR comments; the vote would not be binding and therefore non-appealable, but would classify the modified/added concept as valid.
If TAC endorses the alternative, the RTCTF Chair would update the Board of the straw poll decision.
The RTCRR comments would subsequently be considered at PRS, TAC, and ultimately the ERCOT Board as consistent with Protocols Section 21 process.

## Slide 11: Harmonizing RTC & Battery Energy Storage
RTC KPs
RTC RRs
RTC IA
BESTF KTCs
Other BES RRs
Single Model IA
Single Model NPRR
_____________
For overlapping sections, authors use
RTC Redlines
+
ESR Redlines
PRS
TAC
BOD
BESTF Meetings
PRS
TAC
BOD
RTC Redline Changes
RTC Redline Changes
RTC Redline Changes
Approval of RTC
RRs and IA
Approval of Single Model NPRR & IA
(acknowledging subset of identical RTC redlines to support ESR redlines).
RTCTF Meetings

## Slide 12: Harmonizing RTC & Battery Energy Storage (BES)
RTCTF & BES Task Force (BESTF) meetings are purposefully adjacent or straddling PRS due to inter-relationships of RTC & BES concepts
RTCTF
March 11
April 8
April 30
May 20
June 10
June 29
July 22
August 12
September 9
September 28
October 21
November 12 (if needed)
BESTF
March 13
April 16
May 1
May 21
June 12
June 30
July 23
August 14
September 11
September 29
October 22
November 13 (if needed)
November 5 (ROS)
November 11 (PRS)
November 18 (TAC)
December 8 (Board of Directors)

## Slide 13: Overall RTC Delivery Schedule
Draft Timeline
There are several items/policies, beyond 2020 RTCRRs, that must be addressed prior to the implementation of RTC—e.g.:
  Proxy Offer Curves;
  RUC AS Demand Curves;
  Transitional language for RTC go-live (if any);
  ORDC/RTC results comparison; and
  Target dates for MP detailed requirements (e.g., SCADA changes, XML changes, Market Trials plans).