## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
October 15, 2020

## Slide 2
Project Portfolio Update
  Recent / Upcoming Project Implementations
  2020 Release Targets
  2021 Release Targets
  BES and DGR Pre-Passport Projects
  2020 Project Spending Forecast
  Priority/Rank Options for Revision Requests with Impacts
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Implementations
2020 September Release – Off-Cycle – 9/3/2020 Complete
  RIOO – RARF Replacement – View/Update – Initial Release
2020 October Release – R5 – 10/10/2020 – 10/13/2020 In Flight
  No Revision Requests in this release
2020 November Release – Off-Cycle In Flight
  SCR804 – ERCOT GridGeo Access for Transmission Operators – 11/12/2020
  RIOO – RARF Replacement – View/Update – Follow-Up Release – 11/12/2020
  Enterprise Content Management System (ECMS) Phase 2 – 11/16/2020
2020 November/December Release – Off-Cycle In Flight
  MMS/OS Tech Refresh
2020 December Release – R6 – 12/8/2020 – 12/10/2020 In Flight
  SCR806 – Adding QSE and DME Information to Disclosure Reports
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2020 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/4 – 2/6 | April 3/31 – 4/2 | May 5/26 – 5/29 | August 8/4 – 8/6 | October 10/13 – 10/15 | December 12/8 – 12/10
NPRR873 SCR797 NPRR877 Ph2 NPRR968 NPRR943 EMIL Web Interface NPRR863 FFR NPRR960 NOGRR187 OBDRR011 | SCR802 NPRR928 NPRR929 NPRR978(a) NPRR988 NPRR953 | NPRR856 NPRR884 OBDRR006 SCR803 NPRR887 NPRR907 NPRR985 RMGRR163 NPRR837 NPRR930(a) NPRR933 RRGRR021 | NPRR935(a) NPRR951 NPRR977 NPRR955 NOGRR183 SCR781(a) RRGRR016 RRGRR019 | MIS Go-Live SCR804 RIOO R2 MMS/OS Refresh | SCR806
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
E
E
E
R1
R2
R3
R4
R5
R6
3/1
NPRR930(a) – O&M portion
NPRR935(a) – Sections 4.2.2 (1) (6), 4.2.5
NPRR935(b) – Sections 2.1, 2.2, 4.2.3
NPRR978(a) – Initial report decommissions
PGRR070(b) – Remaining PGRR language
SCR781(a) – View / Edit capability
MMS/OS Upgrade “Chill”
MMS/OS Upgrade “Freeze”
ü
ü
ü
November / December
Off-Cycle
1/1
P
1/19
E
ü
ü
ü
CMM Release 2a
1/30
8/1
November
RIOO – 9/3
RARF Go-Live - View/Update
ü
ü
ü
ü
ü
ü
ü
ü
ü
5/1
ü
7/1
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
10/1
ü
ü

## Slide 5: 2021 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February TBD | April TBD | May TBD | August TBD | October TBD | December TBD
NPRR902 NPRR978 | NPRR905 NPRR971 NPRR986 | NPRR829 NPRR904 NPRR930 NPRR962 NPRR974 NPRR998 NPRR1019 OBDRR009 |  | SCR781(b) | FFR Advancement (NPRR863 FFR) NPRR863 ECRS
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
SCR781(b) – “Add” capability
TBD Items | 2017 | 2018 | 2019 / 2020 / 2021
 | NPRR702 | NPRR825(b), NPRR867, NPRR841 | RRs: 826, 857, 879, 885, 918, 935(b), 936, 939, 941, 965, 1020, 1030, PGRR066, SCR799, SCR800, SCR805
P
P
I
I
I
NS
NS
I
I
E
E
E
On Hold
2024 Go-Lives
RIOO – Q4 2021
RARF Add Functionality Go-Live
TBD Go-Live
E

## Slide 6: BES and DGR Pre-Passport Projects
In October 2020, ERCOT is kicking off two projects to deliver several Revision Requests relating to BES and DGR
  PR353-01 BES Combo Model Implementation Strategy
    NPRR963 – Base Point Deviation Settlement & Deployment Performance Metrics for ESRs (Combo Model)
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    NPRR989 – BESTF-1 ESR Technical Requirements
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    NPRR1026 – BESTF-7 Self-Limiting Facilities and Self-Limiting Resources *
    NOGRR204 – Related to NPRR989, BESTF-1
    NOGRR208 – Related to NPRR1002, BESTF-5
    OBDRR017 – Related to NPRR987, BESTF-3
    RRGRR023 – Related to NPRR1002, BESTF-5 *
  PR354-01 DGR/DESR Implementation Strategy
    NPRR917 – Nodal Pricing for SODGs and SOTGs
    NPRR1016 – Clarify Requirements for DGRs and Distribution Energy Storage Resources (DESRs)
    PGRR082 – Revise Section 5 and Establish Small Generation Interconnection Process *
    RRGRR026 – Related to NPRR1016, Clarify Requirements for DGRs and DESRs
Since these projects are merging multiple RRs, it will take a few months before we can set target go-live dates for these two projects
BES: Battery Energy Storage
DGR: Distributed Generation Resource
ESR: Energy Storage Resource
* Expected to be added to scope upon Board approval

## Slide 7: 2020 Project Spending
2020 PPL Budget = $29.0M
“Potential Demand” represents internal ERCOT projects that have not been fully approved

## Slide 8: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
SCR812 | Create Intermittent Renewable Generation Integration Report | 2021 | 3250 | $30k-$60k, 5-7 months Impact Areas: Reporting Target 2021 when resources are available without disrupting “summer 2021” projects
NPRR1032 | Consideration of Physical Limits of DC Ties in RUC Optimization and Settlements | 2021 | 3260 | $100k-$150k, 5-8 months Impact Areas: MMS, S&B, Reporting Look for a window after “summer 2021” RRs Risk of conflicts with BES/DGR/RTC
NPRR945 | Net Metering Requirements | 2021 | 3270 | $10k-$20k, 3-4 months Impact Areas: RIOO-RS, ERCOT.com Add to end of 2021 list and work into plan without disrupting in-flight projects
Options for…
PPL Rank Information
Next available 2021 Rank in Business Strategy = 3250
Next available Rank in Regulatory = 320
Note
Items in the Regulatory section of the PPL are not tracked against the market Revision Request funding allocation