## Slide 1
Battery Energy Storage Task Force (BESTF) Update to TAC
Kenneth Ragsdale
October 28, 2020

## Slide 2: Outline of BESTF Update
TAC Voting Items ---- None
Dashboards
Next Steps
Appendix

## Slide 3: Battery Energy Task Force Status Dashboard (as of October 22, 2020)
Chart: # Items
| KTC-1 | KTC-2 | KTC-3 | KTC-4 | KTC-5 | KTC-6 | KTC-7 | KTC-8 | KTC-9 | KTC-10 | KTC-11 | KTC-12 | KTC-13 | KTC-14 | KTC-15
Meeting 1
Meeting 2
Not Started | 5
Meeting 3
BESTF Consensus
Approved by TAC | 1 | 5 | 7 | 1
Revision Request In Progress | 1 | 1 | 4 | 14 | 11 | 2
Revision Request Approved | 1 | 2 | 4 | 4 | 1 | 1 | 1 | 1
Closed | 1 | 1 | 1 | 1 | 1 | 1

## Slide 4: Battery Energy Task Force Status Dashboard (as of October 22, 2020)
Chart: % Items
| KTC-1 | KTC-2 | KTC-3 | KTC-4 | KTC-5 | KTC-6 | KTC-7 | KTC-8 | KTC-9 | KTC-10 | KTC-11 | KTC-12 | KTC-13 | KTC-14 | KTC-15
Meeting 1
Meeting 2
Not Started | 56
Meeting 3
BESTF Consensus
Approved by TAC | 50 | 86 | 87 | 11
Revision Request In Progress | 50 | 50 | 67 | 100 | 100 | 22
Revision Request Approved | 100 | 100 | 100 | 100 | 50 | 50 | 17 | 11
Closed | 16 | 50 | 100 | 14 | 13 | 100

## Slide 5: Next Steps
The BESTF meeting scheduled for November 13 has been cancelled. No more scheduled for this year.
Continue to work the items on the Discussion Points and Issue Tracking Spreadsheet
  Posted on BESTF page: http://www.ercot.com/committee/bestf
As additional items receive consensus by BESTF, they will be brought to TAC for voting.
Work through NPRRs submitted to PRS

## Slide 6
Questions?

## Slide 7
APPENDIX
Review Schedule
Review processes for BESTF and TAC

## Slide 8: Energy Storage Roadmap (updated 10-20-20)
2020
Jan 1, 2021
2024
Combination Model for ES
Single-Model ES Improvement NPRRs
Single Model NPRR (NPRR 1014) Approved
Single Model for ES
Implementation Goal
RTC and EMS 3.3 Go-Live
File Single Model NPRR (NPRR 1014)
MMS Change Freeze
EMS/MMS Change Freeze
Note that NPRR 1014 is written “on top of” filed RTC NPRRs
Combination Model NPRRs
*NPRR 957: Board approved
*NPRR 963: Board approved
NPRR 986: Board approved
NPRR 987: Board approved
NPRR 989: Board approved
NPRR 1002: Board approved
*NPRR 1020: Board approved
NPRR 1038 Limited Exemption from Reactive Power Requirements
NPRR 1026: Self-Limiting Facilities and Self-Limiting Resources
NPRR 1029: DC-Coupled Resources
NPRR 1043: Clarification of NPRR986 Language Related to WSL
*NPRR 995: Create Definition and Terms for Settlement Only Energy Storage
Most Combo Model NPRR language will carry over to Single Model era
* Denotes Market Participant-sponsored NPRRs

## Slide 9: Key Milestones
File key NPRRs needed to sustain/improve the current “combo model”: (before the end of Q1 2020)
File NPRRs related to Single Model (and RTC): (before the end of Q1 2020)
Single Model (and RTC) NPRRs BOD approved: (before January 1, 2021)
Start discussion on the integration of hybrid (battery and thermal), and DC-coupled (battery and solar behind the inverter) resources: (early January 2020)
Identify solutions (NPRRs, system changes etc.) for hybrids: (before the end of Q2 2020)

## Slide 10: BESTF Review Process
Internal ERCOT draft policy recommendations and recommendation concepts (elements)
ERCOT presents recommendations for meeting in presentation format.
ERCOT takes feedback and posts in 2 days as initial document for MP edits.
MPs submit feedback as edits to document and any
- Concerns
Alternatives
MPs share initial feedback, concerns, or requests for additional information.
MPs must document concerns and alternative approaches prior to meeting, and be prepared to discuss.
ERCOT provides responses to finalize supporting policy recommendations.
Meeting #1 Meeting #2 Meeting #3
Take consensus and non-consensus items to TAC for vote
ERCOT posts MP feedback and responds to MP redlines, concerns, or alternatives. Issues that have broad consensus may go to TAC for approval following second discussion.

## Slide 11: Harmonizing RTC & Battery Energy Storage (BES)
RTCTF & BESTF meetings are purposefully adjacent or straddling PRS due to inter-relationships of RTC & BES concepts
RTCTF
March 11
April 8
April 30
May 20
June 10
June 29
July 22
August 12
September 9
September 28
October 21
November 12 (if needed)
BESTF
March 13
April 16
May 1
May 21
June 12
June 30
July 23
August 14
September 11
September 29
October 22
November 13 (if needed)
November 5 (ROS)
November 11 (PRS)
November 18 (TAC)
December 8 (Board of Directors)
PRS
September 10
October 15

## Slide 12: Harmonizing RTC & Battery Energy Storage
RTC KPs
RTC RRs
RTC IA
BESTF KTCs
Other BES RRs
Single Model IA
Single Model NPRR
_____________
For overlapping sections, authors use
RTC Redlines
+
ESR Redlines
PRS
TAC
BOD
BESTF Meetings
PRS
TAC
BOD
RTC Redline Changes
RTC Redline Changes
RTC Redline Changes
Approval of RTC
RRs and IA
Approval of Single Model NPRR & IA
(acknowledging subset of identical RTC redlines to support ESR redlines).
RTCTF Meetings

## Slide 13: In-flight NPRRs [as of October 20, 2020] (blue)
  NPRR 1014 (BESTF-4) Energy Storage Resource Single Model: [Target 12/8/20 BoD] [11/18/20 TAC]
  NPRR 1029 (BESTF-6) DC-Coupled Resources: [Target 12/8/20 BoD] [11/18/20 TAC]
  NPRR 1026 (BESTF-7) Self-Limiting Facilities: [Recommended for approval at 10/15/20 PRS] [IA consideration at 11/11/20 PRS] [11/18/20 TAC]
  NPRR 995 (RTF-6) Create Definition and Terms for Settlement Only Energy Storage: [Not on list] [11/04/11 WMS] [11/11/20 PRS]
  NPRR 1043: Clarification of NPRR 986 Language Related to WSL: [Not on list] [Recommended for approval at 10/15/20 PRS] [IA consideration at 11/11/20 PRS] [11/18/20 TAC]

## Slide 14: KTCs Recently Approved by TAC …Working on NPRRs [as of Oct 22, 2020] (green)
  KTC-8-1 Should WSL treatment extend to batteries that can self-serve PUN Load with stored Energy [No NPRR is required (N/A)] [May want to re-consider with “Generation Accumulator” concept as an possibility]
  KTC-10 ESR Study and Capacity Assumptions [at SAWG and ROS]
  KTC-12 Co Located AC Connected ESRs [No NPRR is required (N/A)]
  KTC-15-7 Ancillary Service Responsibility Compliance Related to EEA Level 3 Charging Suspensions [NPRR language being developed by ERCOT] [11/11/20 PRS]

## Slide 15: Not Started or Closed [as of Oct 22, 2020] (black or red)
  KTC 7-4 Settlement Only Energy Storage settled at Nodal pricing while charging and discharging [Closed -- Part of NPRR 995]
  KTC-8-2 Should Wholesale Storage Load treatment extend to non-dispatched energy storage resources? [Closed -- Part of NPRR 995]
  KTC 9-1 ESR (in SCED) interconnected to distribution system …. (to be discussed in coordination with DGR) [Closed -- Part of NPRR 1016]
  KTC 15-3 Switchable Resources (TBD)
  KTC 15-4 Provisions Associated with Delayed Outages (TBD)
  KTC 15-5 Black Start Service (TBD)
  KTC 15-6 RMR and MRA Services (TBD)
  KTC 15-9 Governor Dead-band Telemetry as a Concept (TBD)

## Slide 16: List of NPRRs [as of October 20, 2020]
  NPRR 1043 Clarification of NPRR 986 Language Related to WSL
  NPRR 1038 Limited Exemption from Reactive Power Requirements for Certain Energy Storage Resources
  NPRR 1029 DC-Coupled Resources
  NPRR 1026 Self-Limiting Facilities and Self-Limiting Resources
  NPRR 1020 Add Definition of IBSS [Not on list]
  NPRR 1014 Energy Storage Resource Single Model
  NPRR 1002 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
  NPRR 995 RTF-6 Create Definition and Terms for Settlement Only Energy Storage [Not on list]
  NPRR 989 Energy Storage Resource Technical Requirements
  NPRR 987 Energy Storage Resource Contribution to Physical Responsive Capability and Real-Time On-Line Reserve Capacity Calculations
  NPRR 986 Energy Storage Resource Energy Offer Curves, Pricing, Dispatch, and Mitigation
  NPRR 963 Base Point Deviation Settlement and Deployment Performance Metrics for Energy Storage Resources (Combo Model)
  NPRR 957 RTF-4 Definition of Energy Storage Resource and Related Registration and Telemetry Requirements
Green indicates approved by BoD

## Slide 17
GR – Generation Resource
CLR – Controllable Load Resource
ESR – Energy Storage Resource
MMS – Market Management System
EMS – Energy Management System
NMMS – Network Model Management System
RARF – Resource Asset Registration Form
RIOO – Resource Integration and On-Going Operations
“Combo Model” – Current approach of representing a battery as a GR and a CLR
“Single Model” – Future approach of representing a battery as a single resource
“KTC Recommendation” – Key Topic/Concept Recommendation (this is a “principle” to be used in writing the NPRRs)
“Before the EMS Upgrade and RTC Implementation”
“With the EMS Upgrade and RTC Implementation”