## Sheet1
Document Type | Document Section | Sect | Sub1 | Sub2 | Sub3 | Sub4 | Sub5 | Mapped KPs | Notes | Topic for Scheduling | RTCTF Review Complete | 4/8/2020 | 4/30/2020 | 5/20/2020 | 6/10/2020 | 6/29/2020 | 7/22/2020 | 8/12/2020 | 9/9/2020 | 9/28/2020 | 10/21/2020 | 11/12/2020 | 11/12/2021
NPRR1010 | 6.4.9.1.1 | 6 | 4 | 9 | 1 | 1 | 0 | KP 1.3(1,2,6,7,8,9), KP 4 |  | AS Proxy and General SCED | 2020-04-30 | c | c
NPRR1010 | 6.5.7.3 | 6 | 5 | 7 | 3 | 0 | 0 | KP 1.1(1), KP 1.2(1,3), KP 1.3(1,8,12,13), KP 1.4(1), KP 1.5(10), KP 3(16,18), KP 6 |  | AS Proxy and General SCED | 5/20/2020 (review of minor change following legal review on 8/12/2020) | c | c | c |  |  |  | c
NPRR1008 | 4.4.12 | 4 | 4 | 12 | 0 | 0 | 0 | KP 1.1(4, 5, 7), KP 1.5(10), KP 5(2) |  | ASDC Creation | 5/20/2020 | c | c | c
NPRR1007 | 3.9 | 3 | 9 | 0 | 0 | 0 | 0 | KP 1.4(2), KP 3(3,4,5,15) |  | COP Changes | 2020-04-30 | c | c
NPRR1007 | 3.9.1 | 3 | 9 | 1 | 0 | 0 | 0 | KP 1.3(6,7), KP 1.4(3,4), KP 3(3,4,5,15), KP 4 |  | COP Changes | 2020-04-30 | c | c
NPRR1007 | 3.9.2 | 3 | 9 | 2 | 0 | 0 | 0 | KP 7(2) |  | COP Changes | 2020-04-30 | c | c
NPRR1010 | 6.5.7.3.1 | 6 | 5 | 7 | 3 | 1 | 0 | KP 1.1(2,6), KP 1.4(1), KP 3(17,19) |  | Reliability Deployment Pricing Run | 2020-04-30 | c | c
NPRR1009 | 5.1 | 5 | 1 | 0 | 0 | 0 | 0 | KP 3(1,2), KP 5(3) |  | RUC General Update | 2020-04-30 | c | c
NPRR1009 | 5.2.2.1 | 5 | 2 | 2 | 1 |  |  | KP 3(12) |  | RUC General Update | 2020-04-30 | c | c
NPRR1009 | 5.2.2.2 | 5 | 2 | 2 | 2 | 0 | 0 | KP 4, KP 5(3) |  | RUC General Update | 2020-04-30 | c | c
NPRR1009 | 5.3 | 5 | 3 | 0 | 0 | 0 | 0 | KP 3(1) |  | RUC General Update | 2020-04-30 | c | c
NPRR1009 | 5.4 | 5 | 4 | 0 | 0 | 0 | 0 | KP 3(12), KP 7(2) |  | RUC General Update | 2020-04-30 | c | c
NPRR1009 | 5.4.1 | 5 | 4 | 1 | 0 | 0 | 0 | KP 3(12) |  | RUC General Update | 2020-04-30 | c | c
NPRR1009 | 5.5.2 | 5 | 5 | 2 | 0 | 0 | 0 | KP 3(1,2,5,6,7,8,9,13,14,15), KP 6, KP 7(2) |  | RUC General Update | 2020-04-30 | c | c
OBDRR020 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | KP 1.2(1,2) |  | SWCAP/VOLL | 2020-04-30 | c | c
OBDRR020 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | KP 1.1(1), KP 1.2(1,2) |  | SWCAP/VOLL | 2020-04-30 | c | c
NPRR1008 | 4.4.11 | 4 | 4 | 11 | 0 | 0 | 0 | KP 1.2(1,2,3) |  | SWCAP/VOLL | 5/20/2020 | c | c | c
NPRR1008 | 4.4.11.1 | 4 | 4 | 11 | 1 | 0 | 0 | KP 1.2(1,2,3) |  | SWCAP/VOLL | 5/20/2020 | c | c | c
NPRR1008 | 4.3 | 4 | 3 | 0 | 0 | 0 | 0 | KP 5(7) |  | DAM - AS Only Offer Material | 2020-06-10 |  | c | c | c
NPRR1008 | 4.4.7.2 | 4 | 4 | 7 | 2 | 0 | 0 | KP1.2 (1,3), KP 4, KP 5(1), KP 5(7) |  | DAM - AS Only Offer Material | 2020-06-10 |  | c | c | c
NPRR1008 | 4.4.7.2.1 | 4 | 4 | 7 | 2 | 1 | 0 | KP 1.2(1,3), KP4, KP 5(7) |  | DAM - AS Only Offer Material | 2020-06-10 |  | c | c | c
NPRR1008 | 4.4.7.2.2 | 4 | 4 | 7 | 2 | 2 | - | KP 5(7) |  | DAM - AS Only Offer Material | 2020-06-10 |  | c | c | c
NPRR1008 | 4.4.7.2.3 | 4 | 4 | 7 | 2 | 3 | 0 | KP 5(7) |  | DAM - AS Only Offer Material | 2020-06-10 |  | c | c | c
NPRR1008 | 4.4.7.2.4 | 4 | 4 | 7 | 2 | 4 | 0 | KP 5(7) |  | DAM - AS Only Offer Material | 2020-06-10 |  | c | c | c
NPRR1008 | 4.5.3 | 4 | 5 | 3 | 0 | 0 | 0 | KP 5(7), KP 6 |  | DAM - AS Only Offer Material | 2020-06-10 |  | c | c | c
NPRR1008 | 4.1 | 4 | 1 | 0 | 0 | 0 | 0 | KP 7(2) |  | DAM General Update | 2020-06-10 |  | c | c | c
NPRR1008 | 4.2.1.2 | 4 | 2 | 1 | 2 | 0 | 0 | KP 5(4,5,6) |  | DAM General Update | 2020-06-10 |  | c | c | c
NPRR1008 | 4.4.7.1 | 4 | 4 | 7 | 1 | 0 | 0 | KP 1.3(14), KP 1.5(16), KP 4, KP 5(1,4,7), KP 6 |  | DAM General Update | 6/10/2020 (minor cleanup reviewed on 9/28/20) |  | c | c | c |  |  |  |  | c
NPRR1008 | 4.4.7.1.1 | 4 | 4 | 7 | 1 | 1 | 0 | KP 5(2) |  | DAM General Update | 2020-06-10 |  | c | c | c
NPRR1008 | 4.4.7.3 | 4 | 4 | 7 | 3 | 0 | 0 | KP 7(2) |  | DAM General Update | 2020-06-29 |  | c | c | c | c
NPRR1008 | 4.4.8 | 4 | 4 | 8 | 0 | 0 | 0 | KP 1.2(1,2,3) |  | DAM General Update | 6/10/2020 (reviewed changes to RMR offers on 9/28/20) |  | c | c | c |  |  |  |  | c
NPRR1008 | 4.4.9.3.1 | 4 | 4 | 9 | 3 | 1 | 0 | KP 1.2(1,2,3) |  | DAM General Update | 2020-06-10 |  | c | c | c
NPRR1008 | 4.4.9.3.3 | 4 | 4 | 9 | 3 | 3 | 0 | KP 1.2(1,2,3) |  | DAM General Update | 6/10/2020 (reviewed changes to RMR offers on 9/28/20) |  | c | c | c |  |  |  |  | c
NPRR1008 | 4.4.9.4.1 | 4 | 4 | 9 | 4 | 1 | 0 | KP 1.2(1,2,3), KP 1.3(3) |  | DAM General Update | 6/10/2020 (reviewed changes to contract for capacity offers on 9/28/20) |  | c | c | c |  |  |  |  | c
NPRR1008 | 4.4.9.5.1 | 4 | 4 | 9 | 5 | 1 | 0 | KP 1.2(3) |  | DAM General Update | 2020-06-10 |  | c | c | c
NPRR1008 | 4.5.1 | 4 | 5 | 1 | 0 | 0 | 0 | KP 5(1,2,3,7) |  | DAM General Update | 2020-06-10 |  | c | c | c
OBDRR020 | Appendix 1 | A1 | 0 | 0 | 0 | 0 | 0 | KP 5(1) |  | DAM General Update | 5/20/2020 |  | c | c
NPRR1013 | 25.3 | 25 | 3 | 0 | 0 | 0 | 0 | KP 1.4(1) |  | Market Restart (minor item) | 5/20/2020 |  | c | c
NPRR1010 | 6.4.6 | 6 | 4 | 6 | 0 | 0 | 0 | KP 1.4(3) |  | RTM - Telemetry and RLC | 5/20/2020 |  | c | c | c
NPRR1010 | 6.5.5.2 | 6 | 5 | 5 | 2 | 0 | 0 | KP 1.3(1,2,4), KP 1.4(2,3,4), KP 1.5(3, 9), KP 7(2) |  | RTM - Telemetry and RLC | 5/20/2020 (review of new proposed telemetry point on 7/22/2020 and 8/12/2020 with consensus for new item on 8/12/2020) |  | c | c | c |  | c | c
NPRR1010 | 6.5.7.1.12 | 6 | 5 | 7 | 1 | 12 | 0 | KP 1.4(1,3) |  | RTM - Telemetry and RLC | 5/20/2020 |  | c | c | c
NPRR1010 | 6.5.7.1.13 | 6 | 5 | 7 | 1 | 13 | 0 | KP 1.4(1) |  | RTM - Telemetry and RLC | 5/20/2020 |  | c | c | c
NPRR1010 | 6.5.7.2 | 6 | 5 | 7 | 2 | 0 | 0 | KP 1.4(1,2), KP 1.5(9) |  | RTM - Telemetry and RLC | 5/20/2020 |  | c | c | c
NPRR1008 | 4.1.2 | [6 empty] | KP 5(3) |  | SASM Removal | 2020-10-21 | [9 empty] | c
NPRR1008 | 4.5.2 | 4 | 5 | 2 | 0 | 0 | 0 | KP 4, KP 5(3) |  | SASM Removal | 5/20/2020 |  | c | c
NPRR1010 | 6.4.9 | 6 | 4 | 9 | 0 | 0 | 0 | KPs listed for subsections |  | SASM Removal | 5/20/2020 |  | c | c
NPRR1010 | 6.4.9.1.3 | 6 | 4 | 9 | 1 | 3 | 0 | KP 4, KP 7(2) |  | SASM Removal | 5/20/2020 |  | c | c
NPRR1010 | 6.4.9.2 | 6 | 4 | 9 | 2 | 0 | 0 | KP 4 |  | SASM Removal | 5/20/2020 |  | c | c
NPRR1010 | 6.4.9.2.1 | 6 | 4 | 9 | 2 | 1 | 0 | KP 4 |  | SASM Removal | 5/20/2020 |  | c | c
NPRR1010 | 6.4.9.2.2 | 6 | 4 | 9 | 2 | 2 | 0 | KP 4 |  | SASM Removal | 5/20/2020 |  | c | c
NPRR1010 | 6.4.9.2.3 | 6 | 4 | 9 | 2 | 3 | 0 | KP 4, KP 6 |  | SASM Removal | 5/20/2020 |  | c | c
NPRR1013 | 16.11.4.1 | 16 | 11 | 4 | 1 | 0 | 0 | KP 1.6(5), KP 5(7) |  | Credit | 2020-06-10 |  |  | c | c
NPRR1013 | 16.11.4.3.2 | 16 | 11 | 4 | 3 | 2 | 0 | KP 1.6(5), KP 5(7) |  | Credit | 2020-06-10 |  |  | c | c
NPRR1008 | 4.4.10 | 4 | 4 | 10 | 0 | 0 | 0 | KP 5(7) |  | DAM Credit/Settlement | 2020-06-10 |  |  | c | c
NPRR1008 | 4.6.2.3.1 | 4 | 6 | 2 | 3 | 1 | 0 | KP 5(7) |  | DAM Credit/Settlement | 2020-06-10 |  |  | c | c
NPRR1008 | 4.6.4.1.1 | 4 | 6 | 4 | 1 | 1 | 0 | KP 5(7) |  | DAM Credit/Settlement | 2020-06-10 |  |  | c | c
NPRR1008 | 4.6.4.1.2 | 4 | 6 | 4 | 1 | 2 | 0 | KP 5(7) |  | DAM Credit/Settlement | 2020-06-10 |  |  | c | c
NPRR1008 | 4.6.4.1.3 | 4 | 6 | 4 | 1 | 3 | 0 | KP 5(7) |  | DAM Credit/Settlement | 2020-06-10 |  |  | c | c
NPRR1008 | 4.6.4.1.4 | 4 | 6 | 4 | 1 | 4 | 0 | KP 5(7) |  | DAM Credit/Settlement | 2020-06-10 |  |  | c | c
NPRR1008 | 4.6.4.1.5 | 4 | 6 | 4 | 1 | 5 | 0 | KP 5(7) |  | DAM Credit/Settlement | 2020-06-10 |  |  | c | c
NPRR1008 | 4.6.4.2.1 | 4 | 6 | 4 | 2 | 1 | 0 | KP 5(7) |  | DAM Credit/Settlement | 2020-06-10 |  |  | c | c
NPRR1008 | 4.6.4.2.2 | 4 | 6 | 4 | 2 | 2 | 0 | KP 5(7) |  | DAM Credit/Settlement | 2020-06-10 |  |  | c | c
NPRR1008 | 4.6.4.2.3 | 4 | 6 | 4 | 2 | 3 | 0 | KP 5(7) |  | DAM Credit/Settlement | 2020-06-10 |  |  | c | c
NPRR1008 | 4.6.4.2.4 | 4 | 6 | 4 | 2 | 4 | 0 | KP 5(7) |  | DAM Credit/Settlement | 2020-06-10 |  |  | c | c
NPRR1008 | 4.6.4.2.5 | 4 | 6 | 4 | 2 | 5 | 0 | KP 5(7) |  | DAM Credit/Settlement | 2020-06-10 |  |  | c | c
NPRR1009 | 5.6.2 | 5 | 6 | 2 | 0 | 0 | 0 | KP 3(12) |  | RUC Settlement | 2020-06-29 |  |  | c | c | c
NPRR1009 | 5.7.1.3 | 5 | 7 | 1 | 3 | 0 | 0 | KP 3(10) |  | RUC Settlement | 2020-06-29 |  |  | c | c | c
NPRR1009 | 5.7.1.4 | 5 | 7 | 1 | 4 | 0 | 0 | KP 3(11) |  | RUC Settlement | 2020-06-29 |  |  | c | c | c
NPRR1009 | 5.7.4.1.1 | 5 | 7 | 4 | 1 | 1 | 0 | KP 3(12) |  | RUC Settlement | 2020-06-29 |  |  | c | c | c
NPRR1007 | 3.8.3.1 | 3 | 8 | 3 | 1 | 0 | 0 | KP 1.5(15) |  | Open Settlement Item | In revising 6.6.9, no edits are needed. |  |  |  | c | c | c | c
NPRR1010 | 6.6.9 | 6 | 6 | 9 | 0 | 0 | 0 | KP 1.5(15) |  | Open Settlement Item | 2020-08-12 |  |  |  | c | c | c | c
NPRR1010 | 6.6.9.1 | [6 empty] | KP 1.5(15) |  | Open Settlement Item | 8/12/2020 (review of missed item on 9/9/2020) |  |  |  | c | c | c | c | c
NPRR1010 | 6.6.9.2 | [6 empty] | KP 1.5(15) |  | Open Settlement Item | 2020-08-14 |  |  |  | c | c | c | c
NPRR1010 | 6.6.6.3 | [6 empty] | KP 1.5(15) |  | Missed Settlement Item | 2020-09-09 | [7 empty] | c
NPRR1010 | 6.6.6.10 | [6 empty] | KP 1.5(15) |  | Missed Settlement Item | 2020-09-09 | [7 empty] | c
NOGRR211 | 2.3 | 2 | 3 | 0 | 0 | 0 | 0 | KP 1.5(3,9), KP 7(2) |  | RTM - AS Deployment | 2020-08-12 |  |  |  | c | c | c | c
NOGRR211 | 2.3.1.2 | 2 | 3 | 1 | 2 | 0 | 0 | KP 1.4(1), KP 1.5(8,9) |  | RTM - AS Deployment | 2020-08-12 |  |  |  | c | c | c | c
NOGRR211 | 2.3.2.1 | 2 | 3 | 2 | 1 | 0 | 0 | KP 7(2) |  | RTM - AS Deployment | 2020-08-12 |  |  |  | c | c | c | c
NOGRR211 | 2.3.3.1 | 2 | 3 | 3 | 1 | 0 | 0 | KP 1.5(8,9), KP 7(2) |  | RTM - AS Deployment | 2020-08-12 |  |  |  | c | c | c | c
NPRR1007 | 3.16 | 3 | 16 | 0 | 0 | 0 | 0 | KP 1.5(16), KP 4 |  | RTM - AS Deployment | 2020-06-29 |  |  |  | c | c
NPRR1007 | 3.17.1 | 3 | 17 | 1 | 0 | 0 | 0 | KP 1.5(16) |  | RTM - AS Deployment | 2020-06-29 |  |  |  | c | c
NPRR1007 | 3.18 | 3 | 18 | 0 | 0 | 0 | 0 | KP 1.3(8), KP 1.4(4), KP 1.5(9), KP 7(2) |  | RTM - AS Deployment | 2020-06-29 |  |  |  | c | c
NPRR1010 | 6.5.7.4.1 | 6 | 5 | 7 | 4 | 1 | 0 | KP 1.4(4), KP 1.5(5) |  | RTM - AS Deployment | 7/22/2020 (review of additional sentence related to RRS deployments in UDSP on 8/12/2020) |  |  |  | c | c | c | c
NPRR1010 | 6.5.7.6.1 | 6 | 5 | 7 | 6 | 1 | 0 | KP 1.4(2), KP 1.5(3,5,6,8,12) |  | RTM - AS Deployment | 2020-07-22 |  |  |  | c | c | c
NPRR1010 | 6.5.7.6.2 | 6 | 5 | 7 | 6 | 2 | 0 | KP 1.5(5) |  | RTM - AS Deployment | 2020-07-22 |  |  |  | c | c | c
NPRR1010 | 6.5.7.6.2.1 | 6 | 5 | 7 | 6 | 2 | 1 | KP 1.5(3,4,5) |  | RTM - AS Deployment | 2020-07-22 |  |  |  | c | c | c
NPRR1010 | 6.5.7.6.2.2 | 6 | 5 | 7 | 6 | 2 | 2 | KP 1.5(8,9,10) |  | RTM - AS Deployment | 2020-07-22 |  |  |  | c | c | c
NPRR1010 | 6.5.7.6.2.3 | 6 | 5 | 7 | 6 | 2 | 3 | KP 1.4(1), KP 1.5(7,9) |  | RTM - AS Deployment | 2020-07-22 |  |  |  | c | c | c
NPRR1010 | 6.5.7.6.2.4 | 6 | 5 | 7 | 6 | 2 | 4 | KP 1.4(1), KP 1.5(8,9) |  | RTM - AS Deployment | 2020-07-22 |  |  |  | c | c | c
NPRR1010 | 6.5.9.4.2 | 6 | 5 | 9 | 4 | 2 | 0 | KP 1.4(1), KP 1.5(8) |  | RTM - AS Deployment | 2020-07-22 |  |  |  | c | c | c
NPRR1011 | 8.1.1.2.1 | 8 | 1 | 1 | 2 | 1 | 0 | KP 2(2) |  | RTM - AS Qualification | 2020-08-12 |  |  |  | c | c | c | c
NPRR1011 | 8.1.1.2.1.1 | 8 | 1 | 1 | 2 | 1 | 1 | KP 1.5(16), KP 2(2,3) |  | RTM - AS Qualification | 2020-08-12 |  |  |  | c | c | c | c
NPRR1011 | 8.1.1.2.1.2 | 8 | 1 | 1 | 2 | 1 | 2 | KP 1.4(1), KP 1.5(9), KP 2(4), KP 7(3) |  | RTM - AS Qualification | 2020-08-12 |  |  |  | c | c | c | c
NPRR1011 | 8.1.1.2.1.3 | 8 | 1 | 1 | 2 | 1 | 3 | KP 1.4(1), KP 2(5), KP 7(3) |  | RTM - AS Qualification | 2020-08-12 |  |  |  | c | c | c | c
NPRR1011 | 8.1.1.2.1.6 | 8 | 1 | 1 | 2 | 1 | 6 | KP 1.4(1), KP 2(6), KP 7(3) |  | RTM - AS Qualification | 2020-08-12 |  |  |  | c | c | c | c
NPRR1013 | 1.3.1.4 | 1 | 3 | 1 | 4 | 0 | 0 | KP 6, KP 7(2) |  | RTM General Update | 2020-06-29 |  |  |  | c | c
NPRR1013 | 1.3.3 | 1 | 3 | 3 | 0 | 0 | 0 | KP 6, KP 7(2) |  | RTM General Update | 2020-06-29 |  |  |  | c | c
NOGRR211 | 2.1 | 2 | 1 | 0 | 0 | 0 | 0 | KP 1.4(1), KP 4 |  | RTM General Update | 2020-06-29 |  |  |  | c | c
NOGRR211 | 2.2.4 | 2 | 2 | 4 | 0 | 0 | 0 | KP 1.5(9) |  | RTM General Update | 2020-06-29 |  |  |  | c | c
NOGRR211 | 2.2.4.2 | 2 | 2 | 4 | 2 | 0 | 0 | KP 4 |  | RTM General Update | 2020-06-29 |  |  |  | c | c
NPRR1007 | 3.6.1 | 3 | 6 | 1 | 0 | 0 | 0 | KP 7(2) |  | RTM General Update | 2020-06-29 |  |  |  | c | c
NPRR1007 | 3.8.1 | 3 | 8 | 1 | 0 | 0 | 0 | KP 1.3(12) |  | RTM General Update | 2020-06-29 |  |  |  | c | c
NPRR1007 | 3.8.2 | 3 | 8 | 2 | 0 | 0 | 0 | KP 1.3(1), KP 1.4(2,3), KP 3(3,4,5,15), KP 4 |  | RTM General Update | 2020-06-29 |  |  |  | c | c
NPRR1007 | 3.8.3 | 3 | 8 | 3 | 0 | 0 | 0 | KP 1.4(1,2), KP 1.5(9), KP 7(2) |  | RTM General Update | 6/29/2020 (review of changed reference on 7/22/2020) |  |  |  | c | c | c
NPRR1007 | 3.14.4.1 | 3 | 14 | 4 | 1 | 0 | 0 | KP 7(2) |  | RTM General Update | 2020-06-29 |  |  |  | c | c
NPRR1008 | 4.4.4 | 4 | 4 | 4 | 0 | 0 | 0 | KP 1.4(1,2) |  | RTM General Update | 2020-06-29 |  |  |  | c | c
NPRR1008 | 4.4.7.4 | 4 | 4 | 7 | 4 | 0 | 0 | KP 4, KP 7(2) |  | RTM General Update | 2020-06-29 |  |  |  | c | c
NPRR1010 | 6.1 | 6 | 1 | 0 | 0 | 0 | 0 | KP 1.1(1), KP 4 |  | RTM General Update | 2020-06-29 |  |  |  | c | c
NPRR1010 | 6.3 | 6 | 3 | 0 | 0 | 0 | 0 | KP 1.1(1,6), KP 4 |  | RTM General Update | 2020-06-29 |  |  |  | c | c
NPRR1010 | 6.3.1 | 6 | 3 | 1 | 0 | 0 | 0 | KP 1.3(11), KP 6 |  | RTM General Update | 2020-06-29 |  |  |  | c | c
NPRR1010 | 6.3.2 | 6 | 3 | 2 | 0 | 0 | 0 | KP 1.1(1,6), KP 1.4(2,3), KP 3(4), KP 6, KP 7(2) |  | RTM General Update | 6/29/2020 (reviewed additional reporting item on 9/9/2020 and 9/28/2020) |  |  |  | c | c |  |  | c | c
NPRR1010 | 6.4.7.1 | 6 | 4 | 7 | 1 | 0 | 0 | KP 7(2) |  | RTM General Update | 2020-06-29 |  |  |  | c | c
NPRR1010 | 6.4.9.1.2 | 6 | 4 | 9 | 1 | 2 | 0 | KP 1.1(5), KP 4, KP 6, KP 7(2) |  | RTM General Update | 2020-07-22 |  |  |  | c | c | c
NPRR1010 | 6.5.1.1 | 6 | 5 | 1 | 1 | 0 | 0 | KP 1.2(1,2,3), KP 1.4(1) |  | RTM General Update | 2020-06-29 |  |  |  | c | c
NPRR1010 | 6.5.1.2 | 6 | 5 | 1 | 2 | 0 | 0 | KP 1.3(12), KP 6 |  | RTM General Update | 2020-06-29 |  |  |  | c | c
NPRR1010 | 6.5.7 | 6 | 5 | 7 | 0 | 0 | 0 | KP 1.4(1) |  | RTM General Update | 2020-06-29 |  |  |  | c | c
NPRR1010 | 6.5.9.2 | 6 | 5 | 9 | 2 | 0 | 0 | KP 1.1(6), KP 1.4(1,2), KP 1.5(13) |  | RTM General Update | 2020-06-29 |  |  |  | c | c
NPRR1010 | 6.5.9.3.3 | 6 | 5 | 9 | 3 | 3 | 0 | KP 4, KP 5(3) |  | RTM General Update | 2020-06-29 |  |  |  | c | c
NPRR1010 | 6.5.9.3.4 | 6 | 5 | 9 | 3 | 4 | 0 | KP 5(3) |  | RTM General Update | 2020-06-29 |  |  |  | c | c
NPRR1010 | 6.5.9.4 | 6 | 5 | 9 | 4 | 0 | 0 | KP 1.5(9) |  | RTM General Update | 2020-06-29 |  |  |  | c | c
NPRR1011 | 8.1.1.1 | 8 | 1 | 1 | 1 | 0 | 0 | KP 1.4(1) |  | RTM General Update | 6/29/2020 (review of changed reference on 7/22/2020) |  |  |  | c | c | c
NPRR1011 | 8.1.1.2 | 8 | 1 | 1 | 2 | 0 | 0 | KP 1.4(1) |  | RTM General Update | 2020-06-29 |  |  |  | c | c
NPRR1007 | 3.5.2.1 | 3 | 5 | 2 | 1 | 0 | 0 | KP 1.1(1) |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1007 | 3.5.2.2 | 3 | 5 | 2 | 2 | 0 | 0 | KP 1.1(1) |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1007 | 3.5.2.3 | 3 | 5 | 2 | 3 | 0 | 0 | KP 1.1(1) |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1007 | 3.5.2.4 | 3 | 5 | 2 | 4 | 0 | 0 | KP 1.1(1) |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1007 | 3.5.2.5 | 3 | 5 | 2 | 5 | 0 | 0 | KP 1.1(1) |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1007 | 3.5.2.6 | 3 | 5 | 2 | 6 | 0 | 0 | KP 1.1(1) |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1007 | 3.5.2.7 | 3 | 5 | 2 | 7 | 0 | 0 | KP 1.1(1) |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1010 | 6.6.1 | 6 | 6 | 1 | 0 | 0 | 0 | KP 1.1(1) |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1010 | 6.6.1.1 | 6 | 6 | 1 | 1 | 0 | 0 | KP 1.1(1) |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1010 | 6.6.1.2 | 6 | 6 | 1 | 2 | 0 | 0 | KP 1.1(1) |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1010 | 6.6.1.6 | 6 | 6 | 1 | 6 | 0 | 0 | KP 1.1(1,2,3,6) |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1010 | 6.6.1.7 | 6 | 6 | 1 | 7 | 0 | 0 | KP 1.1(1,2,3,6) |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1010 | 6.6.3.1 | 6 | 6 | 3 | 1 | 0 | 0 | KP 1.1(1) |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1010 | 6.6.3.7 | 6 | 6 | 3 | 7 | 0 | 0 | KP 1.1(1), KP 1.4(1) |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1010 | 6.6.3.9 | 6 | 6 | 3 | 9 | 0 | 0 | KP 1.1(1) |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1010 | 6.6.5.1 | 6 | 6 | 5 | 1 | 0 | 0 | KP 7(4) |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1010 | 6.6.5.2 | 6 | 6 | 5 | 2 | 0 | 0 | KP 4(1) |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1010 | 6.6.5.2.1 | 6 | 6 | 5 | 2 | 1 | 0 | KP 4(1) |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1010 | 6.6.5.1.1.3 | [6 empty] | KP 4(1) |  | RTM Settlement | 2020-07-22 | [5 empty] | c
NPRR1010 | 6.6.5.1.1.4 | [6 empty] | KP 4(1) |  | RTM Settlement | 2020-07-22 | [5 empty] | c
NPRR1010 | 6.6.5.3 | [6 empty] | KP 4(1) |  | RTM Settlement | 2020-07-22 | [5 empty] | c
NPRR1010 | 6.6.5.3.1 | [6 empty] | KP 4(1) |  | RTM Settlement | 2020-07-22 | [5 empty] | c
NPRR1010 | 6.6.5.4 | 6 | 6 | 5 | 4 | 0 | 0 | KP 4(1) |  | RTM Settlement | 2020-07-22 | [5 empty] | c
NPRR1010 | 6.6.5.5 | [6 empty] | KP 4(1) |  | RTM Settlement | 2020-07-22 | [5 empty] | c
NPRR1010 | 6.6.5.5.1 | [6 empty] | KP 4(1) |  | RTM Settlement | 2020-07-22 | [5 empty] | c
NPRR1010 | 6.6.5.6 | [6 empty] | KP 4(1) |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1010 | 6.6.12.1 | 6 | 6 | 12 | 1 | 0 | 0 | KP 3(10) |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1010 | 6.7.1 | 6 | 7 | 1 | 0 | 0 | 0 | KP 4 |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1010 | 6.7.2 | 6 | 7 | 2 | 0 | 0 | 0 | KP 1.4(1), KP 4, KP 5(3) |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1010 | 6.7.2.1 | 6 | 7 | 2 | 1 | 0 | 0 | KP 1.4(1), KP 4 |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1010 | 6.7.2.2 | 6 | 7 | 2 | 2 | 0 | 0 | KP 1.4(1), KP 4 |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1010 | 6.7.3 | 6 | 7 | 3 | 0 | 0 | 0 | KP 1.4(1), KP 4 |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1010 | 6.7.4 | 6 | 7 | 4 | 0 | 0 | 0 | KP 4, KP 5(4,6) |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1010 | 6.7.5 | 6 | 7 | 5 | 0 | 0 | 0 | KPs listed for subsections |  | RTM Settlement | 2020-08-12 |  |  |  |  | c | c | c
NPRR1010 | 6.7.5.1 | 6 | 7 | 5 | 1 | 0 | 0 | KP 1.1(1,3), KP 1.3(14), KP 1.6(1,2,3,4), KP5(7) |  | RTM Settlement | 2020-08-12 |  |  |  |  | c | c | c
NPRR1010 | 6.7.5.2 | 6 | 7 | 5 | 2 | 0 | 0 | KP 1.1(1,3), KP 1.3(14), KP 1.6(1,2,3,4), KP5(7) |  | RTM Settlement | 8/12/2020 (review of missed item on 9/9/2020) |  |  |  |  | c | c | c | c
NPRR1010 | 6.7.5.3 | 6 | 7 | 5 | 3 | 0 | 0 | KP 1.1(1,3), KP 1.3(14), KP 1.6(1,2,3,4), KP5(7) |  | RTM Settlement | 2020-08-12 |  |  |  |  | c | c | c
NPRR1010 | 6.7.5.4 | 6 | 7 | 5 | 4 | 0 | 0 | KP 1.1(1,3), KP 1.3(14), KP 1.6(1,2,3,4), KP5(7) |  | RTM Settlement | 2020-08-12 |  |  |  |  | c | c | c
NPRR1010 | 6.7.5.5 | 6 | 7 | 5 | 5 | 0 | 0 | KP 1.1(1,3), KP 1.3(14), KP 1.6(1,2,3,4), KP5(7) |  | RTM Settlement | 2020-08-12 |  |  |  |  | c | c | c
NPRR1010 | 6.7.5.6 | 6 | 7 | 5 | 6 | 0 | 0 | KP 1.1(1,3), KP 1.3(14), KP 1.6(1,2,3,4), KP5(7) |  | RTM Settlement | 2020-08-12 |  |  |  |  | c | c | c
NPRR1010 | 6.7.5.7 | 6 | 7 | 5 | 7 | 0 | 0 | KP 1.3(9) |  | RTM Settlement | 8/12/2020 (review of missed item on 9/9/2020) |  |  |  |  | c | c | c | c
NPRR1010 | 6.7.5.8 | 6 | 7 | 5 | 8 | 0 | 0 | KP 1.3(9) |  | RTM Settlement | 2020-08-12 |  |  |  |  | c | c | c
NPRR1010 | 6.7.6 | 6 | 7 | 6 | 0 | 0 | 0 | KP 1.6(4) |  | RTM Settlement | 2020-08-12 |  |  |  |  | c | c | c
NPRR1010 | 6.7.7 | 6 | 7 | 7 | 0 | 0 | 0 | KP 1.4(1), KP 5(3) |  | RTM Settlement | 2020-08-12 |  |  |  |  | c | c | c
NPRR1012 | 9.5.3 | 9 | 5 | 3 | 0 | 0 | 0 | All KPs |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1012 | 9.19.1 | 9 | 19 | 1 | 0 | 0 | 0 | KP 5(7) |  | RTM Settlement | 2020-07-22 |  |  |  |  | c | c
NPRR1010 | 6.4.2.3 | 6 | 4 | 2 | 3 | 0 | 0 | KP 1.4(2,3) |  | RTM Offers | 2020-09-09 | [6 empty] | c | c
NPRR1010 | 6.4.3.1 | 6 | 4 | 3 | 1 | 0 | 0 | KP 1.2(3) |  | RTM Offers | 2020-09-09 | [6 empty] | c | c
NPRR1010 | 6.4.3.1.1 | 6 | 4 | 3 | 1 | 1 | 0 | KP 1.2(3), KP 7(2) |  | RTM Offers | 2020-09-09 | [6 empty] | c | c
NPRR1010 | 6.4.4 | 6 | 4 | 4 | 0 | 0 | 0 | KP 1.2(3) |  | RTM Offers | 2020-09-09 | [6 empty] | c | c
NPRR1010 | 6.4.4.1 | 6 | 4 | 4 | 1 | 0 | 0 | KP 1.5(11) |  | RTM Offers | 2020-09-09 | [6 empty] | c | c
NPRR1010 | 6.4.4.2 | 6 | 4 | 4 | 2 | 0 | 0 | KP 1.2(1,2,3) |  | RTM Offers | 2020-09-09 | [6 empty] | c | c
NPRR1010 | 6.4.5 | 6 | 4 | 5 | 0 | 0 | 0 | KP 1.2(3) |  | RTM Offers | 2020-09-09 | [6 empty] | c | c
NPRR1010 | 6.4.7 | 6 | 4 | 7 | 0 | 0 | 0 | KP 7(2) |  | RTM Offers | 2020-09-09 | [6 empty] | c | c
NPRR1010 | 6.4.9.1 | 6 | 4 | 9 | 1 | 0 | 0 | KP 1.3(11), KP 7(2) |  | RTM Offers | 2020-09-09 | [6 empty] | c | c
NPRR1013 | 1.3.1.1 | 1 | 3 | 1 | 1 | 0 | 0 | KP 1.4(1), KP 4, KP 6 |  | Reporting Item | 2020-09-09 | [6 empty] | c | c
NPRR1007 | 3.2.3 | 3 | 2 | 3 | 0 | 0 | 0 | KP1.4(3,4), KP 6 |  | Reporting Item | 2020-09-28 | [6 empty] | c | c | c
NPRR1007 | 3.2.5 | 3 | 2 | 5 | 0 | 0 | 0 | KP 1.4(1,2,3), KP 4, KP 5(7), KP 6 |  | Reporting Item | 2020-09-28 | [6 empty] | c | c | c
NPRR1007 | 3.10.7.2.1 | 3 | 10 | 7 | 2 | 1 | 0 | KP 1.5(1) |  | Reporting Item | 2020-09-28 | [6 empty] | c | c | c
NPRR1008 | 4.2.1.1 | 4 | 2 | 1 | 1 | 0 | 0 | KP 5(1), KP 6 |  | Reporting Item | 2020-09-09 | [6 empty] | c | c
NPRR1009 | 5.8 | 5 | 8 | 0 | 0 | 0 | 0 | KP 4, KP 5(3) |  | Reporting Item | 2020-09-09 | [6 empty] | c | c
NPRR1010 | 6.5.7.5 | 6 | 5 | 7 | 5 | 0 | 0 | KP 1.3(4), KP 1.4(1,3), KP 1.5(9), KP 6 |  | Reporting Item | 2020-09-28 | [6 empty] | c | c | c
NPRR1011 | 8.1.1.3 | 8 | 1 | 1 | 3 | 0 | 0 | KP 6, KP 7(2) |  | AS Performance Monitoring | 2020-10-21 | [7 empty] | c | c | c
NPRR1011 | 8.1.1.3.1 | 8 | 1 | 1 | 3 | 1 | 0 | KKP 1.4(3,4), KP 7(2) |  | AS Performance Monitoring | 2020-10-21 | [7 empty] | c | c | c
NPRR1011 | 8.1.1.3.2 | 8 | 1 | 1 | 3 | 2 | 0 | KP 1.4(3,4), KP 7(2,3) |  | AS Performance Monitoring | 2020-10-21 | [7 empty] | c | c | c
NPRR1011 | 8.1.1.3.3 | 8 | 1 | 1 | 3 | 3 | 0 | KP 1.4(3,4), KP 7(2,3) |  | AS Performance Monitoring | 2020-10-21 | [7 empty] | c | c | c
NPRR1011 | 8.1.1.3.4 | 8 | 1 | 1 | 3 | 4 | 0 | KP 1.4(3,4), KP 7(2,3) |  | AS Performance Monitoring | 2020-10-21 | [7 empty] | c | c | c
NPRR1011 | 8.1.1.4.1 | 8 | 1 | 1 | 4 | 1 | 0 | KP 1.4(1,4), KP 1.5(3), KP 7(1) |  | AS Performance Monitoring | 2020-10-21 | [7 empty] | c | c | c
NPRR1011 | 8.1.1.4.2 | 8 | 1 | 1 | 4 | 2 | 0 | KP 1.3(2,4), KP 1.4(1), KP 1.5(9), KP 7(3) |  | AS Performance Monitoring | 2020-10-21 | [7 empty] | c | c | c
NPRR1011 | 8.1.1.4.3 | 8 | 1 | 1 | 4 | 3 | 0 | KP 1.3(8), KP 1.5(9), KP 7(3) |  | AS Performance Monitoring | 2020-10-21 | [7 empty] | c | c | c
NPRR1011 | 8.1.1.4.4 | 8 | 1 | 1 | 4 | 4 | 0 | KP 1.3(2), KP 1.4(1), KP 1.5(9), KP 7(3) |  | AS Performance Monitoring | 2020-10-21 | [7 empty] | c | c | c
NPRR1011 | 8.1.2 | 8 | 1 | 2 | 0 | 0 | 0 | KP 7(2) |  | AS Performance Monitoring | 2020-10-21 | [7 empty] | c | c | c
NPRR1011 | 8.5.1.1 | 8 | 5 | 1 | 1 | 0 | 0 | KP 1.4(1) |  | AS Performance Monitoring | 2020-10-21 | [7 empty] | c | c | c
NOGRR211 | 9.1.10 | 9 | 1 | 10 | 0 | 0 | 0 | KP 7(2) |  | AS Performance Monitoring | 2020-10-21 | [7 empty] | c | c
NPRR1013 | 2.1 | 2 | 1 | 0 | 0 | 0 | 0 | All KPs |  | Defintions, Acronyms, Alignment | 2020-10-21 | [7 empty] | c | c | c
NPRR1013 | 2.2 | 2 | 2 | 0 | 0 | 0 | 0 | All KPs |  | Defintions, Acronyms, Alignment | 2020-10-21 | [7 empty] | c | c | c
KPs with No Direct Mapping | n/a | 0 | 0 | 0 | 0 | 0 | 0 | KP 1.1(8) | This KP concept is not specific to Protocol and is regarding near-term work that ERCOT will do in coordination with stakeholders groups.
KPs with No Direct Mapping | n/a | 0 | 0 | 0 | 0 | 0 | 0 | KP 1.3(5) | This KP concepts states something will remain the same under RTC.
KPs with No Direct Mapping | n/a | 0 | 0 | 0 | 0 | 0 | 0 | KP 1.3(10) | This KP concepts states something will remain the same under RTC.
KPs with No Direct Mapping | n/a | 0 | 0 | 0 | 0 | 0 | 0 | KP 1.5(2) | This KP is a technical detail that remains the same under RTC is not captured in Protocol.
KPs with No Direct Mapping | n/a | 0 | 0 | 0 | 0 | 0 | 0 | KP 1.5(14) | This KP concepts states something will remain the same under RTC.
KPs with No Direct Mapping | n/a | 0 | 0 | 0 | 0 | 0 | 0 | KP 2(1) | This KP concepts states something will remain the same under RTC.
KPs with No Direct Mapping | n/a | 0 | 0 | 0 | 0 | 0 | 0 | KP 3(20) | This KP concepts states something will remain the same under RTC.