## Action items
Open Action Items | Responsible | Notes | Assigned
Review of the outcome of the Load Distribution Factors (LDFs) in the 2021 timeframe | CMWG | NPRR1004 address identified issue. Will keep monitoring | 2020-02-05
Review increased transparency and policy awareness of Generic Transmission Constraints (GTCs) and curtailments | CMWG | Had 2 works on GTCs. NPRR994 and NOGRR215 are being discussed in realtion to this. | 2020-02-05
Review Locational Real-Time On-Line Reliability Deployment Price Adder | CMWG | ERCOT completing analysis and will come back to CMWG | 2019-11-06
|  | WMWG update – Reviewed analysis, Conditional 1 Solution to NPRR904 and next step is Locational Real-Time On-Line Reliability Deployment Price Adder review by CMWG. | 2019-05-01
2019-02-06
Review of Resource Adequacy forecasts and development of a Net Load forecast | SAWG | Ongoing | 2020-07-08
include possible evaluation and implementation of possible supplemental forecasts to CDR and SARA
Review liquidation procedures as they impact CRRs and recommend potential changes. | MCWG | NPRR1023 discussion ongoing | 2018-10-10
Review credit implications from potential hedging issues and credit risk for Demand Response customers due to high prices | MCWG/ | Not yet taken up | 2019-09-04
| DSWG | ERCOT discussion of upcoming analysis of 4CP and Retail Demand Response Survey | 2019-05-01
Review Fixed Costs in Fuel Adders and bring options to WMS | RCWG | Still Open | 2019-11-06
TAC Assignment: Develop and implement updated methodology used to determine cost of new entry (CONE) | SAWG | Goal - NPRR end of 2020 | 2020-07-08
|  | TAC updated assignment to CONE not Peaker Net Margin | 01/29/20 06/05/2019
Review impacts on CDR from monthly generation interconnection report | SAWG | Ongoing | 2019-09-04
Review concept of establishing a minimum threshold to post Total Wholesale Storage Load (WSL), utilization of Real-Time telemetry, and Resource disclosures | WMWG | Still Open
|  | Following implementing grey-boxed language to post WSL to MIS (NPRR461) | 2018-02-28
Review the mitigation issues and cost impacts and provide a recommendation | WMWG / RCWG | A part of it is IMM SOM issue | 2020-09-08
|  | Discussion with IMM and On December Agenda | 2019-12-04
|  | 06/05/2019- Removed review by RCWG, keep for WMWG | 2019-06-05
|  | 02/06/2019 WMS requested WMWG take up after local pricing issues | 2019-02-06
09/05/2018 – assigned to WMWG/RCWG
TAC Assignment: Review of Protocols in relation to use of “Emergency Condition” | WMWG | NPRR1001 discussion | 2020-09-08
|  | On December Agenda | 2019-12-04
|  | Related to OCN/Outage activity, subsequent NPRRs with E. Goff assistance | 2019-06-05
Look at actual loss factors compared to calculated losses in modeling | WMWG | Still Open - Tabled until RTC work is done | 2019-12-04
|  | Regarding 2018 UFE Analysis | 2019-07-10
Price Corrections and Consideration of “Significance” | WMWG | NPRR1024 discussion going on | 2020-03-04
Develop Alternatives 1 through 3 as potential solutions to the issues in NPRR991 as per the WMWG presentation to the June 3, 2020 WMS meeting | WMWG | WMS recommended rejection of NPRR991 | 2020-06-03
TAC Assignment: Review submission of TDSP read meter data for Loads with Interval Data Recorder (IDR) Meters and Non-Modeled Distributed Generators with Interval Data Recorders prior to Initial settlement of an Operating Day (Settlement – WMS; 867 – RMS) | WMS/RMS | Being addressed by PWG. second workshop scheduled for October 6th | 2020-09-08
|  | 02/22/18 TAC assigned IDR Meter Reads to COPS 3/22/18 TAC requested one forum for discussion/ solutions – RMS will host | 2017-11-30
TAC Assignment: Price Corrections and Consideration of “Significance” | WMS | NPRR1024 under discussion | 2020-01-29
IMM Recommendations from 2019 State of the Market Report assignments to WMS WG |  |  | 2020-07-08
1. Remove Reliability Unit Commitment (RUC) opt-out | WMWG
2. Eliminate two percent rule | CMWG | TAC working with ERCOT on process for voting on this
3. Change Transmission Cost Allocation | WMWG | Alternatives/DC Tie Load - one meeting
4. Include Shadow Prices of Ancillary Services Constraints | WMWG
5. Modifications to the Reliability Deployment Price Adder | WMWG
1) Reliability MWs, not Market MWs
2) Adjust restoration time
3) Remove ERS deployed MWs from ORDC reserve calculations
6. Local (Zonal) RDPA | CMWG | ERCOT is doing analysis
7. Mitigated Offer Changes | WMWG
1) Commitment costs for RUC intervals
2) Opportunity costs
3) Ensure no fixe/non-marginal costs included in fuel adder
8. Implement Transmission Demand Curves | CMWG | Scheduled for discussion next week

## Action items notes
Open Action Items | Responsible | Notes | Assigned
Review of the outcome of the Load Distribution Factors (LDFs) in the 2021 timeframe | CMWG | NPRR1004 address identified issue. Will keep monitoring | 2020-02-05
Review increased transparency and policy awareness of Generic Transmission Constraints (GTCs) and curtailments | CMWG | Had 2 works on GTCs. NPRR994 and NOGRR215 are being discussed in realtion to this. | 2020-02-05
Review Locational Real-Time On-Line Reliability Deployment Price Adder | CMWG | ERCOT completing analysis and will come back to CMWG | 2019-11-06
|  | WMWG update – Reviewed analysis, Conditional 1 Solution to NPRR904 and next step is Locational Real-Time On-Line Reliability Deployment Price Adder review by CMWG. | 2019-05-01
2019-02-06
Review of Resource Adequacy forecasts and development of a Net Load forecast | SAWG | Ongoing | 2020-07-08
include possible evaluation and implementation of possible supplemental forecasts to CDR and SARA
Review liquidation procedures as they impact CRRs and recommend potential changes. | MCWG | NPRR1023 discussion ongoing | 2018-10-10
Review credit implications from potential hedging issues and credit risk for Demand Response customers due to high prices | MCWG/ | Not yet taken up | 2019-09-04
| DSWG | ERCOT discussion of upcoming analysis of 4CP and Retail Demand Response Survey | 2019-05-01
Review Fixed Costs in Fuel Adders and bring options to WMS | RCWG | Still Open | 2019-11-06
TAC Assignment: Develop and implement updated methodology used to determine cost of new entry (CONE) | SAWG | Goal - NPRR end of 2020 | 2020-07-08
|  | TAC updated assignment to CONE not Peaker Net Margin | 01/29/20 06/05/2019
Review impacts on CDR from monthly generation interconnection report | SAWG | Ongoing | 2019-09-04
Constraint Definitions |  | Discussed and concluded that no action can be taken at this time
| WMWG / | Still Open – ERCOT contingency builder at CMWG | 2019-12-04
| NDSWG | Update requested | 2019-09-04
|  | Sham's question about contingencies where resource nodes are isolated due to the contingency definition and/or combination of prior outage and contingency. Should be discussed at NDSWG | 2017-07-12
Review concept of establishing a minimum threshold to post Total Wholesale Storage Load (WSL), utilization of Real-Time telemetry, and Resource disclosures | WMWG | Still Open | 2019-12-04
|  | Update Requested | 2019-09-04
|  | Following implementing grey-boxed language to post WSL to MIS (NPRR461) | 2018-02-28
Deep Dive of potential issues in the Low System-Wide Offer Cap (LCAP) Methodology if cumulative Peaker Net Margin (PNM) exceeds $315,000/Megawatts (MW) year and there are insufficient Ancillary Service offers in the Day-Ahead Market (DAM) | WMWG | Addressed by OBRR015
|  | Update Requested | 2019-09-04
2018-05-02
Review the mitigation issues and cost impacts and provide a recommendation | WMWG / RCWG | A part of it is IMM SOM issue | 2020-09-08
|  | Discussion with IMM and On December Agenda | 2019-12-04
|  | Update Requested | 2019-09-04
|  | 06/05/2019- Removed review by RCWG, keep for WMWG | 2019-06-05
|  | 02/06/2019 WMS requested WMWG take up after local pricing issues | 2019-02-06
09/05/2018 – assigned to WMWG/RCWG
TAC Assignment: Review of Protocols in relation to use of “Emergency Condition” | WMWG | NPRR1001 discussion | 2020-09-08
|  | On December Agenda | 2019-12-04
|  | Update Requested | 2019-09-04
|  | Related to OCN/Outage activity, subsequent NPRRs with E. Goff assistance | 2019-06-05
Look at actual loss factors compared to calculated losses in modeling | WMWG | Still Open - Tabled until RTC work is done | 2019-12-04
|  | Requested update | 2019-09-04
|  | Regarding 2018 UFE Analysis | 2019-07-10
Evaluate moving the deadline for revising energy offer curves closer to Real-Time operations | WMWG | Addressed for Batteries. MPs to submit additional NPRR if needed Waiting on ERCOT draft language | 2020-09-08
2019-12-04
2019-08-07
Review parameters/calculation for ORDC to account for ERS deployment | WMWG | IMM SOM issue | 2020-01-08
Review Process for EMR to set expectations for the 2020 Spring transmission Outage Season and what is best way to support that process – OBD, business process manual etc. | WMWG | Wait for ROS to complete Review first addressed during NPRR930 discussion | 2020-02-05
Review the availability and performance metrics for self-deployment, the reliability deployment price adder ramp, and the TDSP Load management programs | WMWG/DSWG | IMM SOM issue | 2020-02-05
Price Corrections and Consideration of “Significance” | WMWG | NPRR1024 discussion going on | 2020-03-04
Develop Alternatives 1 through 3 as potential solutions to the issues in NPRR991 as per the WMWG presentation to the June 3, 2020 WMS meeting | WMWG | WMS recommended rejection of NPRR991 | 2020-06-03
TAC Assignment: Review submission of TDSP read meter data for Loads with Interval Data Recorder (IDR) Meters and Non-Modeled Distributed Generators with Interval Data Recorders prior to Initial settlement of an Operating Day (Settlement – WMS; 867 – RMS) | WMS/RMS | Update requested | 2019-09-04
|  | Being addressed by PWG. second workshop scheduled for October 6th | 2020-09-08
|  | 02/22/18 TAC assigned IDR Meter Reads to COPS 3/22/18 TAC requested one forum for discussion/ solutions – RMS will host | 2017-11-30
TAC Assignment: Price Corrections and Consideration of “Significance” | WMS | NPRR1024 under discussion | 2020-01-29
TAC Assignment: Summer Assessment Items |  |  | 2019-12-04
1) Switchable Generation Resources (SWGRs) with Exelon items | WMWG/MSWG | WMWG to develop solution, then MSWG NPRR1019
2) Emergency Response Service (ERS) |  | NPRR1006
3) Credit/Collateral for QSE representing Resource only | DSWG/WMWG | WMWG mechanics, then MCWG after ERCOT drafting language
4) Usage of Operating Condition Notices (OCNs) for projected reserve capacity shortage | WMWG/MCWG | NPRR1001
5) N/A
6) Evaluate current TCEQ enforcement discretion process | WMS
7) Process for Summer demand response study
8) N/A
Calpine Item:
Review of Resource Adequacy forecasts and development of a Net Load forecast | WMS | Conclude at RMS, then WMS, then ROS
WMS
SAWG
TAC Assignment: NPRR1006, Update Emergency Response Service (ERS) Restoration Assumption for Reliability Deployment Price Adder to Match Actual Data | WMS | WMS had no consensus at 3/4/2020 Information Session, 2 distinct camps with 2 distinct values - No email vote. WMS Leadership will update TAC in formal report at next TAC meeting | 2020-03-04
IMM Recommendations from 2019 State of the Market Report assignments to WMS WG |  |  | 2020-07-08
1. Remove Reliability Unit Commitment (RUC) opt-out | WMWG
2. Eliminate two percent rule | CMWG | TAC working with ERCOT on process for voting on this
3. Change Transmission Cost Allocation | WMWG | Alternatives/DC Tie Load - one meeting
4. Include Shadow Prices of Ancillary Services Constraints | WMWG
5. Modifications to the Reliability Deployment Price Adder | WMWG
1) Reliability MWs, not Market MWs
2) Adjust restoration time
3) Remove ERS deployed MWs from ORDC reserve calculations
6. Local (Zonal) RDPA | CMWG | ERCOT is doing analysis
7. Mitigated Offer Changes | WMWG
1) Commitment costs for RUC intervals
2) Opportunity costs
3) Ensure no fixe/non-marginal costs included in fuel adder
8. Implement Transmission Demand Curves | CMWG | Scheduled for discussion next week