## Sheet1
TX SET Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2020-09-16
Agenda Item: | Decision / Resolution | Action Items :
July Meeting Notes
| Texas SET approved the notes as written. | The Texas SET Vice Chair will have the notes posted as final to the July meeting page key documents.
The Texas SET Chair provided the Retail Market Subcommittee (RMS) Update on the following topics.
Texas SET 4.0A Changes were all approved. | Posted on ERCOT.com http://www.ercot.com/mktrules/guides/txset
There were no new assignments given to Texas SET.
The RMS Chair and Vice chair stated that they are beginning to ramp up the communication to the Technical Advisory Committee (TAC) related to the Texas SET 5.0 version release to bring visibility of the possible timeline.
ERCOT Discussion Items
ERCOT Staff presented the 1020 Flight Update
ERCOT reviewed the proposed 2021 Flight Schedule and made changes where needed. ERCOT agreed to request RMS to approve the schedule at their next meeting.
Nueces Service Provider Discussion | Texas SET attendees agreed that an out-of-flight test after the 1020 flight completes is the best path to follow and that only connectivity testing should be required and coordinated between Nueces, their active Competitive Retailers (CRs) and ERCOT.
Projects
PR288-02 NAESB Application Tech Refresh Business driver is security—Possible testing specs collaboration with TDTMS | It was noted that project implementation is still on target for 11/2/2020 even though one CR is still in the process of implementing the change.
PR288-01 EDI Map and Translator Replacement | It was noted that project implementation is still on target for 11/2/2020.
ERCOT Staff conducted the TEXAS SET Change Control Conference Call (10 am) | Change Controls on the ERCOT Website. http://www.ercot.com/mktrules/issues/txsetcc
Change Control 2020-825 Modify the 814_20 Implementation Guide to allow the REF~PRT when NM101 equals MQ. | • Texas SET reached consensus with some minor changes and requested that the change be presented to RMS for an email vote that will take place about a week after their October meeting. • It was noted that Texas SET will have an emergency call on October 8th after the Retail Market Training Task Force (RMTTF) meeting to review and make recommendations on the related Implementation Guide redlined version if RMS votes to approve the Change Control.
RMS Assignments this month
COVID ERP Process Discussion (10:30) | TXU conducted a discussion on how the possibility of a customer already on the list that happens to move to another location, but stay with the same REP between now and the end of September would work. • The TDSPs noted that as long as they receive the list to add the ESI prior to the stop date September 30, 2020, there should be no issues from their side. • IT was also recommended that TXU might run the scenario past the PUCT staff to get their thoughts since there will be no more Solix list provided to the CRs.
Discussion Items
Texas SET Enhancement Matrix The Texas SET Chair conducted a discussion on the Texas SET Version 5.0 Release and made changes where needed.
Outstanding Change Controls
Premise Type CC: Update | The TDSPs stated that they are still working on the list, but should have an updated version to review at the next meeting.
IAS Solution CC: Review 814_03 and 814_04 | It was agreed to delay the discussion until next month to allow TDTMS to review the options at their meeting on October 17th.
Add PER segment for Email contact information to the 814_01, 03, and 16. | ONCOR reviewed the changes and agreed to submit the change control for a future Change Control call.
CSA CC: Review Change Control | • The Texas SET Chair reviewed the changes and made updates where needed. • Texas SET meeting attendees agreed that a REF~TD segment should be added to show changes to the new DTM 150 Start Date and DTM 151 End Date segments being added to the 814_18.
2020 Issue I150 A13 Reject Codes | • ERCOT Staff reviewed the two instances that they were to research. • Reject sent by ERCOT for “Invalid Business Process” on the 814_02. • Reject sent by one TDSP for “Order Ineligible to update” for the 814_13. • It was noted that the TDSPs are still compiling the list for possible new codes and will present those at a future meeting.
The Texas SET Chair conducted a discussion and requested consensus on a proposed 2021 TEXAS SET and TDTMS meeting schedule. | Texas SET agreed to wait until the Texas Data Transport and MarkeTrak Systems (TDTMS) has the chance to review at their September 17th meeting before sending the request to ERCOT.
RMS Leadership requested an update on the implementation timeline. | • Texas SET agreed that the Texas SET Version 5.0 implementation date could be the latter part of 2022 to the spring of 2023. It was also noted that due to other projects, the dates could be pushed out to the latter part of 2023 to the spring of 2024
Issues--No new Issues were discussed this month. | Issues on the ERCOT Website http://www.ercot.com/mktrules/issues/txset
Parking Lot
MISP Workshop Action Items • Add a MISP definition in RMG (RMGRR) | Still on Hold
Next Meeting--WebEx Only | 2020-10-21
Attendees F-T-F
Attendees Webex
Amy Velez Energy Services Group ESG | Kathryn Thurman ERCOT
Deb Belin MarketWise | Kathy Scott Centerpoint Energy
Debra Rabago Ambit Energy | Kyle Patrick NRG
Diana Rehfeldt TNMP | Lauren Damen NRG
Darise Taipalus TNMP | Paul Yockey ERCOT
Dave Lowder | Paula Shadle Nueces
Dave Michelsen ERCOT | Reed Comstock
Eric Blakey Just Energy | Sam Pak ONCOR
Frank Nunes ECInfoSystems | Sheri Wiegand TXUE
Jeff Chen Centerpoint Energy | Stephen Wilson TXU Energy
Jim Lee AEP | Steven Pliler TXU Energy
Jordon Troublefield ERCOT