## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
November 11, 2020

## Slide 2
Project Portfolio Update
  Recent / Upcoming Project Implementations
  2020 Release Targets
  2021 Release Targets
  ESR and DGR Pre-Passport Projects
  2020 Project Spending Forecast
  Priority/Rank Options for Revision Requests with Impacts
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Implementations
2020 November Release – Off-Cycle In Flight
  SCR804 – ERCOT GridGeo Access for Transmission Operators – 11/12/2020
  RIOO – RARF Replacement – View/Update – Follow-Up Release – 11/12/2020
  Enterprise Content Management System (ECMS) Phase 2 – 11/16/2020
2020 December Release – Off-Cycle In Flight
  MMS/OS Tech Refresh – 12/16/2020
2020 December Release – R6 – 12/8/2020 – 12/10/2020 In Flight
  SCR806 – Adding QSE and DME Information to Disclosure Reports
2021 February Release – R1 – 2/6/2020 – 2/8/2020 In Flight
  NPRR902 – ERCOT Critical Energy Infrastructure Information
  NPRR974 – Capacity Insufficiency Operating Condition Notice (OCN) Transparency
  NPRR978 – Alignment with Amendments to PUCT Substantive Rule 25.505
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2020 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/4 – 2/6 | April 3/31 – 4/2 | May 5/26 – 5/29 | August 8/4 – 8/6 | October 10/13 – 10/15 | December 12/8 – 12/10
NPRR873 SCR797 NPRR877 Ph2 NPRR968 NPRR943 EMIL Web Interface NPRR863 FFR NPRR960 NOGRR187 OBDRR011 | SCR802 NPRR928 NPRR929 NPRR978(a) NPRR988 NPRR953 | NPRR856 NPRR884 OBDRR006 SCR803 NPRR887 NPRR907 NPRR985 RMGRR163 NPRR837 NPRR930(a) NPRR933 RRGRR021 | NPRR935(a) NPRR951 NPRR977 NPRR955 NOGRR183 SCR781(a) RRGRR016 RRGRR019 | MIS Go-Live SCR804 RIOO R2 MMS/OS Refresh | SCR806 NPRR978(b)
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
E
E
E
R1
R2
R3
R4
R5
R6
3/1
NPRR930(a) – O&M portion
NPRR935(a) – Sections 4.2.2 (1) (6), 4.2.5
NPRR935(b) – Sections 2.1, 2.2, 4.2.3
NPRR978(a) – Initial report decommissions
NPRR978(b) – Additional report changes
PGRR070(b) – Remaining PGRR language
SCR781(a) – View / Edit capability
MMS/OS Upgrade “Chill”
MMS/OS Upgrade “Freeze”
ü
ü
ü
December
Off-Cycle
1/1
P
E
1/19
E
ü
ü
ü
CMM Release 2a
1/30
8/1
November
RIOO – 9/3
RARF Go-Live - View/Update
ü
ü
ü
ü
ü
ü
ü
ü
ü
5/1
ü
7/1
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
10/1
ü
ü

## Slide 5: 2021 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/6 – 2/8 | April 4/3 – 4/5 | May 5/29 – 5/31 | August 8/7 – 8/9 | October 10/15 – 10/17 | December 12/11 – 12/14
NPRR902 NPRR974 NPRR978(c) | NPRR905 NPRR971 NPRR986 NPRR1043 | NPRR829 NPRR904 NPRR1006 NPRR930 NPRR962 NPRR974 NPRR998 NPRR1019 OBDRR009 |  | SCR781(b) | FFR Advancement (NPRR863 FFR) NPRR1015 NPRR863 ECRS NPRR1015
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
NPRR978(c) – Final report changes
SCR781(b) – “Add” capability
TBD Items | 2018 | 2019 / 2020 / 2021
 | NPRR825(b), NPRR867, NPRR841 | RRs: 826, 857, 879, 885, 918, 935(b), 936, 939, 941, 965, 1020, 1030, PGRR066, SCR799, SCR800, SCR805
P
P
P
I
I
I
I
NS
I
I
E
E
E
On Hold
2024 Go-Lives
RIOO – Q4 2021
RARF Add Functionality Go-Live
TBD Go-Live
E
Pending Board approval
2021 Release Dates are still being finalized

## Slide 6: ESR and DGR Pre-Passport Projects
On 10/16/2020, ERCOT initiated two projects to deliver several Revision Requests relating to ESR and DGR
  PR353-01 BES Combo Model Implementation Strategy
    NPRR963 – Base Point Deviation Settlement & Deployment Performance Metrics for ESRs (Combo Model)
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    NPRR989 – BESTF-1 ESR Technical Requirements
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    NPRR1026 – BESTF-7 Self-Limiting Facilities and Self-Limiting Resources *
    NPRR1038 – BESTF-8 Limited Exemption from Reactive Power Requirements for Certain ESRs
    NOGRR204 – Related to NPRR989, BESTF-1
    NOGRR208 – Related to NPRR1002, BESTF-5
    OBDRR017 – Related to NPRR987, BESTF-3
    PGRR081 – Related to NPRR1026, BESTF-7 *
    RRGRR023 – Related to NPRR1002, BESTF-5 *
  PR354-01 DGR/DESR Implementation Strategy
    NPRR917 – Nodal Pricing for SODGs and SOTGs
    NPRR1016 – Clarify Requirements for DGRs and Distribution Energy Storage Resources (DESRs)
    PGRR082 – Revise Section 5 and Establish Small Generation Interconnection Process *
    RRGRR026 – Related to NPRR1016, Clarify Requirements for DGRs and DESRs
Since these projects are merging multiple RRs, it will take a few months before we can set target go-live dates for these two projects
BES: Battery Energy Storage
DGR: Distributed Generation Resource
ESR: Energy Storage Resource
* Expected to be added to scope upon Board approval

## Slide 7: 2020 Project Spending
2020 PPL Budget = $29.0M
“Potential Demand” represents internal ERCOT projects that have not been fully approved

## Slide 8: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR1026 | BESTF-7 Self-Limiting Facilities | 2020 | 3010 | $200k-$250k, 7-10 months Impact Areas: RIOO, EMS, OTS Plan to add to PR353-01 BES Combo Model Implementation Strategy project (see slide 6)
NPRR1007 NPRR1008 NPRR1009 NPRR1010 NPRR1011 NPRR1012 NPRR1013 | RTC–NP 3: Mgmt Activities ERCOT System RTC–NP 4: Day-Ahead Operations RTC–NP 5: Trans. Security Analysis & RUC RTC–NP 6: Adj. Period and Real-Time Ops RTC–NP 8: Performance Monitoring RTC–NP 9: Settlement and Billing RTC–NP 1, 2, 16, and 25 | 2020 | 235 | REGULATORY $50M-$55M, 3.5-4.5 years Impact Areas: MMS, EMS, S&B, NMMS, CMM, OTS, Registration Plan to add to Passport project
NPRR1014 | BESTF-4 Energy Storage Resource Single Model | 2020 | 3015 | $3.5M-$4.5M, 2-3 years Impact Areas: EMS, MMS, S&B, OS Plan to add to Passport project
NPRR1029 | BESTF-6 DC-Coupled Resources | 2020 | 3015 | $800k-$1.2M, 6-8 months Impact Areas: EMS, OS, S&B, MMS Plan to add to Passport project
PGRR082 | Revise Section 5 and Establish Small Generation Interconnection Process | 2020 | 3070 | $700k-$900k, 18-24 months Impact Areas: RIOO, NMMS Plan to add to PR354-01 DGR/DESR Implementation Strategy project (see slide 6)
Options for…
PPL Rank Information
Next available 2021 Rank in Business Strategy = 3280
Next available Rank in Regulatory = 320
Discussed at ROS