## Wind Chart
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Approved for Synchronization | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 19INR0174 | Elbow Creek repower | Howard | 2019-10-15 | 2007-11-30 | 2019-06-27 | Wind | WT | 0 | 2019 | No
[7 empty] | 18INR0038 | Barrow Ranch Wind | Andrews | 2020-07-31 | 2018-06-26 | 2020-02-26 | Wind | WT | 160 | 2020 | Yes
[7 empty] | 19INR0080 | Whitehorse Wind | Fisher | 2020-09-30 | 2018-12-05 | 2019-12-27 | Wind | WT | 418.9 | 2020 | Yes
[7 empty] | 19INR0156 | Aviator Wind | Coke | 2020-10-01 | 2019-02-14 | 2020-06-24 | Wind | WT | 525 | 2020 | Yes
[7 empty] | 16INR0081 | Mesteno Wind | Starr | 2020-10-31 | 2018-04-25 | 2019-12-12 | Wind | WT | 201.6 | 2020 | Yes
[7 empty] | 17INR0068 | Sweetwater 2 repower | Nolan | 2020-10-31 | 2003-06-27 | 2017-12-20 | Wind | WT | 7.3 | 2020 | No
[7 empty] | 18INR0073 | Sweetwater 1 repower | Nolan | 2020-10-31 | 2002-10-23 |  | Wind | WT | 3 | 2020 | No
[7 empty] | 19INR0112 | Cranel Wind | Refugio | 2020-11-20 | 2018-10-12 | 2020-05-19 | Wind | WT | 220 | 2020 | Yes
[7 empty] | 19INR0120 | Sherbino II Wind repower | Pecos | 2020-11-27 | 2008-02-28 | 2020-06-09 | Wind | WT | -18 | 2020 | Yes
[7 empty] | 11INR0062 | Shaffer Wind | Nueces | 2020-11-30 | 2013-07-02 | 2019-04-05 | Wind | WT | 226 | 2020 | Yes
[7 empty] | 17INR0069 | Trent repower | Nolan | 2020-11-30 | 2018-10-19 | 2019-05-09 | Wind | WT | 6.4 | 2020 | No
[7 empty] | 17INR0070 | Desert Sky repower | Pecos | 2020-11-30 | 2018-10-18 | 2019-09-06 | Wind | WT | 7.2 | 2020 | Yes
[7 empty] | 18INR0016 | RTS 2 Wind | McCulloch | 2020-12-02 | 2017-11-21 | 2020-04-29 | Wind | WT | 179.91 | 2020 | Yes
[7 empty] | 19INR0051 | Vera Wind | Knox | 2020-12-02 | 2018-07-10 | 2020-07-21 | Wind | WT | 208.8 | 2020 | Yes
[7 empty] | 20INR0305 | Vera Wind V110 | Knox | 2020-12-02 | 2018-07-10 | 2020-07-21 | Wind | WT | 34 | 2020 | Yes
[7 empty] | 19INR0053 | Hidalgo II Wind | Hidalgo | 2020-12-07 | 2019-04-25 | 2019-12-10 | Wind | WT | 51 | 2020 | Yes
[7 empty] | 15INR0064b | Harald (BearKat Wind B) | Glasscock | 2020-12-08 | 2018-05-30 | 2020-05-12 | Wind | WT | 162.1 | 2020 | Yes
[7 empty] | 17INR0035 | Las Majadas Wind | Willacy | 2020-12-14 | 2018-04-13 | 2020-10-21 | Wind | WT | 272.6 | 2020 | Yes
[7 empty] | 18INR0064 | Silver Star repower | Eastland | 2020-12-16 | 2018-10-16 | 2020-07-28 | Wind | WT | -7.2 | 2020 | Yes
[7 empty] | 20INR0019 | Trinity Hills Wind repower | Young | 2020-12-18 | 2018-10-17 | 2020-05-22 | Wind | WT | -27 | 2020 | No
[7 empty] | 20INR0045 | Maverick Creek I W | Concho | 2020-12-19 | 2018-07-30 | 2020-09-01 | Wind | WT | 373.2 | 2020 | Yes
[7 empty] | 17INR0031 | Espiritu Wind | Cameron | 2020-12-21 | 2020-01-29 |  | Wind | WT | 25.2 | 2020 | Yes
[7 empty] | 18INR0075 | Gulf Wind 1 repower | Kenedy | 2020-12-21 | 2007-08-28 | 2020-07-31 | Wind | WT | 0 | 2020 | No
[7 empty] | 20INR0042 | Chalupa Wind | Cameron | 2020-12-21 | 2018-09-28 | 2020-08-10 | Wind | WT | 174 | 2020 | Yes
[7 empty] | 19INR0100 | Prairie Hill Wind | McLennan | 2020-12-22 | 2018-09-17 | 2020-11-12 | Wind | WT | 300 | 2020 | Yes
[7 empty] | 16INR0111 | Venado Wind | Starr | 2020-12-30 | 2018-12-22 |  | Wind | WT | 201.6 | 2020 | Yes
[7 empty] | 16INR0086 | Cactus Flats Wind | Concho | 2020-12-31 | 2017-03-15 | 2018-06-11 | Wind | WT | 148.4 | 2020 | Yes
[7 empty] | 17INR0027b | Coyote Wind | Scurry | 2020-12-31 | 2016-08-09 | 2020-11-25 | Wind | WT | 242.6 | 2020 | Yes
[7 empty] | 17INR0052 | Horse13 CallD repower | Taylor | 2020-12-31 | 2019-05-22 |  | Wind | WT | 44 | 2020 | Yes
[7 empty] | 17INR0061 | Capricorn IV repower | Sterling | 2020-12-31 | 2008-01-15 | 2020-08-19 | Wind | WT | 9 | 2020 | No
[7 empty] | 18INR0033 | Oveja Wind | Irion | 2020-12-31 | 2018-07-24 | 2019-04-05 | Wind | WT | 300 | 2020 | Yes
[7 empty] | 18INR0069 | Indian Mesa repower | Pecos | 2020-12-31 | 2018-12-04 | 2018-11-02 | Wind | WT | 0 | 2020 | No
[7 empty] | 18INR0079 | Woodward I repower | Pecos | 2020-12-31 | 2018-12-12 | 2019-11-13 | Wind | WT | 0 | 2020 | Yes
[7 empty] | 19INR0163 | Sage Draw Wind | Lynn | 2020-12-31 | 2018-01-03 | 2019-12-12 | Wind | WT | 338 | 2020 | Yes
[7 empty] | 14INR0009 | WKN Amadeus Wind | Fisher | 2021-01-08 | 2018-03-15 | 2020-10-26 | Wind | WT | 250.12 | 2021 | Yes
[7 empty] | 17INR0025 | Reloj Del Sol Wind | Zapata | 2021-01-15 | 2018-12-21 |  | Wind | WT | 209.4 | 2021 | Yes
[7 empty] | 17INR0054 | Capricorn I & III repower | Sterling | 2021-01-29 | 2006-11-14 |  | Wind | WT | 32 | 2021 | No
[7 empty] | 21INR0449 | Panther Creek III Repower | Howard | 2021-02-02 | 2009-03-19 |  | Wind | WT | 15.96 | 2021 | No
[7 empty] | 18INR0059 | East Raymond Wind | Willacy | 2021-02-03 | 2018-09-18 | 2020-10-06 | Wind | WT | 201.6 | 2021 | Yes
[7 empty] | 19INR0038 | High Lonesome W | Crockett | 2021-02-08 | 2018-04-17 | 2019-11-26 | Wind | WT | 449.5 | 2021 | Yes
[7 empty] | 20INR0262 | High Lonesome Wind Phase II | Crockett | 2021-02-08 | 2019-07-22 | 2020-02-28 | Wind | WT | 50.6 | 2021 | Yes
[7 empty] | 18INR0080 | Woodward 2 repower | Pecos | 2021-02-28 | 2018-12-18 | 2018-12-19 | Wind | WT | 0 | 2021 | Yes
[7 empty] | 20INR0046 | Maverick Creek II W | Concho | 2021-03-23 | 2018-07-30 | 2020-11-02 | Wind | WT | 118.8 | 2021 | Yes
[7 empty] | 20INR0088 | West Raymond (El Trueno) Wind | Willacy | 2021-04-27 | 2019-05-20 |  | Wind | WT | 239.8 | 2021 | Yes
[7 empty] | 20INR0033 | WILDWIND | Cooke | 2021-06-18 | 2020-02-21 |  | Wind | WT | 180.08 | 2021 | Yes
[7 empty] | 18INR0031 | Maryneal Wind | Nolan | 2021-07-01 | 2020-01-31 |  | Wind | WT | 182.4 | 2021 | Yes
[7 empty] | 20INR0052 | Griffin Trail Wind | Knox | 2021-07-01 | 2019-03-04 |  | Wind | WT | 225.6 | 2021 | Yes
[7 empty] | 20INR0083 | Baird North Wind | Callahan | 2021-07-15 | 2019-05-31 |  | Wind | WT | 331.2 | 2021 | Yes
[7 empty] | 21INR0498 | Baird North II Wind | Callahan | 2021-07-15 | 2020-10-15 |  | Wind | WT | 20 | 2021 | Yes
[7 empty] | 19INR0128 | White Mesa Wind | Crockett | 2021-07-30 | 2018-12-13 |  | Wind | WT | 152.3 | 2021 | Yes
[7 empty] | 20INR0068 | Blackjack Creek Wind | Bee | 2021-09-30 | 2019-10-24 |  | Wind | WT | 240.5 | 2021 | Yes
[7 empty] | 21INR0005 | Hutt Wind | Midland | 2021-10-06 | 2020-05-26 |  | Wind | WT | 336 | 2021 | No
[7 empty] | 19INR0145 | Aquilla Lake Wind | Hill | 2021-10-29 | 2020-06-30 |  | Wind | WT | 202 | 2021 | Yes
[7 empty] | 20INR0256 | Aquilla Lake 2 Wind | Hill | 2021-10-29 | 2020-06-30 |  | Wind | WT | 100 | 2021 | Yes
[7 empty] | 16INR0085 | Priddy Wind | Mills | 2021-11-30 | 2020-08-13 |  | Wind | WT | 300 | 2021 | Yes
[7 empty] | 18INR0043 | Edmondson Ranch Wind | Glasscock | 2021-12-01 | 2017-10-04 |  | Wind | WT | 293.28 | 2021 | Yes
[7 empty] | 20INR0142 | Ajax Wind | Wilbarger | 2021-12-01 | 2020-07-14 |  | Wind | WT | 630 | 2021 | Yes
[7 empty] | 15INR0034 | El Algodon Alto W | San Patricio | 2021-12-15 | 2020-04-02 |  | Wind | WT | 201 | 2021 | Yes
[7 empty] | 19INR0052 | TG East Wind | Knox | 2021-12-15 | 2018-10-22 |  | Wind | WT | 336 | 2021 | Yes
[7 empty] | 19INR0117 | Roadrunner Crossing Wind | Eastland | 2021-12-15 | 2020-04-17 |  | Wind | WT | 200.2 | 2021 | Yes
[7 empty] | 20INR0217 | CAROL wind | Potter | 2021-12-17 | 2020-09-11 |  | Wind | WT | 169.2 | 2021 | No
[7 empty] | 21INR0263 | Monarch Creek Wind | Throckmorton | 2021-12-31 | 2020-08-24 |  | Wind | WT | 209 | 2021 | No
[7 empty] | 21INR0467 | Apogee Wind | Haskell | 2021-12-31 | 2020-03-10 |  | Wind | WT | 393.24 | 2021 | Yes
[7 empty] | 20INR0129 | Foxtrot Wind | Karnes | 2022-02-01 | 2020-05-05 |  | Wind | WT | 504 | 2022 | Yes
[7 empty] | 18INR0068 | Loraine Windpark Phase III | Mitchell | 2022-05-06 | 2018-04-10 |  | Wind | WT | 100 | 2022 | Yes
[7 empty] | 18INR0030 | Canyon Wind | Scurry | 2022-05-31 | 2018-09-20 |  | Wind | WT | 259.44 | 2022 | Yes
[7 empty] | 16INR0104 | Big Sampson Wind | Crockett | 2022-09-01 | 2019-11-08 |  | Wind | WT | 400 | 2022 | No
[7 empty] | 16INR0033 | Hart Wind | Castro | 2022-12-31 | 2018-08-06 |  | Wind | WT | 151.5 | 2022 | No
[7 empty] | 19INR0022 | Monte Alto I | Willacy | 2022-12-31 | 2020-02-13 |  | Wind | WT | 223.8 | 2022 | No
[7 empty] | 19INR0099a | Kontiki 1 Wind (ERIK) | Glasscock | 2023-03-01 | 2018-05-07 |  | Wind | WT | 250.1 | 2023 | Yes
[7 empty] | 19INR0099b | Kontiki 2 Wind (ERNEST) | Glasscock | 2023-03-01 | 2018-05-07 |  | Wind | WT | 250.1 | 2023 | Yes
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | Cumulative MW Synchronized | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned
2000 | 160.37 | 160.37 | 0 | 0 | 0 | 0
2001 | 859.29 | 859.29 | 0 | 0 | 0 | 0
2002 | 1019.79 | 1019.79 | 0 | 0 | 0 | 0
2003 | 1217.29 | 1217.29 | 0 | 0 | 0 | 0
2004 | 1325.29 | 1325.29 | 0 | 0 | 0 | 0
2005 | 1902.69 | 1902.69 | 0 | 0 | 0 | 0
2006 | 2633.39 | 2633.39 | 0 | 0 | 0 | 0
2007 | 4203.41 | 4203.41 | 0 | 0 | 0 | 0
2008 | 8101.01 | 8101.01 | 0 | 0 | 0 | 0
2009 | 9007.57 | 9007.57 | 0 | 0 | 0 | 0
2010 | 9458.49 | 9458.49 | 0 | 0 | 0 | 0
2011 | 9603.49 | 9603.49 | 0 | 0 | 0 | 0
2012 | 10698.35 | 10698.35 | 0 | 0 | 0 | 0
2013 | 11100.05 | 11100.05 | 0 | 0 | 0 | 0
2014 | 12728.93 | 12728.93 | 0 | 0 | 0 | 0
2015 | 15857.48 | 15857.48 | 0 | 0 | 0 | 0
2016 | 17662.45 | 17662.45 | 0 | 0 | 0 | 0
2017 | 20697.84 | 20697.84 | 0 | 0 | 0 | 0
2018 | 21777 | 21777 | 0 | 0 | 0 | 0
2019 | 23860 | 23860 | 0 | 0 | 0 | 0
2020 | 29908.58 | 25120.58 | 4514 | 271 | 3 | 0
2021 | 36177.97 | 25120.58 | 5584.43 | 4707.8 | 765.16 | 0
2022 | 37816.25 | 25120.58 | 5584.43 | 5571.24 | 1540 | 0
2023 | 38316.45 | 25120.58 | 5584.43 | 6071.44 | 1540 | 0

## Solar Chart
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Approved for Synchronization | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 12INR0059b | HOVEY (Barilla Solar 1B) | Pecos | 2020-04-30 | 2013-12-26 |  | Solar | PV | 7.4 | 2020 | Yes
[7 empty] | 19INR0184 | Oxy Solar | Ector | 2020-09-30 | 2019-01-30 | 2019-07-31 | Solar | PV | 16.2 | 2020 | Yes
[7 empty] | 18INR0062 | Wagyu Solar | Brazoria | 2020-10-30 | 2019-06-03 | 2020-05-22 | Solar | PV | 120 | 2020 | Yes
[7 empty] | 18INR0045 | Misae Solar | Childress | 2020-12-15 | 2018-07-18 | 2020-01-16 | Solar | PV | 240.8 | 2020 | Yes
[7 empty] | 20INR0031 | Rippey Solar | Cooke | 2020-12-18 | 2019-05-15 | 2020-11-20 | Solar | PV | 59.8 | 2020 | Yes
[7 empty] | 20INR0261 | Kellam Solar | Van Zandt | 2020-12-18 | 2019-07-30 | 2020-11-17 | Solar | PV | 59.8 | 2020 | Yes
[7 empty] | 19INR0034 | Greasewood Solar | Pecos | 2020-12-23 | 2020-01-29 | 2020-10-10 | Solar | PV | 255 | 2020 | Yes
[7 empty] | 19INR0151 | Impact Solar | Lamar | 2020-12-23 | 2019-07-02 | 2020-09-02 | Solar | PV | 198.55 | 2020 | Yes
[7 empty] | 20INR0204 | BlueBell Solar II | Sterling | 2020-12-31 | 2020-03-12 | 2020-11-12 | Solar | PV | 115 | 2020 | Yes
[7 empty] | 18INR0055 | Long Draw Solar | Borden | 2021-01-04 | 2018-08-16 | 2020-11-20 | Solar | PV | 226.73 | 2021 | Yes
[7 empty] | 20INR0219 | Eunice Solar | Andrews | 2021-01-29 | 2019-12-11 |  | Solar | PV | 426.7 | 2021 | Yes
[7 empty] | 20INR0054 | Taygete Solar | Pecos | 2021-02-15 | 2018-10-26 |  | Solar | PV | 255.07 | 2021 | Yes
[7 empty] | 20INR0037 | Coniglio Solar | Fannin | 2021-03-01 | 2019-08-03 |  | Solar | PV | 125.68 | 2021 | Yes
[7 empty] | 19INR0081 | Anson Solar 1 | Jones | 2021-03-03 | 2019-06-05 |  | Solar | PV | 201.53 | 2021 | Yes
[7 empty] | 17INR0020b | RE Maplewood 2b Solar | Pecos | 2021-03-12 | 2019-05-06 |  | Solar | PV | 28 | 2021 | Yes
[7 empty] | 21INR0026 | Juno Solar (Phase I) | Borden | 2021-05-15 | 2018-12-22 |  | Solar | PV | 166.12 | 2021 | Yes
[7 empty] | 15INR0044 | Corazon Solar | Webb | 2021-05-31 | 2020-01-09 |  | Solar | PV | 202.64 | 2021 | Yes
[7 empty] | 15INR0090 | Pflugerville Solar | Travis | 2021-05-31 | 2017-06-13 |  | Solar | PV | 144 | 2021 | Yes
[7 empty] | 17INR0020a | RE Maplewood 2a Solar | Pecos | 2021-06-01 | 2019-05-06 |  | Solar | PV | 222 | 2021 | Yes
[7 empty] | 19INR0044 | Lily Solar | Kaufman | 2021-06-01 | 2019-03-29 |  | Solar | PV | 147.63 | 2021 | Yes
[7 empty] | 20INR0130 | Ramsey Solar | Wharton | 2021-06-01 | 2020-05-29 |  | Solar | PV | 514 | 2021 | Yes
[7 empty] | 21INR0233 | Taygete II Solar | Pecos | 2021-06-01 | 2019-03-27 |  | Solar | PV | 203.8 | 2021 | Yes
[7 empty] | 21INR0477 | Azure Sky Solar | Haskell | 2021-06-01 | 2020-04-01 |  | Solar | PV | 228.4 | 2021 | Yes
[7 empty] | 19INR0088 | Aragorn Solar | Culberson | 2021-06-30 | 2018-05-31 |  | Solar | PV | 187.2 | 2021 | Yes
[7 empty] | 20INR0032 | Titan Solar | Culberson | 2021-06-30 | 2019-02-04 |  | Solar | PV | 270 | 2021 | Yes
[7 empty] | 21INR0229 | Prospero Solar II | Andrews | 2021-07-01 | 2020-01-17 |  | Solar | PV | 250 | 2021 | Yes
[7 empty] | 18INR0060 | Brightside Solar | Bee | 2021-07-30 | 2020-06-11 |  | Solar | PV | 50 | 2021 | Yes
[7 empty] | 19INR0091 | Phoenix Solar | Fannin | 2021-08-10 | 2019-10-22 |  | Solar | PV | 82.3 | 2021 | Yes
[7 empty] | 21INR0501 | Juno Solar (Phase II) | Borden | 2021-08-15 | 2018-12-22 |  | Solar | PV | 147.09 | 2021 | Yes
[7 empty] | 21INR0276 | Elara Solar | Frio | 2021-09-01 | 2019-07-12 |  | Solar | PV | 132.4 | 2021 | Yes
[7 empty] | 15INR0059 | Emerald Grove Solar | Pecos | 2021-09-15 | 2017-12-04 |  | Solar | PV | 108 | 2021 | Yes
[7 empty] | 19INR0073 | Shakes Solar | Zavala | 2021-10-01 | 2018-10-26 |  | Solar | PV | 206 | 2021 | Yes
[7 empty] | 19INR0121 | Galloway Solar | Concho | 2021-10-01 | 2019-12-20 |  | Solar | PV | 250 | 2021 | Yes
[7 empty] | 20INR0216 | Starr Solar Ranch | Starr | 2021-10-01 | 2020-10-01 |  | Solar | PV | 135.99 | 2021 | Yes
[7 empty] | 20INR0082 | Vision Solar 1 | Navarro | 2021-10-05 | 2020-01-13 |  | Solar | PV | 129.24 | 2021 | Yes
[7 empty] | 20INR0081 | Strategic Solar 1 | Ellis | 2021-10-31 | 2020-01-13 |  | Solar | PV | 136.85 | 2021 | Yes
[7 empty] | 16INR0114 | Upton Solar | Upton | 2021-11-01 | 2015-12-04 |  | Solar | PV | 104.56 | 2021 | Yes
[7 empty] | 19INR0103 | Rodeo Solar | Andrews | 2021-11-01 | 2019-08-20 |  | Solar | PV | 200 | 2021 | No
[7 empty] | 19INR0042 | Long Point Solar | Brazoria | 2021-12-01 | 2019-10-24 |  | Solar | PV | 100 | 2021 | No
[7 empty] | 21INR0031 | Indigo Solar | Fisher | 2021-12-15 | 2020-10-15 |  | Solar | PV | 125 | 2021 | No
[7 empty] | 21INR0274 | Carol Solar | Potter | 2021-12-17 | 2020-09-11 |  | Solar | PV | 223.2 | 2021 | No
[7 empty] | 19INR0085 | Blue Jay Solar | Grimes | 2021-12-30 | 2020-10-26 |  | Solar | PV | 210 | 2021 | Yes
[7 empty] | 20INR0222 | Tyson Nick Solar | Lamar | 2021-12-30 | 2020-08-28 |  | Solar | PV | 90 | 2021 | No
[7 empty] | 20INR0266 | Tres Bahias Solar | Calhoun | 2021-12-30 | 2020-08-07 |  | Solar | PV | 195 | 2021 | Yes
[7 empty] | 18INR0053 | Fort Bend Solar | Fort Bend | 2021-12-31 | 2019-06-30 |  | Solar | PV | 240 | 2021 | Yes
[7 empty] | 19INR0045 | Rayos Del Sol | Cameron | 2021-12-31 | 2018-11-06 |  | Solar | PV | 137.45 | 2021 | Yes
[7 empty] | 19INR0093 | Solemio | Hopkins | 2021-12-31 | 2020-10-22 |  | Solar | PV | 81.4 | 2021 | No
[7 empty] | 20INR0101 | Westoria Solar | Brazoria | 2021-12-31 | 2020-03-20 |  | Solar | PV | 203.35 | 2021 | Yes
[7 empty] | 21INR0213 | Vancourt Solar | Cameron | 2021-12-31 | 2020-06-11 |  | Solar | PV | 45.73 | 2021 | Yes
[7 empty] | 21INR0221 | Delilah Solar 1 | Lamar | 2021-12-31 | 2020-08-26 |  | Solar | PV | 250 | 2021 | Yes
[7 empty] | 21INR0389 | Red-tailed Hawk Solar | Wharton | 2021-12-31 | 2020-08-28 |  | Solar | PV | 355.27 | 2021 | Yes
[7 empty] | 21INR0406 | Old 300 Solar Center | Fort Bend | 2021-12-31 | 2020-04-16 |  | Solar | PV | 438.75 | 2021 | Yes
[7 empty] | 21INR0491 | Delilah Solar 1B | Lamar | 2021-12-31 | 2020-08-27 |  | Solar | PV | 250 | 2021 | Yes
[7 empty] | 18INR0050 | Mustang Creek Solar | Jackson | 2022-01-01 | 2019-01-04 |  | Solar | PV | 152.25 | 2022 | Yes
[7 empty] | 19INR0041 | Myrtle Solar | Brazoria | 2022-01-01 | 2019-11-13 |  | Solar | PV | 240 | 2022 | Yes
[7 empty] | 19INR0134 | Cottonwood Bayou Solar | Brazoria | 2022-01-01 | 2019-11-13 |  | Solar | PV | 150 | 2022 | No
[7 empty] | 20INR0069 | Danish Fields Solar | Wharton | 2022-01-01 | 2020-02-24 |  | Solar | PV | 201 | 2022 | Yes
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | Cumulative MW Synchronized | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned | 21INR0016 | Danish Fields II Solar | Wharton | 2022-01-01 | 2020-02-24 |  | Solar | PV | 201 | 2022 | Yes
2010 | 15 | 15 | 0 | 0 | 0 | 0 | 21INR0017 | Danish Fields III Solar | Wharton | 2022-01-01 | 2020-02-24 |  | Solar | PV | 201 | 2022 | Yes
2011 | 15 | 15 | 0 | 0 | 0 | 0 | 19INR0001 | Texas Solar Nova | Kent | 2022-01-31 | 2019-07-01 |  | Solar | PV | 252.2 | 2022 | Yes
2012 | 72.3 | 72.3 | 0 | 0 | 0 | 0 | 20INR0203 | Pine Forest Solar | Hopkins | 2022-02-01 | 2020-07-29 |  | Solar | PV | 284.29 | 2022 | No
2013 | 121.2 | 121.2 | 0 | 0 | 0 | 0 | 21INR0384 | Concho Valley Solar | Tom Green | 2022-03-01 | 2020-09-28 |  | Solar | PV | 159.8 | 2022 | No
2014 | 168.7 | 168.7 | 0 | 0 | 0 | 0 | 21INR0413 | Big Star Solar | Bastrop | 2022-03-31 | 2020-10-02 |  | Solar | PV | 220.61 | 2022 | No
2015 | 289.28 | 289.28 | 0 | 0 | 0 | 0 | 19INR0035 | Norton Solar | Runnels | 2022-04-01 | 2019-06-20 |  | Solar | PV | 125 | 2022 | Yes
2016 | 565.78 | 565.78 | 0 | 0 | 0 | 0 | 19INR0155 | Morrow Lake Solar | Frio | 2022-04-01 | 2019-08-29 |  | Solar | PV | 204 | 2022 | Yes
2017 | 1067.78 | 1067.78 | 0 | 0 | 0 | 0 | 21INR0431 | Galloway 2 Solar | Concho | 2022-04-01 | 2019-12-20 |  | Solar | PV | 110 | 2022 | Yes
2018 | 1856.78 | 1856.78 | 0 | 0 | 0 | 0 | 22INR0205 | Sbranch Solar | Wharton | 2022-04-01 | 2020-07-26 |  | Solar | PV | 154 | 2022 | Yes
2019 | 2281.38 | 2281.38 | 0 | 0 | 0 | 0 | 22INR0352 | Sparta Solar | Bee | 2022-04-01 | 2020-08-14 |  | Solar | PV | 256 | 2022 | Yes
2020 | 4926.46 | 3853.91 | 1065.15 | 7.4 | 0 | 0 | 20INR0248 | Second Division Solar | Brazoria | 2022-05-01 | 2020-10-14 |  | Solar | PV | 100 | 2022 | No
2021 | 13353.54 | 3853.91 | 1291.88 | 7388.15 | 819.6 | 0 | 20INR0236 | Old Hickory Solar | Jackson | 2022-05-15 | 2020-06-30 |  | Solar | PV | 250 | 2022 | Yes
2022 | 20763.78 | 3853.91 | 1291.88 | 11215.79 | 4402.2 | 0 | 21INR0019 | Zier Solar | Kinney | 2022-05-25 | 2020-10-22 |  | Solar | PV | 160 | 2022 | No
2023 | 21379.78 | 3853.91 | 1291.88 | 11215.79 | 5018.2 | 0 | 20INR0214 | Noble Solar | Denton | 2022-05-30 | 2020-10-10 |  | Solar | PV | 279 | 2022 | No
[7 empty] | 20INR0053 | Bravepost Solar | Tom Green | 2022-05-31 | 2019-10-30 |  | Solar | PV | 200 | 2022 | Yes
[7 empty] | 20INR0143 | Soda Lake Solar 2 | Crane | 2022-05-31 | 2018-08-20 |  | Solar | PV | 202.99 | 2022 | No
[7 empty] | 21INR0021 | Green Holly Solar | Dawson | 2022-05-31 | 2020-05-19 |  | Solar | PV | 413.6 | 2022 | No
[7 empty] | 21INR0022 | Red Holly Solar | Dawson | 2022-05-31 | 2020-10-19 |  | Solar | PV | 260 | 2022 | No
[7 empty] | 21INR0278 | Fighting Jays Solar | Fort Bend | 2022-05-31 | 2020-06-22 |  | Solar | PV | 356.55 | 2022 | Yes
[7 empty] | 22INR0257 | Corazon Solar Phase II | Webb | 2022-05-31 | 2020-08-04 |  | Solar | PV | 203.9 | 2022 | No
[7 empty] | 19INR0131 | Cutlass Solar | Fort Bend | 2022-06-01 | 2020-09-23 |  | Solar | PV | 300 | 2022 | No
[7 empty] | 20INR0098 | Danciger Solar | Brazoria | 2022-06-01 | 2020-03-20 |  | Solar | PV | 203.2 | 2022 | Yes
[7 empty] | 21INR0351 | 7V Solar | Fayette | 2022-09-30 | 2020-09-01 |  | Solar | PV | 246.3 | 2022 | No
[7 empty] | 20INR0226 | Timberwolf POI A Solar | Upton | 2022-12-01 | 2019-12-11 |  | Solar | PV | 152.11 | 2022 | No
[7 empty] | 20INR0091 | Misae Solar II | Childress | 2022-12-20 | 2019-02-21 |  | Solar | PV | 517.35 | 2022 | Yes
[7 empty] | 19INR0169 | Sun Valley Solar | Hill | 2022-12-29 | 2020-03-15 |  | Solar | PV | 250 | 2022 | No
[7 empty] | 20INR0202 | Rueter Solar | Bosque | 2022-12-31 | 2020-10-15 |  | Solar | PV | 200 | 2022 | No
[7 empty] | 21INR0261 | Horizon Solar | Frio | 2022-12-31 | 2019-07-12 |  | Solar | PV | 204.09 | 2022 | Yes
[7 empty] | 16INR0049 | Nazareth Solar | Castro | 2023-06-01 | 2018-05-10 |  | Solar | PV | 201 | 2023 | No
[7 empty] | 20INR0241 | Crowded Star Solar | Jones | 2023-06-30 | 2019-12-17 |  | Solar | PV | 215 | 2023 | No
[7 empty] | 21INR0490 | Delilah Solar 1A | Lamar | 2023-06-30 | 2020-08-27 |  | Solar | PV | 200 | 2023 | No

## Battery Chart
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Approved for Synchronization | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 20INR0220 | Eunice Storage | Andrews | 2021-01-29 | 2019-12-11 |  | Battery | BA | 40.26 | 2021 | Yes
[7 empty] | 20INR0276 | North Fork Energy Storage | Williamson | 2021-05-15 | 2020-04-28 |  | Battery | BA | 100.49 | 2021 | Yes
[7 empty] | 20INR0294 | Lily Storage | Kaufman | 2021-06-01 | 2020-07-14 |  | Battery | BA | 51.74 | 2021 | Yes
[7 empty] | 21INR0364 | Gambit Batt | Brazoria | 2021-06-01 | 2020-05-28 |  | Battery | BA | 102.4 | 2021 | Yes
[7 empty] | 21INR0365 | Bat Cave Energy Storage | Mason | 2021-06-01 | 2020-02-21 |  | Battery | BA | 100.49 | 2021 | Yes
[7 empty] | 21INR0476 | Azure Sky BESS | Haskell | 2021-06-01 | 2020-04-01 |  | Battery | BA | 77.6 | 2021 | Yes
[7 empty] | 20INR0291 | Silicon Hill Storage | Travis | 2021-06-15 | 2020-03-27 |  | Battery | BA | 104.62 | 2021 | Yes
[7 empty] | 21INR0244 | Madero Grid | Hidalgo | 2021-06-30 | 2019-12-06 |  | Battery | BA | 101.52 | 2021 | Yes
[7 empty] | 21INR0522 | Ignacio Grid | Hidalgo | 2021-06-30 | 2020-10-27 |  | Battery | BA | 101.52 | 2021 | Yes
[7 empty] | 19INR0176 | Roughneck Storage | Brazoria | 2021-07-01 | 2020-05-13 |  | Battery | BA | 50 | 2021 | Yes
[7 empty] | 21INR0033 | Red Holly Storage | Dawson | 2021-07-01 | 2020-10-19 |  | Battery | BA | 50 | 2021 | No
[7 empty] | 20INR0089 | Chisholm Grid | Tarrant | 2021-07-09 | 2019-08-16 |  | Battery | BA | 101.7 | 2021 | Yes
[7 empty] | 21INR0460 | Republic Road Storage | Robertson | 2021-07-12 | 2020-10-29 |  | Battery | BA | 50 | 2021 | Yes
[7 empty] | 21INR0029 | Green Holly Storage | Dawson | 2021-08-01 | 2020-10-19 |  | Battery | BA | 50 | 2021 | No
[7 empty] | 21INR0357 | SP TX-12B BESS | Upton | 2021-09-01 | 2020-05-01 |  | Battery | BA | 25.12 | 2021 | Yes
[7 empty] | 21INR0510 | Crossett Power Batt | Crane | 2021-12-30 | 2020-08-05 |  | Battery | BA | 206.97 | 2021 | No
[7 empty] | 20INR0281 | Queen BESS | Upton | 2022-05-06 | 2020-08-06 |  | Battery | BA | 50 | 2022 | No
[7 empty] | 20INR0280 | High Lonesome BESS | Crockett | 2022-06-01 | 2020-08-26 |  | Battery | BA | 50 | 2022 | No
[7 empty] | 22INR0325 | BRP Dickens BESS | Dickens | 2022-09-30 | 2020-11-02 |  | Battery | BA | 202.41 | 2022 | No
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | Cumulative MW Synchronized | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned
2012 | 36 | 36 | 0 | 0 | 0 | 0
2013 | 36 | 36 | 0 | 0 | 0 | 0
2014 | 36 | 36 | 0 | 0 | 0 | 0
2015 | 38 | 38 | 0 | 0 | 0 | 0
2016 | 39 | 39 | 0 | 0 | 0 | 0
2017 | 72.5 | 72.5 | 0 | 0 | 0 | 0
2018 | 93.8 | 93.8 | 0 | 0 | 0 | 0
2019 | 103.7 | 103.7 | 0 | 0 | 0 | 0
2020 | 306.4 | 195.4 | 0 | 0 | 0 | 111
2021 | 1630.41 | 195.4 | 0 | 1007.46 | 306.97 | 120.58
2022 | 1932.44 | 195.4 | 0 | 1007.46 | 609 | 120.58

## Gas-Combined Cycle Chart
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Approved for Synchronization | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 16INR0054 | NASA | Harris | 2018-09-01 | 2016-10-27 | 2017-11-27 | Gas | CC | 12 | 2018 | Yes
[7 empty] | 20INR0282 | Odessa-Ector Unit 2 (Block 2) Uprate Repower | Ector | 2020-06-15 | 2019-11-01 |  | Gas | CC | 83 | 2020 | Yes
[7 empty] | 20INR0286 | Wise County Power Repower (CT1, CT2) | Wise | 2020-12-01 | 2001-03-19 |  | Gas | CC | 21 | 2020 | Yes
[7 empty] | 18INR0077 | Colorado Bend 2 repower | Wharton | 2020-12-31 | 2015-12-17 | 2019-06-19 | Gas | CC | 45 | 2020 | No
[7 empty] | 19INR0014 | Formosa Increase | Calhoun | 2020-12-31 | 2019-04-30 | 2020-03-04 | Gas | CC | 240 | 2020 | Yes
[7 empty] | 21INR0328 | RIO NOGALES UPGRADE CT2 repower | Guadalupe | 2021-01-02 | 2020-04-18 | 2020-11-19 | Gas | CC | 13 | 2021 | No
[7 empty] | 20INR0312 | Barney Davis IPAC #4 repower | Nueces | 2021-05-01 | 2008-06-18 |  | Gas | CC | 48 | 2021 | No
[7 empty] | 21INR0202 | R Massengale | Lubbock | 2021-06-03 | 2020-10-30 |  | Gas | CC | 58 | 2021 | Yes
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | Cumulative MW Synchronized | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned
1999 | 2867 | 2867 | 0 | 0 | 0 | 0
2000 | 7851 | 7851 | 0 | 0 | 0 | 0
2001 | 14437 | 14437 | 0 | 0 | 0 | 0
2002 | 18913 | 18913 | 0 | 0 | 0 | 0
2003 | 24611 | 24611 | 0 | 0 | 0 | 0
2004 | 26111 | 26111 | 0 | 0 | 0 | 0
2005 | 26009 | 26009 | 0 | 0 | 0 | 0
2006 | 26728 | 26728 | 0 | 0 | 0 | 0
2007 | 27285 | 27285 | 0 | 0 | 0 | 0
2008 | 27846 | 27846 | 0 | 0 | 0 | 0
2009 | 28779 | 28779 | 0 | 0 | 0 | 0
2010 | 30240 | 30240 | 0 | 0 | 0 | 0
2011 | 30958 | 30958 | 0 | 0 | 0 | 0
2012 | 30958 | 30958 | 0 | 0 | 0 | 0
2013 | 31008 | 31008 | 0 | 0 | 0 | 0
2014 | 33550 | 33550 | 0 | 0 | 0 | 0
2015 | 34367 | 34367 | 0 | 0 | 0 | 0
2016 | 33968 | 33968 | 0 | 0 | 0 | 0
2017 | 36429 | 36429 | 0 | 0 | 0 | 0
2018 | 36429 | 36429 | 0 | 0 | 0 | 0
2019 | 36429 | 36429 | 0 | 0 | 0 | 0
2020 | 36830 | 36429 | 297 | 104 | 0 | 0
2021 | 36949 | 36429 | 310 | 162 | 48 | 0

## Gas-Other Chart
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Approved for Synchronization | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 20INR0206 | PES1 | Harris | 2020-12-23 | 2019-12-20 |  | Gas | GT | 306 | 2020 | Yes
[7 empty] | 20INR0104 | GoodAlta | Navarro | 2021-04-01 | 2020-03-16 |  | Gas | GT | 150 | 2021 | No
[7 empty] | 19INR0056 | Chamon 2 | Harris | 2021-05-01 | 2019-09-20 |  | Gas | GT | 100 | 2021 | No
[7 empty] | 19INR0057 | Old Bloomington Road | Victoria | 2021-05-01 | 2020-05-20 |  | Gas | GT | 100 | 2021 | Yes
[7 empty] | 20INR0231 | Topaz Power Plant | Galveston | 2021-06-01 | 2020-04-28 |  | Gas | GT | 510 | 2021 | Yes
[7 empty] | 20INR0267 | Greens Bayou Expansion | Harris | 2021-06-01 | 2019-10-31 |  | Gas | GT | 140 | 2021 | No
[7 empty] | 21INR0201 | Brandon | Lubbock | 2021-06-03 | 2020-10-30 |  | Gas | GT | 21 | 2021 | Yes
[7 empty] | 22INR0371 | PES 2 Power Station | Harris | 2021-07-01 | 2019-12-17 |  | Gas | GT | 102 | 2021 | Yes
[7 empty] | 21INR0506 | Ty Cooke | Lubbock | 2021-07-31 | 2020-10-30 |  | Gas | GT | 33 | 2021 | Yes
[7 empty] | 17INR0022 | MIRAGE | Harris | 2021-11-01 | 2016-08-31 |  | Gas | GT | 11 | 2021 | Yes
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | Cumulative MW Synchronized | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned
1999 | 33796.03 | 33796.03 | 0 | 0 | 0 | 0
2000 | 33796.03 | 33796.03 | 0 | 0 | 0 | 0
2001 | 34262.59 | 34262.59 | 0 | 0 | 0 | 0
2002 | 34262.59 | 34262.59 | 0 | 0 | 0 | 0
2003 | 34210.59 | 34210.59 | 0 | 0 | 0 | 0
2004 | 32708.69 | 32708.69 | 0 | 0 | 0 | 0
2005 | 31309.49 | 31309.49 | 0 | 0 | 0 | 0
2006 | 30866.49 | 30866.49 | 0 | 0 | 0 | 0
2007 | 29140.49 | 29140.49 | 0 | 0 | 0 | 0
2008 | 28773.29 | 28773.29 | 0 | 0 | 0 | 0
2009 | 23743.29 | 23743.29 | 0 | 0 | 0 | 0
2010 | 21030.17 | 21030.17 | 0 | 0 | 0 | 0
2011 | 20673.47 | 20673.47 | 0 | 0 | 0 | 0
2012 | 20649.47 | 20649.47 | 0 | 0 | 0 | 0
2013 | 20124.47 | 20124.47 | 0 | 0 | 0 | 0
2014 | 20015.47 | 20015.47 | 0 | 0 | 0 | 0
2015 | 18636.67 | 18636.67 | 0 | 0 | 0 | 0
2016 | 19677.05 | 19677.05 | 0 | 0 | 0 | 0
2017 | 18984.19 | 18984.19 | 0 | 0 | 0 | 0
2018 | 19803.35 | 19803.35 | 0 | 0 | 0 | 0
2019 | 19577.05 | 19577.05 | 0 | 0 | 0 | 0
2020 | 20039.94 | 19732.64 | 0 | 306 | 0 | 1.3
2021 | 21206.94 | 19732.64 | 0 | 1083 | 390 | 1.3