## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
December 10, 2020

## Slide 2
Project Portfolio Update
  Recent / Upcoming Project Implementations
  2020 Release Targets
  2021 Release Targets
  ESR and DGR Pre-Passport Projects
  2020 Project Spending Forecast
  Priority/Rank Options for Revision Requests with Impacts
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Implementations
2020 November Release – Off-Cycle Complete
  SCR804 – ERCOT GridGeo Access for Transmission Operators – 11/12/2020
  RIOO – RARF Replacement – View/Update – Follow-Up Release – 11/13/2020
  Enterprise Content Management System (ECMS) Phase 2 – 11/16/2020
2020 December Release – Off-Cycle In Flight
  MMS/OS Tech Refresh – reschedule in progress (see 12/8/2020 Market Notice)
2020 December Release – R6 – 12/8/2020 – 12/10/2020 In Flight
  SCR806 – Adding QSE and DME Information to Disclosure Reports
  NPRR978(b) – Alignment with Amendments to PUCT Substantive Rule 25.505
    Non-Forecast Zone scope
2021 February Release – R1 – 2/6/2020 – 2/8/2020 In Flight
  NPRR974 – Capacity Insufficiency Operating Condition Notice (OCN) Transparency
  NPRR978(c) – Alignment with Amendments to PUCT Substantive Rule 25.505
    Forecast Zone scope
  NOGRR195 – Generator Voltage Control Tolerance Band
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2020 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/4 – 2/6 | April 3/31 – 4/2 | May 5/26 – 5/29 | August 8/4 – 8/6 | October 10/13 – 10/15 | December 12/8 – 12/10
NPRR873 SCR797 NPRR877 Ph2 NPRR968 NPRR943 EMIL Web Interface NPRR863 FFR NPRR960 NOGRR187 OBDRR011 | SCR802 NPRR928 NPRR929 NPRR978(a) NPRR988 NPRR953 | NPRR856 NPRR884 OBDRR006 SCR803 NPRR887 NPRR907 NPRR985 RMGRR163 NPRR837 NPRR930(a) NPRR933 RRGRR021 | NPRR935(a) NPRR951 NPRR977 NPRR955 NOGRR183 SCR781(a) RRGRR016 RRGRR019 | MIS Go-Live SCR804 RIOO R2 MMS/OS Refresh | SCR806 NPRR978(b)
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
3/1
NPRR930(a) – O&M portion
NPRR935(a) – Sections 4.2.2 (1) (6), 4.2.5
NPRR935(b) – Sections 2.1, 2.2, 4.2.3
NPRR978(a) – Initial report decommissions
NPRR978(b) – Non-Forecast Zone scope
PGRR070(b) – Remaining PGRR language
SCR781(a) – View / Edit capability
MMS/OS Upgrade “Chill”
MMS/OS Upgrade “Freeze”
ü
ü
ü
December
Off-Cycle
1/1
E
E
1/19
E
ü
ü
ü
CMM Release 2a
1/30
8/1
November
RIOO – 9/3
RARF Go-Live - View/Update
ü
ü
ü
ü
ü
ü
ü
ü
ü
5/1
ü
7/1
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
10/1
ü
ü
ü
ü

## Slide 5: 2021 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/6 – 2/8 | April 4/3 – 4/5 | May 5/29 – 5/31 | August 8/7 – 8/9 | October 10/15 – 10/17 | December 12/11 – 12/14
NPRR902 NPRR974 NPRR978(c) NOGRR195 | NPRR902 NPRR905 NPRR971 NPRR986 NPRR1043 | NPRR829 NPRR904 NPRR1006 NPRR930 NPRR962 NPRR974 NPRR998 NPRR1019 OBDRR009 |  | NPRR829 SCR781(b) | FFR Advancement (NPRR863 FFR) NPRR1015 NPRR863 ECRS NPRR1015
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
NPRR978(c) – Forecast Zone scope
SCR781(b) – “Add” capability
TBD Items | 2018 | 2019 / 2020 / 2021
 | NPRR825(b), NPRR867, NPRR841 | RRs: 826, 857, 879, 885, 918, 935(b), 936, 939, 941, 962, 965, 1020, 1030, PGRR066, SCR799, SCR800, SCR805
E
E
E
P
P
I
I
P
P
E
E
E
E
On Hold
2024 Go-Lives
RIOO – Q4 2021
RARF Add Functionality Go-Live
TBD Go-Live
E
SCR804
Go-Live – 3/18/2021
TO training in Feb.
I
Impacts of the MMS/OS Tech Refresh delay on other projects is being evaluated
ECMS – May
Market Info & Grid Info to new platform
Improved dashboards and displays
Replace NoticeBuilder
ECMS – Dec.
Combine ERCOT.com and MIS
Improved search
New navigation

## Slide 6: ESR and DGR Pre-Passport Projects
On 10/16/2020, ERCOT initiated two projects to deliver several Revision Requests relating to ESR and DGR
  PR353-01 BES Combo Model Implementation Strategy (now in Planning phase)
    NPRR963 – Base Point Deviation Settlement & Deployment Performance Metrics for ESRs (Combo Model)
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    NPRR989 – BESTF-1 ESR Technical Requirements
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    NPRR1026 – BESTF-7 Self-Limiting Facilities and Self-Limiting Resources
    NPRR1038 – BESTF-8 Limited Exemption from Reactive Power Requirements for Certain ESRs
    NOGRR204 – Related to NPRR989, BESTF-1
    NOGRR208 – Related to NPRR1002, BESTF-5
    OBDRR017 – Related to NPRR987, BESTF-3
    PGRR081 – Related to NPRR1026, BESTF-7
    RRGRR023 – Related to NPRR1002, BESTF-5
  PR354-01 DGR/DESR Implementation Strategy (now in Planning phase)
    NPRR917 – Nodal Pricing for SODGs and SOTGs
    NPRR1016 – Clarify Requirements for DGRs and Distribution Energy Storage Resources (DESRs)
    PGRR082 – Revise Section 5 and Establish Small Generation Interconnection Process *
    RRGRR026 – Related to NPRR1016, Clarify Requirements for DGRs and DESRs
Since these projects are merging multiple RRs, it will take a few months before target go-live dates are established for these two projects (gate to Execution target is February 2021)
BES: Battery Energy Storage
DGR: Distributed Generation Resource
ESR: Energy Storage Resource

## Slide 7: 2020 Project Spending
2020 PPL Budget = $29.0M
“Potential Demand” represents internal ERCOT projects that have not been fully approved

## Slide 8: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR995 | RTF-6 Create Definition and Terms for Settlement Only Energy Storage | TBD | TBD | Additional time requested to complete IA Expect to post IA for review at January PRS
NPRR1034 | Frequency-Based Limits on DC Tie Imports or Exports | 2021 | 3280 | $35k–$55k, 4–6 months Impact Areas: Grid Displays, NoticeBuilder, Reporting, MIS Add to end of 2021 list (funded by Southern Cross – work into the plan at a time consistent with conditions outlined in the IA [similar to NPRR857])
NPRR1050 | Change to the Summer Commercial Operations Date Deadline for Including Planned Generation Capacity in Reports on the CDR | N/A | N/A | <$5k O&M – no project required
NPRR1051 | Removal of the Price Floor Applied to Day-Ahead Settlement Point Prices | 2021 | 2705 | $10k–$20k, 3–5 months Impact Areas: MMS Risk of conflicts with RTC/BES/DGR Rank 2705 puts this NPRR in the “High” range of the “Consider When Resources are Available” prioritization category
PPL Rank Information
Next available 2021 Rank in Business Strategy = 3280
Next available Rank in Regulatory = 320
Options for…