| PGRR Number | 088 | PGRR Title | Include Financial Security Amount in the Monthly Generator Interconnection Status Report |
| --- | --- | --- | --- |

| Date | December 18, 2020 |
| --- | --- |

| Submitter’s Information |  |
| --- | --- |
| Name | Bill Barnes |
| E-mail Address | bill.barnes@nrg.com |
| Company | Reliant Energy Retail Services LLC |
| Phone Number | 512-691-6137 |
| Cell Number | 315-885-5925 |
| Market Segment | Independent Retail Electric Provider |

Comments

Reliant Energy Retail Services LLC (Reliant) files these comments on PGRR088, Include Financial Security Amount in the Monthly Generator Interconnection Status Report, to incorporate feedback from the Transmission Service Providers (TSPs) to clarify the entity responsible for providing the financial security information and to clarify that either party to the Interconnection Agreement can request confidentiality.  These comments were reviewed at the December 16th, 2020, Planning Working Group (PLWG) meeting and no other feedback was provided on the language.

Revised Cover Page Language

None

Revised Proposed Guide Language

5.5.4	Notification to ERCOT Concerning Certain Project Developments

(1)	The following submissions shall be provided to ERCOT via the online Resource Integration and Ongoing Operations (RIOO) system:

(a)	The TSP must submit a change request via the online RIOO system within ten Business Days upon completion of the following events:

(i)	Signing of the FIS study scope agreement; and

(ii)	Funding of the FIS study scope agreement.

(b)	The TSP must submit a change request via the online RIOO system to transmit a copy of the signed SGIA to ERCOT within ten Business Days of execution.

(c)	The TSP must submit a change request via the online RIOO system within ten Business Days of execution, a copy of any financially binding agreement between the IE and the TSP under which the interconnection for a Generation Resource will be constructed.

(d)	The TSP must submit a change request via the online RIOO system within ten Business Days after it receives both a notice to proceed with construction of the interconnection for the Generation Resource and the financial security sufficient to fund the interconnection facilities pursuant to either agreement addressed in items (b) or (c) above.  ERCOT will include in the monthly Generator Interconnection Status report the name of the interconnecting TSP and the total amount of financial security sufficient to fund the interconnection facilities as provided by the TSP except when it is designated confidential in the Interconnection Agreement filed with the Public Utility Commission of Texas (PUCT).

(e)	An MOU or EC must submit a change request via the online RIOO system confirming the Entity’s intent to construct and operate a proposed Generation Resource and interconnect such Generation Resource to its own transmission system.

(f)	Except for IEs proposing to interconnect Generation Resources powered by wind or photovoltaic solar energy, the IE must submit a change request via the online RIOO system to provide Section 8, Attachment B, Declaration of Adequate Water Supplies, for each proposed Generation Resource within ten Business Days of securing the relevant water supply rights, or, for Resources that do not require a water supply right to operate (other than wind or photovoltaic solar), within ten Business Days of executing the SGIA.