## Slide 1: ESR and DGR Pre-Passport Projects
On 10/16/2020, ERCOT initiated two projects to deliver several Revision Requests relating to ESR and DGR
  PR353-01 BES Combo Model Implementation (now in Planning phase)
    NPRR963 – Base Point Deviation Settlement & Deployment Performance Metrics for ESRs (Combo Model)
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    NPRR989 – BESTF-1 ESR Technical Requirements
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    NPRR1026 – BESTF-7 Self-Limiting Facilities and Self-Limiting Resources
    NPRR1038 – BESTF-8 Limited Exemption from Reactive Power Requirements for Certain ESRs
    NOGRR204 – Related to NPRR989, BESTF-1
    NOGRR208 – Related to NPRR1002, BESTF-5
    OBDRR017 – Related to NPRR987, BESTF-3
    PGRR081 – Related to NPRR1026, BESTF-7
    RRGRR023 – Related to NPRR1002, BESTF-5
  PR354-01 DGR/DESR Implementation (now in Planning phase)
    NPRR917 – Nodal Pricing for SODGs and SOTGs
    NPRR1016 – Clarify Requirements for DGRs and Distribution Energy Storage Resources (DESRs)
    NPRR1052 – Load Zone Pricing for Settlement Only Storage Prior to NPRR995 Implementation
    PGRR082 – Revise Section 5 and Establish Small Generation Interconnection Process *
    RRGRR026 – Related to NPRR1016, Clarify Requirements for DGRs and DESRs
Since these projects are merging multiple RRs, it will take a few months before target go-live dates are established for these two projects (gate to Execution target is February 2021)
BES: Battery Energy Storage
DGR: Distributed Generation Resource
ESR: Energy Storage Resource
Red text = New addition since last report

## Slide 2: NPRR 1016 – Pre-Passport DGR Implementation Timeline
Kicked-off
Oct 2020
Gate to Execution
Feb 2021
Go-Live Dec 2021 (revised goal)
Previous target
go-live
Q2/2022